## Baseline Scenario
Sample Use and Adoption Report Scenario
Sample Use and Adoption Scenario – BASELINE REPORT
Tribe Called Qwest (TCQ) received $275,000 to conduct a Use and Adoption grant. With the funds, the Tribe plans to provide broadband subscriptions, purchase Internet capable devices, and conduct trainings.
Because TCQ's period of performance begins on November 1, 2022, the first period reported in their Baseline Report will only cover five months instead of six. The Year 1, Period 1 column will reflect the following dates: 11/1/2022–3/31/2022. The Year 1, Period 2 column will encompass six months, and the Year 2, Period 1 column will encompass the final month of their project.
There are 80 Tribal households (of which 25 are at or below 150% of the poverty line), 5 Tribal businesses, and 6 community anchor institutions within Tribe Called Qwest’s service area. With TBCP funds, the Tribe will purchase one year of subsidized broadband for all 80 Tribal households, 2 Tribal businesses (a gas station and convenience shop), and 3 CAIs (the Tribe’s government office, community center, and health center). Of the 80 households, 30 are already served with speeds of 25/3. The remaining 50 are serviceable but do not currently have service due to an inability to afford customer premise equipment (CPE), monthly Internet payments, and/or Internet capable devices. All tribal businesses and CAIs within the funded service area are serviceable but do not have access to minimum qualifying service. The subsidized service will provide speeds of 100/20 Mbps or greater.
The Tribe also plans to purchase and distribute broadband devices. All 80 households will receive one $1,000 laptop, which is intended to be used for telework and remote learning purposes. Each of the 50 households that do not currently have broadband service, 2 businesses, and 3 CAIs will receive a router and other customer premise equipment necessary to connect to the Internet ($100 per household, business, or CAI). Eight desktop computers ($1,500 each) will be procured for the Tribe’s CAIs: 3 computers for the government office, 4 computers for the community center, and 1 computer for the health center. Finally, the Tribe will purchase 20 tablets (each worth $300) for Tribal staff.
The average household size for Tribal homes within Tribe Called Qwest’s service area is 4; therefore, the Tribe calculates that 120 individuals (30 households x 4 individuals per household) had access to telework, online learning, and telehealth service prior to receiving grant funds. After connecting the 50 households that did not previously have Internet service, the Tribe estimates that 320 individuals (80 households x 4 individuals per household) will have access to these services.
Two new positions—an IT Director and an IT Assistant—will be created as part of the grant. Tribe Called Qwest plans to hold one workforce development training for Tribal staff (estimated attendance of 25) and three digital literacy trainings for Tribal members (estimated attendance of 100 per training).
There are four schools within Tribe Called Qwest’s service area, including one high-school with an enrollment of 180. The Tribe estimates that 45 individuals will successfully exit high-school with a diploma or GED during the lifetime of their TBCP grant and that all 4 schools will engage in a hybrid learning model (partially remote, partially in-person).
The Tribe will hire contractors to install the CPE and conduct the workforce development and digital literacy trainings.
Simplified Project Plan
|  | Year 1 Period 1 | Year 1 Period 2 | Year 2 Period 1
| Procure and distribute laptops | X
| Procure and distribute computers | X
| Procure and distribute routers/CPE | X
| Procure and distribute tablets | X
| Install CPE | X | X
| Purchase Internet subscriptions |  | X
| Conduct workforce development training | X
| Conduct digital literacy training | X | X | X
| Hire IT Director and IT Assistant | X
Summary of Use & Adoption Solutions and Outcomes:
● 80 broadband subscriptions for Tribal households for a period of one year
o 30 subscriptions for previously served households
o 50 subscriptions for previously unserved households
o 25 subscriptions for households at or below 150% of the poverty line
● 2 broadband subscriptions for Tribal businesses
● 3 broadband subscriptions for Tribal CAIs
● 80 laptops for Tribal households at $1,000 per unit
● 55 routers/CPE for unserved Tribal households, businesses, and CAIs at $100 per unit
● 8 computers for Tribal CAIs at $1,500 per unit
● 20 tablets for Tribal staff at $300 per unit
● 2 new positions
● 1 workforce development training with an estimated attendance of 25
● 3 digital literacy trainings with an estimated attendance of 100 for each training

## Baseline Report
OMB Control No. 0660-0047 Expiration Date: 07/31/2025
TRIBAL BROADBAND CONNECTIVITY PROGRAM BASELINE REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: | Tribe Called Qwest |  |  |  |  | Award Identification Number: |  |  |  | NT22TBC0000000
| Recipient Street Address: | 123 Qwest Lane |  |  |  |  | Report Submission Date (MM/DD/YYYY): |  |  |  | 2022-12-01
| City, State, Zip Code: | Washington, DC, 20230
| DUNS/UEI Number: | 123456789
| Period of Performance Start Date (MM/DD/YYYY): | 2022-11-01 |  |  |  |  | Period of Performance End Date (MM/DD/YYYY): |  |  |  | 2023-10-31
| Report Period Start Date (MM/DD/YYYY): | 2022-11-01 |  |  |  |  | Report Period End Date (MM/DD/YYYY): |  |  |  | 2022-12-01
BROADBAND USE & ADOPTION AND INFRASTRUCTURE MILESTONES/KEY INDICATORS
INFRASTRUCTURE PROJECT MILESTONE CATEGORIES
1 | Please use the table provided to report your projected cumulative totals for each semi-annual reporting period within each year of your project. Year One begins on your award start date. The cumulative total is based on the expenditure of your project budget and should be reported cumulatively from the award start date through the end of each semi-annual period. For example, if you expect to complete a particular milestone within the first three periods of your project, the third period and all subsequent periods should state the projected final count.
| MILESTONE CATEGORIES |  | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
|  |  | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
1a. Overall Project
1b. Environmental Assessment
1c. Network Design
1d. Rights Of Way
1e. Construction Permits And Other Approvals
1f. Site Preparation
1g. Equipment Procurement
1h. Network Build (all components - owned, leased, Indefeasible Rights of Use, etc.)
1i. Equipment Deployment
1j. Network Testing
1k. Other (please specify)
NETWORK BUILD PROGRESS
2 | Please use the table provided to report your projected cumulative totals for each semi-annual reporting period within each year of your project. Year One begins on your award start date. The cumulative total is based on the expenditure of your project budget and should be reported cumulatively from the award start date through the end of each semi-annual period. For example, if you expect to complete a particular milestone within the first three periods of your project, the third period and all subsequent periods should state the projected final count.
| NETWORK BUILD PROGRESS | MIDDLE OR LAST MILE | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
|  |  | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
2a. Number of new fiber miles (aerial or underground)
2b. Number of fiber miles leased
2c. Number of existing fiber miles upgraded
2d. Number of new wireless links
2e. Number of new towers
2f. Number of new interconnection points
2g. Number of signed agreements with broadband wholesalers or last mile providers
2h. Number of potential agreements (i.e., agreements currently being negotiated) with broadband wholesalers or last mile providers (This number should NOT be reported cumulatively)
2i. Obtained licenses: 2.5 (EBS), 3.5 (CBRS)
2j. Other (please specify)
BROADBAND INFRASTRUCTURE KEY INDICATORS
3 | Please use the following table to provide projected cumulative totals for each subscriber type and speed category for your project. Except as indicated, information is reported cumulatively from start of award through the end of each semi-annual period. Please write “NA” if your project does not include an indicator.
| PROJECTED NUMBER OF SUBSCRIBERS AND SPEED |  | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
| SUBSCRIBER TYPE | SPEED TYPE | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
| 3a. Unserved Tribal Households | Number of Unserved Tribal Households connected to broadband infrastructure
Number of Unserved Tribal Households connected to broadband infrastructure at speeds of at least 100/20
Number of Unserved Tribal Households connected to broadband infrastructure at speeds of at least 25/3
Number of Unserved Tribal Households connected to broadband infrastructure by copper or DSL cable line
Number of Unserved Tribal Households connected to broadband infrastructure by wireless connection
Number of Unserved Tribal Households connected to broadband infrastructure by fiber optic connection
| 3b. Tribal Households | Number of Tribal Households connected to broadband infrastructure
Number of Tribal Households connected to broadband infrastructure at speeds of at least 100/20
Number of Tribal Households connected to broadband infrastructure at speeds of at least 25/3
Number of Tribal Households connected to broadband infrastructure by copper or DSL cable line
Number of Tribal Households connected to broadband infrastructure by wireless connection
Number of Tribal Households connected to broadband infrastructure by fiber optic connection
| 3c. Tribal Households At or Below 150% of the Poverty Line | Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure
Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at minimum speeds of at least 100/20
Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at minimum speeds of 25/3
Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by copper or DSL cable line
Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by wireless connection
Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by fiber optic connection
| 3d. Tribal Community Anchor Institutions (CAIs) | Number of Tribal CAIs connected to broadband infrastructure
Number of Tribal CAIs connected to broadband infrastructure at minimum speeds of at least 100/20
Number of Tribal CAIs connected to broadband infrastructure at minimum speeds of at least 25/3
Number of Tribal CAIs connected to broadband infrastructure by copper or DSL cable line
Number of Tribal CAIs connected to broadband infrastructure by wireless connection
Number of Tribal CAIs connected to broadband infrastructure by fiber optic connection
| 3e. Tribal Businesses | Number of Tribal Businesses connected to broadband infrastructure
Number of Tribal Businesses connected to broadband infrastructure at speeds of at least 100/20
Number of Tribal Businesses connected to broadband infrastructure at speeds of at least 25/3
Number of Tribal Businesses connected to broadband infrastructure by copper or DSL cable line
Number of Tribal Businesses connected to broadband infrastructure by wireless connection
Number of Tribal Businesses connected to broadband infrastructure by fiber optic connection
BROADBAND USE & ADOPTION KEY INDICATORS
4 | Please use the following table to provide projected cumulative totals for each subscriber and access type for your project. Except as indicated, information is reported cumulatively from the award start date through the end of each semi-annual period. Please write “NA” if your project does not include an indicator.
| PROJECTED NUMBER OF SUBSCRIBERS AND SPEED |  | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
| BENEFICIARY TYPE | ACCESS TYPE | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
| 4a. Unserved Tribal Households | Number of Unserved Tribal Households passed/serviceable | 50 | 50 |  | 50
|  | Number of Unserved Tribal Households with new access | 0 | 50 |  | 50
| 4b. Tribal Households | Number of Tribal Households passed/serviceable | 80 | 80 |  | 80
|  | Number of Tribal Households with new access | 0 | 50 |  | 50
| 4c. Tribal Households At or Below 150% of the Poverty Line | Number of Tribal Households At or Below 150% of the Poverty Line passed/serviceable | 25 | 25 |  | 25
|  | Number of Tribal Households At or Below 150% of the Poverty Line with new access | 0 | 25 |  | 25
| 4d. Tribal Businesses | Number of Tribal Businesses passed/serviceable | 5 | 5 |  | 5
|  | Number of Tribal Businesses with new access | 0 | 2 |  | 2
| 4e. Tribal Community Anchor Institutions | Number of Tribal Community Anchor Institutions passed/serviceable | 6 | 6 |  | 6
|  | Number of Tribal Community Anchor Institutions with new access | 0 | 3 |  | 3
BROADBAND USE & ADOPTION DEMOGRAPHIC INDICATORS
5 | Please use the following table to report the demographic information of funded service areas. For each, list projected cumulative total for each population. This information should be reported cumulatively from award start date through the end of each semi-annual reporting period. Please write “NA” if your project does not include an indicator.
| DEMOGRAPHIC INDICATORS |  | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
| SUBSCRIBER TYPE | ESTIMATED POPULATION IN SERVICE AREA | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
| 5a. Unserved Tribal Population | Number of Unserved Native American/Alaska Native/Native Hawaiian Households in funded service area | 50 | 0 |  | 0
|  | Number of Unserved Native American/Alaska Native/Native Hawaiian Tribal Businesses in funded service area | 5 | 3 |  | 3
|  | Number of Unserved Native American/Alaska Native/Native Hawaiian Community Anchor Institutions in funded service area | 6 | 3 |  | 3
|  | Number of Unserved Native American/Alaska Native/Native Hawaiian Households At or Below 150% of the Poverty Line in funded service area | 25 | 0 |  | 0
| 5b. Tribal Population | Number of Tribal Households in funded service area | 80 | 80 |  | 80
|  | Number of Tribal Businesses in funded service area | 5 | 5 |  | 5
|  | Number of Tribal Community Anchor Institutions in funded service area | 6 | 6 |  | 6
|  | Number of Tribal Households At or Below 150% of the Poverty Line in funded service area | 25 | 25 |  | 25
BROADBAND USE & ADOPTION WORKFORCE INDICATORS
6 | Please use the following table to provide estimated totals for each workforce expansion and development indicator. For each indicator, report the estimated figure for the corresponding project period. This information should be reported cumulatively from the award start date through the end of each semi-annual reporting period. Please write “NA” if your project does not include an indicator.
| WORKFORCE INDICATORS |  | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
| OUTCOMES | QUESTIONS | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
| 6a. Telework | Number of individuals with ability to telework prior to receiving TBCP grant funds | 120
|  | Number of individuals with ability to telework after receiving TBCP grant funds | 120 | 320 |  | 320
| 6b. New Positions | Number of new positions created | 2 | 2 |  | 2
|  | Number of new positions filled | 2 | 2 |  | 2
| 6c. Participation in Workforce Development Trainings | Number of individuals who attended workforce development training event | 25 | 25 |  | 25
| 6d. Workforce Development Trainings | Number of workforce development training events held | 1 | 1 |  | 1
BROADBAND USE & ADOPTION EDUCATIONAL SUCCESS INDICATORS
7 | Please use the following table to provide anticipated totals for each educational attainment indicator. For each indicator, report the projected number for all corresponding project periods. This information should be reported cumulatively from the award start date through the end of each semi-annual reporting period. Please write “NA” if your project does not include an indicator.
| EDUCATIONAL SUCCESS INDICATORS |  | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
| OUTCOMES | QUESTIONS | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
| 7a. Access to Online Learning | Number of individuals with ability to participate in online learning prior to receiving TBCP grant funds | 120
|  | Number of individuals with ability to participate in online learning after receiving TBCP grant funds | 120 | 320 |  | 320
| 7b. Participation in Online Learning | Number of individuals who attend online learning classes | 50 | 175 |  | 175
|  | Number of individuals who attend virtual/in-person school activities | 60 | 200 |  | 200
| 7c. Parental Participation in School Activities | Number of parents/legal guardians who attend virtual/in-person school activities | NA | NA |  | NA
| 7d. High School Enrollment and Completion | Number of individuals enrolled in high school | 180 | 180 |  | 180
|  | Number of individuals who successfully exited high school program with degree (diploma/GED) | 0 | 45 |  | 45
| 7e. School Participation in Remote Learning | Number of schools in program | 4 | 4 |  | 4
|  | Number of schools engaged in remote learning model | 0 | 0 |  | 0
| 7f. School Participation in In-Person Learning | Number of schools in program | 4 | 4 |  | 4
|  | Number of schools engaged in in-person learning model | 0 | 0 |  | 0
| 7g. School Participation in Hybrid Learning | Number of schools in program | 4 | 4 |  | 4
|  | Number of schools engaged in hybrid learning model | 4 | 4 |  | 4
BROADBAND USE & ADOPTION TELEHEALTH INDICATORS
8 | Please use the following table to provide anticipated totals for each telehealth expansion indicator. For each indicator, list the projected number for all corresponding project periods. This information should be reported cumulatively from the award start date through the end of each semi-annual reporting period. Please write “NA” if your project does not include an indicator.
| TELEHEALTH INDICATORS |  | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
| OUTCOMES | QUESTIONS | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
| 8a. Access to Telehealth Services | Number of individuals with ability to participate in telehealth services prior to receiving TBCP grant funds | 120
|  | Number of individuals with ability to participate in telehealth service after receiving TBCP grant funds | 120 | 120 |  | 120
| 8b. New Access to Telehealth Services | Number of individuals with new access to telehealth services | 0 | 200 |  | 200
| 8c. Telehealth Appointments Scheduled | Estimated number of telehealth appointments scheduled | NA | NA |  | NA
BROADBAND USE & ADOPTION DIGITAL INCLUSION INDICATORS
9 | Please use the following table to provide anticipated totals for each digital inclusion indicator. For each indicator, list the projected number for all corresponding project periods. This information should be reported cumulatively from the award start date through the end of each semi-annual period. Please write “NA” if your project does not include an indicator.
| DIGITAL INDICATORS |  | Year 1 |  |  | Year 2 |  | Year 3 |  |  |  | Year 4 |  | Year 5
| OUTCOMES | QUESTIONS | Period 1 - Projected | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected |  | Period 2 - Projected |  | Period 1 - Projected | Period 2 - Projected | Period 1 - Projected | Period 2 - Projected
| 9a. Participation in Affordable Broadband Connectivity Program | Number of households in affordable broadband connectivity programs | 0 | 80 |  | 80
| 9b. Digital Literacy Trainings | Number of digital literacy training events held | 1 | 2 |  | 3
| 9c. Tribal Programs Transitioned to Online Platform | Number of Tribal programs transitioned to online platform now (after receiving TBCP grant funds) | NA | NA |  | NA
| 9d. Devices Distributed to Individuals | Number of individuals given device | 100 | 100 |  | 100
| 9e. Devices Distributed to Households | Number of households given device | 80 | 80 |  | 80
| 9f. Devices Distributed to Other Entities (i.e., community anchor institutions, schools, Tribal businesses) | Number of other entities given device | 5 | 5 |  | 5
TYPE OF INTERNET DEVICES
10 | Please describe the Internet Devices you will acquire using TBCP funding.
| Device Type |  | Number of Devices |  |  |  |  | Total Cost
| Laptop |  | 80 |  |  |  |  | 80000
| Computer |  | 8 |  |  |  |  | 12000
| Router |  | 55 |  |  |  |  | 5500
| Tablet |  | 20 |  |  |  |  | 6000
TYPE OF COLLABORATORS
11 | Please list all projected funded and unfunded collaborators in table below.
COLLABORATORS
| Collaborator Organization Type | Collaborator Organization Name | Collaborator POC Name |  | Collaborator POC Email |  |  |  | Funded or Unfunded Collaboration
| Contractor | CPE Installers, Inc. | Adam Smith |  | Asmith@CPEinstallers.com |  |  |  | Funded
| Contractor | Technology Training Solutions | Jane Train |  | Jtrain@TTS.org |  |  |  | Funded
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | [5 empty] | Telephone (area code, number and extension): |  |  |  | 123-456-7890 ext 1
Quincy Tippe
| Signature of Certifying Official: | [5 empty] | Email Address: |  |  |  | Q.Tippe@TCQ.org
[7 empty] | Date: |  |  |  | 2022-12-01

## Performance (Tech) Scenario
Sample Use and Adoption Report Scenario
Sample Use and Adoption Scenario – PERFORMANCE (TECHNICAL) REPORT
Tribe Called Qwest is now five months into their one-year project. The Tribe is preparing to submit their Year 1, Period 1 Performance (Technical) Report.
As planned and outlined in the baseline report, the Tribe was able to procure and distribute all 80 laptops, 8 desktop computers, and 20 tablets in Year 1, Period 1. Due to vendor delays, the tribe has only received 25 of the 55 units of CPE. Broadband subscriptions have not yet been purchased; therefore, no unserved households, businesses, or CAIs have received new access. Similarly, the number of individuals with access to remote telework, online learning, and telehealth service are limited to the number of individuals that had prior access to the Internet.
The Tribe anticipated that two new positions—an IT Director and IT Assistant—would be created and filled by the end of Year 1, Period 1. The Tribe initiated both positions but was only able to hire an IT Director. More applications were received than expected for the IT Assistant position and interviews were not concluded as of the end of the Period.
In the baseline report, the Tribe also anticipated holding one workforce development training (with an estimated attendance of 25) and one digital literacy training (estimated attendance of 100) during Year 1, Period 1. Both trainings occurred according to schedule. However, attendance at the workforce development training was lower than expected (actual attendance of 19) due to a bout of Covid-19 that broke out in the government building and infected Tribal staff. Interest in the digital literacy training was higher than expected, leading to a larger attendance than anticipated (actual attendance of 164).
Because the Year 1, Period 1 activities occurred during the Winter and early Spring, no individuals exited high school during the project period. The Tribe anticipated that all four schools in the project area—one high school, one middle school, and two elementary schools—would engage in hybrid learning during Year 1, Period 1. The high school and middle school did engage in hybrid learning; however, because of poor Internet connectivity and difficulties associated with conducting virtual lessons for K-5 students, the two elementary schools switched to a fully in-person learning model. None of the schools were entirely virtual.
TCQ had their Finance Director cross-check the Budget Execution section of their Performance (Technical) Report with their Federal Financial Report (SF-425) before submission.

## Performance (Technical) Report
OMB Control No. 0660-0047 Expiration Date: 07/31/2025
TRIBAL BROADBAND CONNECTIVITY PROGRAM PERFORMANCE (TECHNICAL) REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: | Tribe Called Qwest |  |  |  | Award Identification Number: |  |  |  | NT22TB00000000
| Recipient Street Address: | 123 Qwest Lane |  |  |  | Report Submission Date (MM/DD/YYYY): |  |  |  | 2022-04-15
| City, State, Zip Code: | Washington, DC, 20230 |  |  |  | Final Report: |  |  |  | Yes
| DUNS/UEI Number: | 123456789 | [7 empty] | No
| Period of Performance Start Date (MM/DD/YYYY): | 2022-11-01 |  |  |  | Period of Performance End Date (MM/DD/YYYY): |  |  |  | 2023-10-31
| Report Period Start Date (MM/DD/YYYY): | 2022-11-01 |  |  |  | Report Period End Date (MM/DD/YYYY): |  |  |  | 2023-03-31
BROADBAND USE & ADOPTION AND INFRASTRUCTURE MILESTONES/KEY INDICATORS
INFRASTRUCTURE PROJECT MILESTONE CATEGORIES
1 | Please use the table provided to indicate the percentage of completion for cumulative activities conducted with TBCP grant funds. The percentage of completion is based on the expenditure of your project budget and should be reported cumulatively from the award start date through the end of each semi-annual reporting period. For example, if you expect to complete a particular milestone within the first three periods of your project, the third period and all subsequent periods should state 100%. Please also provide a brief description (100 words or less) of the primary activities involved in meeting each milestone (a single description should be provided for each milestone, covering all periods in years one through N). Please write “NA” if your project does not include an activity. If necessary, please insert additional milestones at the bottom of the chart.
MILESTONE CATEGORIES
|  |  | Percent Complete |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
1a. Overall Project
1b. Environmental Assessment
1c. Network Design
1d. Rights Of Way
1e. Construction Permits And Other Approvals
1f. Site Preparation
1g. Equipment Procurement
1h. Network Build (all components - owned, leased, Indefeasible Rights of Use, etc.)
1i. Equipment Deployment
1j. Network Testing
1k. Other (please specify)
1l. Please describe significant project accomplishments during this reporting period funded through TBCP grant. (600 words or less)
1m. Please describe any challenges to achieving project accomplishments during this reporting period funded through TBCP grant. (600 words or less)
NETWORK BUILD PROGRESS
2 | Please use the following table to report key indicators and progress of your Infrastructure project. Except as indicated, information should be reported cumulatively from the award start date through the end of the semi-annual period. Please write “NA” if your project does not include this indicator.
NETWORK BUILD PROGRESS
|  |  | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
2a. Number of new fiber miles (aerial or underground)
2b. Number of fiber miles leased
2c. Number of existing fiber miles upgraded
2d. Number of new wireless links
2e. Number of new towers
2f. Number of new interconnection points
2g. Number of signed agreements with broadband wholesalers or last mile providers
2h. Number of potential agreements (i.e., agreements currently being negotiated) with broadband wholesalers or last mile providers (This number should NOT be reported cumulatively)
2i. Obtained licenses: 2.5 (EBS), 3.5 (CBRS)
2j. Other (please specify)
BROADBAND INFRASTRUCTURE KEY INDICATORS
3 | Please use the following table to provide the cumulative totals for each subscriber category and speed type for your project. Except as indicated, information should be reported cumulatively from award start date through the end of the semi-annual period. Please write “NA” in narrative text if your project does not include this indicator.
PROJECTED NUMBER OF SUBSCRIBERS AND SPEED
| SUBSCRIBER TYPE | SPEED TYPE | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 3a. Unserved Tribal Households | Number of Unserved Tribal Households connected to broadband infrastructure
Number of Unserved Tribal Households connected to broadband infrastructure at speeds of at least 100/20
Number of Unserved Tribal Households connected to broadband infrastructure at speeds of at least 25/3
Number of Unserved Tribal Households connected to broadband infrastructure by copper or DSL cable line
Number of Unserved Tribal Households connected to broadband infrastructure by wireless connection
Number of Unserved Tribal Households connected to broadband infrastructure by fiber optic connection
| 3b. Tribal Households | Number of Tribal Households connected to broadband infrastructure
Number of Tribal Households connected to broadband infrastructure at speeds of at least 100/20
Number of Tribal Households connected to broadband infrastructure at speeds of at least 25/3
Number of Tribal Households connected to broadband infrastructure by copper or DSL cable line
Number of Tribal Households connected to broadband infrastructure by wireless connection
Number of Tribal Households connected to broadband infrastructure by fiber optic connection
| 3c. Tribal Households At or Below 150% of the Poverty Line | Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure
Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at minimum speeds of at least 100/20
Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at minimum speeds of 25/3
Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by copper or DSL cable line
Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by wireless connection
Number of Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by fiber optic connection
| 3d. Tribal Community Anchor Institutions | Number of Tribal Community Anchor Institutions connected to broadband infrastructure
Number of Tribal Community Anchor Institutions connected to broadband infrastructure at minimum speeds of at least 100/20
Number of Tribal Community Anchor Institutions connected to broadband infrastructure at minimum speeds of at least 25/3
Number of Tribal Community Anchor Institutions connected to broadband infrastructure by copper or DSL cable line
Number of Tribal Community Anchor Institutions connected to broadband infrastructure by wireless connection
Number of Tribal Community Anchor Institutions connected to broadband infrastructure by fiber optic connection
| 3e. Tribal Businesses | Number of Tribal Businesses connected to broadband infrastructure
Number of Tribal Businesses connected to broadband infrastructure at speeds of at least 100/20
Number of Tribal Businesses connected to broadband infrastructure at speeds of at least 25/3
Number of Tribal Businesses connected to broadband infrastructure by copper or DSL cable line
Number of Tribal Businesses connected to broadband infrastructure by wireless connection
Number of Tribal Businesses connected to broadband infrastructure by fiber optic connection
BROADBAND USE & ADOPTION KEY INDICATORS
4 | Please use the following table to provide the cumulative totals for each beneficiary category and access type for your project. Except as indicated, information should be reported cumulatively from award start date through the end of the semi-annual period. Please write “NA” in narrative text if your project does not include this indicator.
PROJECTED NUMBER OF SUBSCRIBERS AND SPEED
| BENEFICIARY TYPE | ACCESS TYPE | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 4a. Unserved Tribal Households | Number of Unserved Tribal Households passed/serviceable | 50 |  |  |  | NA
|  | Number of Unserved Tribal Households with new access | 0 |  |  |  | NA
| 4b. Tribal Households | Number of Tribal Households passed/serviceable | 80 |  |  |  | NA
|  | Number of Tribal Households with new access | 0 |  |  |  | NA
| 4c. Tribal Households At or Below 150% of the Poverty Line | Number of Tribal Households At or Below 150% of the Poverty Line passed/serviceable | 25 |  |  |  | NA
|  | Number of Tribal Households At or Below 150% of the Poverty Line with new access | 0 |  |  |  | NA
| 4d. Tribal Businesses | Number of Tribal Businesses passed/serviceable | 5 |  |  |  | NA
|  | Number of Tribal Businesses with new access | 0 |  |  |  | NA
| 4e. Tribal Community Anchor Institutions | Number of Tribal Community Anchor Institutions passed/serviceable | 6 |  |  |  | NA
|  | Number of Tribal Community Anchor Institutions with new access | 0 |  |  |  | NA
BROADBAND USE & ADOPTION DEMOGRAPHIC INDICATORS
5 | Please use the following table to provide demographics of funded service areas. For each, list the cumulative total for each population. This information should be reported cumulatively from award start date through the end of each semi-annual reporting period. Please write “NA” if your project does not include this indicator.
DEMOGRAPHIC INDICATORS
| SUBSCRIBER TYPE | ESTIMATED POPULATION IN SERVICE AREA | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 5a. Unserved Tribal Population | Number of Unserved Native American/Alaska Native/Native Hawaiian Households in funded service area | 50 |  |  |  | NA
|  | Number of Unserved Native American/Alaska Native/Native Hawaiian Tribal Businesses in funded service area | 5 |  |  |  | NA
|  | Number of Unserved Native American/Alaska Native/Native Hawaiian Community Anchor Institutions in funded service area | 6 |  |  |  | NA
|  | Number of Unserved Native American/Alaska Native/Native Hawaiian Households At or Below 150% of the Poverty Line in funded service area | 25 |  |  |  | NA
| 5b. Tribal Population | Number of Tribal Households in funded service area | 80 |  |  |  | NA
|  | Number of Tribal Businesses in funded service area | 5 |  |  |  | NA
|  | Number Tribal Community Anchor Institutions in funded service area | 6 |  |  |  | NA
|  | Number of Tribal Households At or Below 150% of the Poverty Line in funded service area | 25 |  |  |  | NA
BROADBAND USE & ADOPTION WORKFORCE INDICATORS
6 | Please use the following table to provide totals for each workforce outcome and question. For each question, list the total for each project period. This information should be reported cumulatively from the award start date through the end of each semi-annual period. Please write “NA” if your project does not include this indicator.
WORKFORCE INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 6a. Telework | Number of individuals with ability to telework prior to receiving TBCP grant funds | 120 |  |  |  | NA
|  | Number of individuals with ability to telework after receiving TBCP grant funds | 0 |  |  |  | NA
| 6b. New Positions | Number of new positions created | 2 |  |  |  | NA
|  | Number of new positions filled | 1 |  |  |  | More applications were submitted than expected for the IT Assistant postion; therefore, we were unable to conclude the interview and hiring process by the end of Year 1, Period 1. We expect to hire and onboard an IT Assistant in the first months of Year 2, Period 2.
| 6c. Participation in Workforce Development Trainings | Number of individuals who attended workforce development training event | 19 |  |  |  | The workforce development training was intended for Tribal employees. There was an outbreak of Covid in the Tribal government building a few days before the workforce training took place, and the virus quickly spread among Tribal administrative staff. Several employees fell ill and were unable to attend the training.
| 6d. Workforce Development Trainings | Number of workforce development training events held | 1 |  |  |  | NA
BROADBAND USE & ADOPTION EDUCATIONAL SUCCESS INDICATORS
7 | Please use the following table to provide totals for each educational success outcome and question. For each question, list total for each project period. This information should be reported cumulatively from the award start date through the end of each semi-annual period. Please write “NA” if your project does not include this indicator.
EDUCATIONAL SUCCESS INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 7a. Access to Online Learning | Number of individuals with ability to participate in online learning prior to receiving TBCP grant funds | 120 |  |  |  | NA
|  | Number of individuals with ability to participate in online learning after receiving TBCP grant funds | 120 |  |  |  | NA
| 7b. Participation in Online Learning | Number of individuals who attended online learning classes | 50 |  |  |  | NA
|  | Number of individuals who attended virtual/in-person school activities | 60 |  |  |  | NA
| 7c. Parental Participation in School Activities | Number of parents/legal-guardians who attended virtual/in-person school activities | NA |  |  |  | NA
| 7d. High School Enrollment and Completion | Number of individuals enrolled in high school | 180 |  |  |  | NA
|  | Number of individuals who successfully exited high school program with degree (diploma/GED) | 0 |  |  |  | NA
| 7e. School Participation in Remote Learning | Number of schools in program | 4 |  |  |  | NA
|  | Number of schools engaged in remote learning model | 0 |  |  |  | NA
| 7f. School Participation in In-Person Learning | Number of schools in program | 4 |  |  |  | NA
|  | Number of schools engaged in in-person learning model | 2 |  |  |  | The 2 elemetary schools within our service area had previoulsy been conducting hybrid (virtual and in-person) lessons. However, because of improving public health condtions, limited Internet connectivity, and the inherent difficulties in leading online lessons for young (K-5) learners, our governing body elected for the 2 elementary schools to revert to an entirley in-person learning model.
| 7g. School Participation in Hybrid Learning | Number of schools in program | 4 |  |  |  | NA
|  | Number of schools engaged in hybrid learning model | 2 |  |  |  | We originally anticipated that all 4 schools within our service area–1 high school, 1 middle school, and 2 elementary schools–would engage in hybrid learning. However, the 2 elementary schools reverted to an in-person model (see note above), resulting in a reduction of the number of schools engaged in hybrid learning from 4 to 2.
BROADBAND USE & ADOPTION TELEHEALTH INDICATORS
8 | Please use the following table to provide totals for each telehealth outcome and question. For each question, list total for each project period. This information should be reported cumulatively from the award start date through the end of each semi-annual period. Please write “NA” if your project does not include this indicator.
TELEHEALTH INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 8a. Access to Telehealth Services | Number of individuals with ability to participate in telehealth services prior to receiving TBCP grant funds | 120 |  |  |  | NA
|  | Number of individuals with ability to participate in telehealth service after receiving TBCP grant funds | 120 |  |  |  | NA
| 8b. New Access to Telehealth Services | Number of individuals with new access to telehealth services | 0 |  |  |  | NA
| 8c. Telehealth Appointments Scheduled | Estimated number of telehealth appointments scheduled | NA |  |  |  | NA
BROADBAND USE & ADOPTION DIGITAL INCLUSION INDICATORS
9 | Please use the following table to provide totals for each digital inclusion outcome and question. For each question, list total for each project period. This information should be reported cumulatively from the award start date through the end of each semi-annual period. Please write “NA” if your project does not include this indicator.
DIGITAL INCLUSION INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 9a. Participation in Affordable Broadband Connectivity Program | Number of households in affordable broadband connectivity program | 0 |  |  |  | NA
| 9b. Digital Literacy Trainings | Number of digital literacy training events held | 1 |  |  |  | NA
| 9c. Tribal Programs Transitioned to Online Platform | Number of Tribal programs transitioned to online platform previously (before receiving TBCP grant funds) | NA |  |  |  | NA
|  | Number of Tribal programs transitioned to online platform now (after receiving TBCP grant funds) | NA |  |  |  | NA
| 9d. Devices Distributed to Individuals | Number of individuals given device | 100 |  |  |  | NA
| 9e. Devices Distributed to Households | Number of households given device | 80 |  |  |  | NA
| 9f. Devices Distributed to Other Entities (i.e., community anchor institutions, schools, Tribal businesses) | Number of other entities given device | 5 |  |  |  | NA
TYPE OF INTERNET DEVICES
10 | Please describe the Internet Devices you have acquired using TBCP funding.
| Device Type |  | Number of Devices |  |  |  | Total Cost
| Laptop |  | 80 |  |  |  | 80000
| Computer |  | 8 |  |  |  | 12000
| Router |  | 25 |  |  |  | 2500
| Tablet |  | 20 |  |  |  | 6000
TYPE OF COLLABORATORS
11 | Please list all funded and unfunded collaborators in table below.
COLLABORATORS
| Collaborator Organization Type | Collaborator Organization Name | Collaborator POC Name | Collaborator POC Email |  |  |  | Funded or Unfunded Collaboration
| Contractor | CPE Installers, Inc | Adam Smith | Asmith@CPEInstallers.com |  |  |  | Funded
| Contractor | Technology Training Solutios | Jane Train | Jtrain@TTS.org |  |  |  | Funded
INFRASTRUCTURE DEPLOYMENT BUDGET EXECUTION DETAILS
12 | Please provide details below on your total budget and total funding expended to date for each budget element, including detailed disbursements of federal funds obligated from project inception through end of this reporting period. Figures should be reported cumulatively from the award start date to the end of the applicable reporting period.
| ACTUAL BUDGET |  |  |  | Federal Funds Expended |  |  |  |  | Total Funds Expended
| 12a. Administrative and legal expenses | [8 empty] | 0
| 12b. Land, structures, rights-of way, appraisals, etc. | [8 empty] | 0
| 12c. Relocation expenses and payments | [8 empty] | 0
| 12d. Architectural and engineering fees | [8 empty] | 0
| 12e. Other architectural and engineering fees | [8 empty] | 0
| 12f. Project inspection fees | [8 empty] | 0
| 12g. Site work | [8 empty] | 0
| 12h. Demolition and removal | [8 empty] | 0
| 12i. Construction | [8 empty] | 0
| 12j. Equipment | [8 empty] | 0
| 12k. Miscellaneous | [8 empty] | 0
| Subtotal |  |  |  | 0 |  |  |  |  | 0
| 12l. Contingencies |  |  |  | 0 |  |  |  |  | 0
| Totals |  |  |  | 0 |  |  |  |  | 0
BROADBAND USE & ADOPTION BUDGET EXECUTION DETAILS
13 | Please provide details below on your total budget and total funding expended to date for each budget element, including detailed disbursements of federal funds obligated from project inception through end of this reporting period. Figures should be reported cumulatively from the award start date to the end of the applicable reporting period.
| GRANT PROGRAM, FUNCTION, OR ACTIVITY |  |  |  | Actual Budget |  |  |  |  | Total Funds Expended
| 13a. Personnel |  |  |  | 60000 |  |  |  |  | 25000
| 13b. Fringe Benefits |  |  |  | 6000 |  |  |  |  | 2500
| 13c. Travel | [8 empty] | 0
| 13d. Equipment |  |  |  | 103500 |  |  |  |  | 0
| 13e. Supplies |  |  |  | 20000 |  |  |  |  | 15000
| 13f. Contractual |  |  |  | 2000 |  |  |  |  | 1000
| 13g. Construction | [8 empty] | 0
| 13h. Other |  |  |  | 83500 |  |  |  |  | 82500
| 13i. Total Direct Charges (sum of 13a thru 13h) |  |  |  | 275000 |  |  |  |  | 126000
| 13j. Indirect Charges | [8 empty] | 0
| 13k. Totals (sum of 13i+13j) |  |  |  | 275000 |  |  |  |  | 126000
OTHER INDICATORS
14 | Please use the following table to provide the maximum upload and download speed in Mbps for each question. Information should be reported as of the report date. Please write "N/A" if your project does not include this indicator.
| Project Speed | [7 empty] | Upload |  | Download
| Outcome |  | Questions
| 14a. Maximum available speed upon project completion |  | What is the maximum available speeds for Tribal Households in your eligible area? | [5 empty] | 0 |  | 0
|  |  | What is the maximum available speeds for Tribal Businesses in your eligible area? | [5 empty] | 0 |  | 0
|  |  | What is the maximum available speeds for Tribal CAIs in your eligible area? | [5 empty] | 0 |  | 0
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: |  |  |  |  | Telephone (area code, number and extension): |  |  |  | 123-456-7890 ext 1
Quincy Tippe
| Signature of Certifying Official: |  |  |  |  | Email Address: |  |  |  | Q.Tippe@TCQ.org
[6 empty] | Date: |  |  |  | 2023-09-30

## Annual Scenario
Sample Use and Adoption Report Scenario
Sample Use and Adoption Scenario – ANNUAL REPORT
Tribe Called Qwest is now one year into their one-year project and all grant activities are complete. The Tribe is preparing to submit their Year 1 Annual Report.
Over the past year, TCQ has procured and distributed 80 laptops to Tribal households; 55 routers/CPE to unserved Tribal households, businesses, and CAIs; 8 computers to Tribal CAIs; and 20 tablets to Tribal staff.
TCQ has also purchased broadband subscriptions for 80 Tribal households, 2 Tribal businesses, and 3 Tribal CAIs. Thirty of these households had an Internet connection at speeds of 25/3 prior to the receipt of grant funds. The remaining 50 households, 2 businesses, and 3 CAIs were previously unserved. A contractor (CPE Installers, Inc) has installed Customer Premise Equipment in the 50 unserved households, 2 unserved businesses, and 3 unserved CAIs. At the end of Year 1, all 80 households, 2 businesses, and 3 CAIs were connected to broadband at speeds of 100/20 Mbps or greater.
During Year 1, TCQ held 1 workforce development training for Tribal staff and 3 digital literacy trainings. The Tribe hired the contractor Technology Training Solutions to design and implement the trainings. Two positions–an IT Director and IT Assistant–were created and filled.

## Annual Report
OMB Control No. 0660-0047 Expiration Date: 07/31/2025
TRIBAL BROADBAND CONNECTIVITY PROGRAM ANNUAL REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: | Tribe Called Qwest | Award Identification Number: |  | NT22TBC0000000
| Recipient Street Address: | 123 Qwest Lane | Report Submission Date (MM/DD/YYYY): |  | 2023-10-31
| City, State, Zip Code: | Washington, DC, 20230
| DUNS/UEI Number: | 123456789
| Period of Performance Start Date (MM/DD/YYYY): | 2022-11-01 | Period of Performance End Date (MM/DD/YYYY): |  | 2023-10-31
| Report Period Start Date (MM/DD/YYYY): | 2022-11-01 | Report Period End Date (MM/DD/YYYY): |  | 2023-10-31
1 | Provide the number of locations or geographic areas at which broadband service was provided using the grant funds. (Please attach associated shapefiles of geographic areas) (600 words or less)
During the past year, TCQ provided subsidized broadband service at 85 locations: 80 Tribal households (50 of which were unserved prior to this project), 2 Tribal businesses, and 3 Tribal community anchor institutions.
2 | Please describe each service provided with grant funds. (600 words or less)
Over the past year, TCQ procured and distributed 80 laptops to Tribal households; 55 routers/CPE to unserved Tribal households, businesses, and CAIs; 8 computers to Tribal CAIs; and 20 tablets to Tribal staff. TCQ also purchased broadband subscriptions for 80 Tribal households, 2 Tribal businesses, and 3 Tribal CAIs. Thirty of these households had an Internet connection at speeds of 25/3 prior to the receipt of grant funds. The remaining 50 households, 2 businesses, and 3 CAIs were previously unserved. A contractor (CPE Installers, Inc) installed Customer Premise Equipment in the 50 unserved households, 2 unserved businesses, and 3 unserved CAIs. At the end of Year 1, all 80 households, 2 businesses, and 3 CAIs were connected to broadband at speeds of 100/20 Mbps or greater. During Year 1, TCQ also held one workforce development training for Tribal staff and three digital literacy trainings. The Tribe hired the contractor Technology Training Solutions to design and implement the trainings. Two positions–an IT Director and IT Assistant–were created and filled.
3 | If applicable, please list subcontractors and describe how they expended funds. (600 words or less)
Two contractors received grant funds during the reporting period. CPE Installers, Inc. received grant funds to install Customer Premise Equipment in 50 households, 2 businesses, and 3 CAIs. Technology Training Solutions was hired to design and implement 1 workforce development training and 3 digital literacy trainings.
4 | Please describe how the recipient and subrecipient (if applicable) expended the funds. (600 words or less)
TCQ procured and distributed 80 laptops to Tribal households; 55 routers/CPE to unserved Tribal households, businesses, and CAIs; 8 computers to Tribal CAIs; and 20 tablets to Tribal staff. TCQ also purchased broadband subscriptions for 80 Tribal households, 2 Tribal businesses, and 3 Tribal CAIs.
5 | If applicable, please list each subrecipients that received a subgrant through funding. (600 words or less)
NA
6 | Please provide the barriers to broadband use and adoption or broadband infrastructure deployment work that you experienced during the reporting period of this award to date. What steps did you take to address them? (600 words or less)
Over the past year, barriers to broadband Use and Adoption activities included supply chain bottlenecks which delayed the delivery of CPE, a bout of Covid-19 that prevented several Tribal employees from attending the workforce development training, and a slower-than-anticipated timeline for CPE installation. There is little that TCQ could do to address the CPE supply chain bottleneck. Instead, TCQ took advantage of the procurement delay to meet with the contractor CPE Installers Inc. and hammer out an installation plan and timeline for Tribal households, businesses, and CAIs. CPE installation itself was delayed by internal circumstances at CPE Installers, Inc. Fortunately, TCQ and CPE Installers built sufficient lag time into the CPE installation plan that this did not require an extension of the project timeline. TCQ estimated that 25 Tribal employees would attend the workforce development training. However, due to a covid outbreak in the government building in the week prior to the training, only 19 staff members were able to attend. To address this, TCQ and Technology Training Solutions, the contractor that planned and conducted the workforce development training, agreed to record the training. The recording was then sent to all Tribal employees.
7 | Please describe whether or not your organization connected NOFO purpose areas to broadband adoption and use or broadband infrastructure deployment work. (600 words or less)
TCQ promoted affordable broadband programs and broadband adoption activities by providing one year of subsidized internet service for 80 households, 2 businesses, and 3 CAIs. TCQ also purchased Customer Premise Equipment for 50 households, 2 businesses, and 3 CAIs that could not afford it. TCQ promoted broadband adoption by holding 3 well-attended digital literacy trainings. Due to the purchase of 80 laptops, 8 computers, and 20 tablets, more people in the service area can access telehealth or remote learning.
8 | Please describe your project's achieved accomplishments during this reporting period. (600 words or less)
During the reporting period, TCQ held three digital literacy trainings that were highly-attended (164 attendees at the first training, 113 at the second training, and 107 at the third training). The project also created two new jobs (IT Director and IT Assistant) which were both filled by Tribal members. Grant funds were used to provide devices and subsidized broadband service to 80 households, 2 businesses, and 3 CAIs. Fifty of the households were previously unserved; of these 50, 25 are at or below 150% of the poverty line.
9 | Using the Excel spreadsheet template titled "TBCP Reports Addendum A", please provide an updated count of Households within each of the eligible tribal block groups along with their Location ID that you connected to your network. The locations should match and conform to the Federal Communications Commission (FCC) Broadband Serviceable Location Fabric, which is a unique identifier for the geographic coordinates, and where available, the address(es) associated with each location. Please be sure to select 'Annual Report' checkbox when completing the addendum.
10 | Using the Excel spreadsheet template titled "TBCP Reports Addendum B", please provide an updated count of Tribal Businesses within each of the eligible tribal block groups along with their Location ID that you connected to your network. The locations should match and conform to the Federal Communications Commission (FCC) Broadband Serviceable Location Fabric, which is a unique identifier for the geographic coordinates, and where available, the address(es) associated with each location. Please be sure to select 'Annual Report' checkbox when completing the addendum.
11 | Using the Excel spreadsheet template titled "TBCP Reports Addendum C", please provide an updated count of Community Anchor Institutions (CAIs) within each of the eligible tribal block groups along with their Location ID that you connected to your network. The locations should match and conform to the Federal Communications Commission (FCC) Broadband Serviceable Location Fabric, which is a unique identifier for the geographic coordinates, and where available, the address(es) associated with each location. Please be sure to select 'Annual Report' checkbox when completing the addendum.
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: |  |  | Telephone (area code, number and extension): |  | 123-456-7890 ext 1
Quincy Tippe
| Signature of Certifying Official: |  |  | Email Address: |  | Q.Tippe@TCQ.org
|  |  |  | Date: |  | 2023-09-30

## TBCP Reports Addendum A
OMB Control No. 0660-0047 Expiration Date: 07/31/2025
TRIBAL BROADBAND CONNECTIVITY PROGRAM REPORTS ADDENDUM A
Recipient Organization: |  | Tribe Called Qwest |  |  | Award Identification Number: |  |  |  | NT22TBC0000000
Recipient Street Address: |  | 123 Qwest Lane |  |  | Report Submission Date (MM/DD/YYYY): |  |  |  | 2023-10-31
City, State, Zip Code: |  | Washington, DC, 20230 |  |  | DUNS/UEI Number: |  |  |  | 123456789
Reporting Period Start Date (MM/DD/YYYY): |  | 2022-11-01 |  |  | Report Type: |  |  |  | Baseline Report
Reporting Period End Date (MM/DD/YYYY): |  | 2023-10-31 | [6 empty] | Annual Report
Household Locations in the Service Area
The Location ID is the Fabric ID associated with the Federal Communications Commission maps required by the Broadband Deployment Broadband Deployment Accuracy and Technology Availability (DATA) Act, Pub. L. No. 116-130, 134 Stat. 228 (2020) (codified at 47 U.S.C. §§ 641-646) (Broadband DATA Maps). The “location_id” data element is a unique identifier for the location served. A Location ID should be included for each location in the Broadband Serviceable Location Fabric when the Fabric is made available to filers. Number of units refers to one location that has multiple units within that one location. Please insert rows at the bottom of the table to report additional location data if needed.
Location ID | Street Address | City | State | ZIP |  | Latitude |  | Longitude |  |  | Tribal Block Group | # of Units
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | Quincy Tippe |  |  |  |  | Telephone (area code, number and extension): |  |  | 123-456-7890 ext 1
| Signature of Certifying Official: | [5 empty] | Email Address: |  |  | Q.Tippe@TCQ.org
[7 empty] | Date: |  |  | 2023-09-30

## TBCP Reports Addendum B
OMB Control No. 0660-0047 Expiration Date: 07/31/2025
TRIBAL BROADBAND CONNECTIVITY PROGRAM REPORTS ADDENDUM B
Recipient Organization: |  | Tribe Called Qwest |  |  | Award Identification Number: |  |  |  | NT22TBC0000000
Recipient Street Address: |  | 123 Qwest Lane |  |  | Report Submission Date (MM/DD/YYYY): |  |  |  | 2023-10-31
City, State, Zip Code: |  | Washington, DC, 20230 |  |  | DUNS/UEI Number: |  |  |  | 123456789
Reporting Period Start Date (MM/DD/YYYY): |  | 2022-11-01 |  |  | Report Type: |  |  |  | Baseline Report
Reporting Period End Date (MM/DD/YYYY): |  | 2023-10-31 | [6 empty] | Annual Report
Tribal Business Locations in the Service Area
The Location ID is the Fabric ID associated with the Federal Communications Commission maps required by the Broadband Deployment Broadband Deployment Accuracy and Technology Availability (DATA) Act, Pub. L. No. 116-130, 134 Stat. 228 (2020) (codified at 47 U.S.C. §§ 641-646) (Broadband DATA Maps). The “location_id” data element is a unique identifier for the location served. A Location ID should be included for each location in the Broadband Serviceable Location Fabric when the Fabric is made available to filers. Number of units refers to one location that has multiple units within that one location. Please insert rows at the bottom of the table to report additional location data if needed. Number of units refers to one location that has multiple units within that one location. Please insert rows at the bottom of the table to report additional location data if needed.
Location ID | Street Address | City | State | ZIP |  | Latitude |  | Longitude |  |  | Tribal Block Group | # of Units
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | Quincy Tippe |  |  |  |  | Telephone (area code, number and extension): |  |  | 123-456-7890 ext 1
| Signature of Certifying Official: | [5 empty] | Email Address: |  |  | Q.Tippe@TCQ.org
[7 empty] | Date: |  |  | 2023-09-30

## TBCP Reports Addendum C
OMB Control No. 0660-0047 Expiration Date: 07/31/2025
TRIBAL BROADBAND CONNECTIVITY PROGRAM REPORTS ADDENDUM C
Recipient Organization: |  | Tribe Called Qwest |  |  | Award Identification Number: |  |  |  | NT22TBC0000000
Recipient Street Address: |  | 123 Qwest Lane |  |  | Report Submission Date (MM/DD/YYYY): |  |  |  | 2023-10-31
City, State, Zip Code: |  | Washington, DC, 20230 |  |  | DUNS/UEI Number: |  |  |  | 123456789
Reporting Period Start Date (MM/DD/YYYY): |  | 2022-11-01 |  |  | Report Type: |  |  |  | Baseline Report
Reporting Period End Date (MM/DD/YYYY): |  | 2023-10-31 | [6 empty] | Annual Report
Community Anchor Institution (CAI) Locations in the Service Area
The Location ID is the Fabric ID associated with the Federal Communications Commission maps required by the Broadband Deployment Broadband Deployment Accuracy and Technology Availability (DATA) Act, Pub. L. No. 116-130, 134 Stat. 228 (2020) (codified at 47 U.S.C. §§ 641-646) (Broadband DATA Maps). The “location_id” data element is a unique identifier for the location served. A Location ID should be included for each location in the Broadband Serviceable Location Fabric when the Fabric is made available to filers. Number of units refers to one location that has multiple units within that one location. Please insert rows at the bottom of the table to report additional location data if needed.
Location ID | Street Address | City | State | ZIP |  | Latitude |  | Longitude |  |  | Tribal Block Group | # of Units
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | Quincy Tippe |  |  |  |  | Telephone (area code, number and extension): |  |  | 123-456-7890 ext 1
| Signature of Certifying Official: | [5 empty] | Email Address: |  |  | Q.Tippe@TCQ.org
[7 empty] | Date: |  |  | 2023-09-30