## Baseline Report
OMB Control No. 0660-0048 Expiration Date: 07/31/2025
CONNECTING MINORITY COMMUNITIES PILOT PROGRAM BASELINE REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: | Motown State College |  |  |  | Award Identification Number: |  |  | 05-03-C14005
| Recipient Street Address: | 456 Berry Gordy Rd |  |  |  | Report Submission Date (MM/DD/YYYY): |  |  | 2022-09-15
| City, State, Zip Code: | Detroit, MI 24680 |  |  |  | DUNS/UEI Number: |  |  | 7796WER57798
| Period of Performance Start Date (MM/DD/YYYY): | 2022-08-01 |  |  |  | Period of Performance End Date (MM/DD/YYYY): |  |  | 2024-07-31
| Reporting Period Start Date (MM/DD/YYYY): | 2022-08-01 |  |  |  | Reporting Period End Date (MM/DD/YYYY): |  |  | 2022-09-14
MILESTONES/KEY INDICATORS
PROJECT MILESTONE CATEGORIES
1 | Please use the following table to project project element completion as a percentage of funds spent on project elements over the projected number of four year periods that the project element will take to complete. For project elements which fall into a project milestone category which is not listed on this table, please list this project element in row 1j. Other.
| MILESTONE CATEGORIES |  | Year 1 |  | Year 2 |  | Year 3 |  |  | Year 4
|  |  | Period 1 - Projected April 1, 2022-Sept 30, 2022 | Period 2 - Projected Oct 1, 2022-March 31, 2023 | Period 1 - Projected April 1, 2023- Sept 30, 2023 | Period 2 - Projected Oct 1, 2023-March 31, 2024 | Period 1 - Projected April 1, 2024-Sept 30, 2024 | Period 2 - Projected |  | Period 1 - Projected |  | Period 2 - Projected
| 1a. Overall Project |  | 10% | 30% | 50% | 90% | 100%
| 1b. Network Design |  | 0% | 50% | 60% | 75% | 100%
| 1c. Equipment Procurement |  | 0% | 10% | 45% | 80% | 100%
| 1d. Network Build (all components - owned, leased, Indefeasible Rights of Use, etc.) |  | 0% | 20% | 50% | 60% | 100%
| 1e. Broadband Deployment |  | 0% | 40% | 75% | 85% | 100%
| 1f. Equipment Deployment |  | 0% | 30% | 60% | 85% | 100%
| 1g. Remote Learning |  | 10% | 25% | 60% | 100% | 100%
| 1h. Anchor Community Adoption |  | 0% | 30% | 75% | 95% | 100%
| 1i. Digital Skills/Workforce Development Training |  | 20% | 40% | 70% | 100% | 100%
| 1j. Other (please specify): |  | 0% | 0% | 0% | 0% | 0%
ORGANIZATIONAL PARTNERS
2a | Please use the following table to list your organizational partners, the type of organization, the organization's role in completion of project activities, and whether or not the partner has changed their involvement or role in the project within the past six months.
| PARTNER NAME |  | Partner Type |  |  | Partner Role | [5 empty] | Change in Past Six Months?
| Supreme Consulting (MBE) |  | Non-Funded Partner |  |  | Contractor | [5 empty] | No
| MCI |  | Non-Funded Partner |  |  | Unfunded Collaborator | [5 empty] | No
| Aretha Franklin Public Library |  | Community Anchor Institution |  |  | Unfunded Collaborator | [5 empty] | No
| Digital Network Support Coalition |  | Not-for-Profit 501(c)3 |  |  | Subrecipient | [5 empty] | No
2b | If you selected "Community Anchor Institution" or "Community-Based Organization" for any of the listed partner organizations, please specify.
The Aretha Franklin Public Library will serve as a partner for Motown State College's project on Inclusive-Tech Innovation Plan. This will create a vibrant and connected community that leverages broadband to support economic growth and prosperity within the anchor communities. The library will serve as an extension of Motown State as it will host numerous training opportunities for the community in the city of Detroit. The community will be able to take online classes and training linked to Motown State College and will have the opportunity to rent laptops and other IT equipment for training-related projects.
REMOTE LEARNING INFRASTRUCTURE
3a | What types of technology (hardware, software, online platforms) will be deployed to facilitate and improve remote learning infrastructure?
| TECHNOLOGY NAME |  | Technology Type |  |  | Technology Description |  |  |  |  | Total Cost
| Laptop |  | Hardware |  |  | 100 Dell Laptops |  |  |  |  | 69900
| Desktop Computer |  | Hardware |  |  | 100 Dell Inspiron Desktops ($649 per desktop) |  |  |  |  | 64900
| Operating Systems |  | Software |  |  | Microsoft Windows ($199) |  |  |  |  | 199
| Server |  | Online Platform |  |  | Microsoft Azure ($65/month) |  |  |  |  | 1560
| Cloud-based software |  | Cloud Services |  |  | Salesforce ($150 per user per month) |  |  |  |  | 3600
3b | What types of professional development training will be implemented to facilitate and improve remote learning infrastructure and IT management?
| Professional Development Training Type |  |  | Number of Participants |  |  | Professional Development Training Description
| Data Analytics |  |  | 750 |  |  | Participants will earn badges from IBM, Google, Amazon (AWS), SAP and Microsoft. Students will learn about digital literacy, web design, programming, and artificial intelligence.
| Cloud Computing Training |  |  | 700 |  |  | Participants will understand the convergence of development, security, and operations to seamlessly integrate security within a continuous delivery pipeline.
| SAP Administration |  |  | 300 |  |  | Participants will learn SAP Architecture, Managing SAP System Administration Daily Tasks, Configuration and Administration of SAP systems, and SAP Basic Administration.
| Software Engineering |  |  | 200 |  |  | Participants will undergo an intense six-week boot camp to learn how to build, test, and deploy a front-end web application, and set up continuous integration and continuous delivery pipelines to deploy a react application.
ANCHOR COMMUNITY ADOPTION
4a | List the anchor community activities your project will carry out over the course of the grant period of performance.
| Anchor Community Activity |  | Census Tract |  |  | Target Beneficiary | [5 empty] | Target Output for the Grant Period of Performance
| Digital Literacy and Software Applications Training |  | 6019000100, 6019005408 |  |  | Senior citizens from the anchor communities | [5 empty] | 325
BROADBAND INTERNET AND DEVICES
5a | Describe the Internet Devices which will be acquired with CMC-provided funds (excluding mobile phones).
| Number of Devices | Loan or Donation? | Device Type |  |  | Total Cost |  |  |  | Recipient
| 100 | Loan | Tablet Device |  |  | 79990 |  |  |  | Student
| 100 | Loan | Laptop/Computer |  |  | 37000 |  |  |  | College/University Staff
| 100 | Loan | WiFi Hotspot |  |  | 27000 |  |  |  | Student
| 100 | Donation | Other (Please Explain) |  |  | 15500 |  |  |  | College/University Staff
5b | If you defined any Device Type as "Other," please explain.
Routers will be placed in various offices across campus.
5c | Describe the Broadband Subscriptions which will be acquired with CMC-provided funds.
| Number of Subscriptions | Provider Type | Average Cost to Recipient |  | Total Cost to Institution (If Applicable) |  | Recipient |  |  |  |  | Speed
| 100 | Mobile (i.e. Hotspot) | 40 |  | 18000 |  | Student |  |  |  |  | 30 Mbps
| 100 | Fiber | 40 |  | 22000 |  | College/University Staff |  |  |  |  | 25/3 Mbps
| 55 | Fixed Wireless | 37 |  | 24420 |  | MBE Employees |  |  |  |  | 75Mbps down/10Mbps up
| 3 | Satellite | 6000 |  | 18000 |  | Not-for-Profit 501(c)3 Employees |  |  |  |  | 100 Mbps
| 100 | DSL | 100 |  | 200000 |  | Faculty |  |  |  |  | 50 Mbps
| 100 | Cable | 150 |  | 180000 |  | Faculty |  |  |  |  | 500 Mbps
5d | Describe the Broadband Deployments which will be undertaken with CMC-provided funds.
| Location | Location Type | Network Type |  | Deployment Cost |  | Ongoing Cost |  |  | Description
| Science and Tech Branch | On-Campus | Fixed Wireless |  | 11000 |  | College/University Staff |  |  | Acquire IT infrastructure and 5G bandwidth.
| Satellite Campuses | On-Campus | Fiber |  | 13000 |  | College/University Staff |  |  | Deploy fiber-optic cable and wireless technology.
DIGITAL SKILLS AND WORKFORCE DEVELOPMENT
6a | What types of digital skills or workforce development will be offered?
| Type of Training | Number of Participants | Participants Who Completed Training |  | Participant Type |  | Training Objectives |  | Training Objectives Met? |  |  | College Credit Awarded?
| Computer Fundamentals | 300 | N/A |  | At-Risk Youth |  | Teaching inner-city students the core functions of a computer |  | No |  |  | Yes
| Digital Marketing | 200 | N/A |  | College Student |  | Teaching college students how to leverage digital channels to connect with current or prospective customers |  | No |  |  | Yes
| UX/UI | 225 | N/A |  | K-12 Student |  | 6 week bootcamp course teaching all stages of design process |  | No |  |  | Yes
6b | Will participants be awarded a certification upon completion of training? If so, describe the certification.
We are in the process of setting up and offering these trainings. We anticipate 300 students for Computer Fundamentals, in which the students will receive 3 credit hours. 200 for Digital Marketing-Google Certification and a UX/UI Master Certificate for UX/Ui training.
MEASUREMENT AND EVALUATION
7a | Describe performance measurements which will be utilized to evaluate the project’s effectiveness or the benefits delivered to project beneficiaries.
| Project Purpose |  | Benefit |  |  | Beneficiary |  |  |  | How Will This Be Measured?
| Increase Digital and Technical Workforce |  | Prepare students and youth to be able to effectively secure employment in the IT Field. |  |  | Students |  |  |  | Tracking the number of students that completed the course and secured a job in IT within 6-8 months.
| Remote Learning |  | Students will be able to take classes virtually increasing enrollment (hybrid) |  |  | Institution |  |  |  | Data showing how many students are hybrid and how many are FT remote students.
7b | Describe performance measurements which will be utilized to evaluate the project's impact on digital equity.
| Project Purpose |  | Benefit |  |  | Beneficiary |  |  |  | How Will This Be Measured?
| Internet-connected devices-laptops, tablets, computers |  | Providing equipment to underserved community |  |  | Community Members |  |  |  | Digital Landscape metric-measures the presence of tech components that allow people within a community to fully participate digitally.
| High Speed Internet Access |  | Upgrade current internet access |  |  | Institution |  |  |  | Students, faculty and staff utilization of faster internet access.
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: |  |  |  |  | Telephone (area code, number, and extension): |  |  | 313-555-1212
Jim Shoe
| Signature of Certifying Official: |  |  |  |  | Email Address: |  |  | jim.shoe@motown.edu
[6 empty] | Date: |  |  | 2022-09-15