## Performance (Technical) Report
OMB Control No. 0660-0048 Expiration Date: 07/31/2025
CONNECTING MINORITY COMMUNITIES PILOT PROGRAM PERFORMANCE (TECHNICAL) REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: | Motown State College |  |  |  | Award Identification Number: |  | 05-03-C14005
| Recipient Street Address: | 456 Berry Gordy Rd |  |  |  | Report Submission Date (MM/DD/YYYY): |  | 2022-10-28
| City, State, Zip Code: | Detroit, MI 23456 |  |  |  | Final Report |  | Yes
| DUNS/UEI Number: | 7796WER57798 | [5 empty] | No
| Period of Performance Start Date (MM/DD/YYYY): | 2022-08-01 |  |  |  | Period of Performance End Date (MM/DD/YYYY): |  | 2024-07-31
| Report Period Start Date (MM/DD/YYYY): | 2022-08-01 |  |  |  | Report Period End Date (MM/DD/YYYY): |  | 2022-09-30
GENERAL PROJECT INFORMATION
1a | What key milestones have been achieved in the past six months?
During the past two months, Motown State College has finalized contractual agreements and expenses: Training, Technology, Laptops, and Broadband. We also implemented new IT infrastructure, procured and distributed laptops and launched applications for the IT/Digital Skills Training Program. During the past two months, Motown State College has finalized contractual agreements with project partners and vendors in the project areas of Training, Technology, Laptops, and Broadband. We implemented new IT infrastructure, including hiring 2 new IT assistants, training all new and existing IT employees, and beginning steps to upgrade the campus WiFi network. We procured and distributed 100 laptops to students in need after completing a process to identify the students most in need of broadband connectivity equipment. Finally, we launched 4 courses for the IT & Digital Skills Training Program.
1b | What barriers or challenges have you encountered in the course of achieving your project milestones?
More than 20 percent of households in Detroit County--almost 60,000 households -- have no internet access at all. About 9 percent (5,400) have only mobile internet or dial-up service. The Motown State College network infrastructure has not been updated significantly since 2013, resulting in most network devices being end-of-life or outdated. Currently, Motown State is leveraging a 2G bandwidth from its internet service provider to support its IT infrastructure, Learning Management System, and business applications. The Motown State College network infrastructure has not been updated significantly since 2013, resulting in most network devices being end-of-life or outdated. Currently, Motown State is leveraging a 2G bandwidth from its internet service provider to support its IT infrastructure, Learning Management System, and business applications. Beginning other project activities, including launching the laptop and hotspot distribution program and launching new training courses before the campus WiFi network has been fully upgraded, has proven challenging.
1c | Please describe any issues anticipated during the next reporting period that may impact planned progress against the project milestones. In particular, please identify any areas or issues where technical assistance from NTIA may be useful.
We do not anticipate servicing the 60,000 households with the upgrading of internet access. Shortage of workers, equipment needed, and colder weather will prevent us from providing this upgrade. We anticipate within the next six months to service an estimated 10,000-12,000 households. However, with fall and winter coming, there will be issues completing this milestone. In addition to providing loaner laptops to students, we have also purchased a cache of hotspots for students to "Check out" from the library for mobile and at-home use. We have not yet determined a plan to manage these hotspots, address any problems that may occur, and identify a Motown employee to manage the devices. We may require technical assistance from NTIA to do so.
1d | What notable successes have been achieved in the project, thus far?
Students at Motown State College now have increased access to devices, remote access via Close2Home, and access to a 24X7 support facility. In addition, students in the English as a Second Language program have access of laptops, and all students have the ability to access a cache of hot spots for at-home and mobile use. Students now can connect to on-campus and remote educational resources and services. Lastly, the IT Infrastructure network is currently being upgraded to 5G and we have purchased 300 laptops to assist students with remote learning.
1e | Please describe significant project milestones planned for completion during the next reporting period.
During the next reporting period, we will host an employer Technology Sandbox Symposium, host Tech Apprenticeship Technical Assistance, and host Geek Squad Academy for Middle School and High School students.
1f | Is this project a consortium project? |  | No
ORGANIZATIONAL PARTNERS
2a | Please use the following table to list your organizational partners, the type of organization, the organization's role in completion of project activities, and whether or not the partner has changed their involvement or role in the project within the past six months.
| PARTNER NAME |  | Partner Type |  |  | Partner Role |  |  | Change in Past Six Months?
| Digital Network Support Coalition |  | Not-for-Profit 501(c)3 |  |  | Subrecipient |  |  | No
| Supreme Consulting (MBE) |  | Non-Funded Partner |  |  | Contractor |  |  | No
| Aretha Franklin Public Library |  | Community Anchor Institution |  |  | Unfunded Collaborator |  |  | No
2b | If you selected "Community Anchor Institution" or "Community-Based Organization" for any of the listed partner organizations, please specify.
The Aretha Franklin Public Library will serve as a partner for Motown State College project on Inclusive-Tech Innovation Plan which will create a vibrant and connected community that leverages broadband to support economic growth and prosperity within the anchor communities. The library will serve as an extension of Motown State as it will host numerous training opportunities for the community in the city of Detroit. The community will be able to take online classes and training linked to Motown State College and will have the opportunity to rent laptops and other IT equipment for training-related projects.
2c | What barriers or challenges have you encountered in the course of working with any of these project partners that may impact the goals or outcomes of the project?
Initially, the library did not have have enough computers or laptops to handle the volume of individuals that will be utilizing the training opportunities. In addition, some of the computers were older and couldn't handle the capacity of work that would needed. Therefore, the library needed an additional 15 computers to replace six older computers and nine brand new to support the training. There was a backorder for Dell desktop PCs causinga six-week delay. We don't anticipate any further delays.
REMOTE LEARNING INFRASTRUCTURE
3a | What types of technology (hardware, software, online platforms) have you deployed to facilitate and improve remote learning infrastructure?
| TECHNOLOGY NAME |  | Technology Type |  |  | Technology Description |  |  | Total Cost
| Desktop Computer |  | Hardware |  |  | 8 Dell Inspiron Desktop ($649 per desktop) |  |  | 64900
| Operating Systems |  | Software |  |  | Microsoft Windows ($199) |  |  | 199
| Server |  | Online Platform |  |  | Microsoft Azure ($65 per month) |  |  | 1560
3b | What types of professional development training have you implemented to facilitate and improve remote learning infrastructure and IT management?
| Professional Development Training Type |  |  | Number of Participants |  |  | Professional Development Training Description
| Data Analytics |  |  | 100 |  |  | Participants will earn badges from IBM, Google, Amazon (AWS), SAP and Microsoft. Students will learn about digital literacy, web design, programming, and artifical intelligence.
| Cloud Computing Training |  |  | 250 |  |  | Participants will understand the convergence of development, security, and operations to seamlessly integrate security within a continuous delivery pipeline.
| SAP Administration |  |  | 75 |  |  | Participants will learn SAP Architecture, Managing SAP System Administration Daily Tasks, Configuration and Administration of SAP systems, and SAP Basic Administration.
3c | What percentage of classes are currently offered remotely? |  | 43%
3d | What percentage of classes are currently offered using a hybrid model? |  | 57%
ANCHOR COMMUNITY ADOPTION
4a | List the anchor community activities your project has completed in the last six months, and the results of those activities.
| Anchor Community Activity |  | Census Tract |  |  | Target Beneficiary |  |  | Target Output for Next Six Months
| Digital Literacy and Software Applications Training |  | 6019000100, 6019005408 |  |  | Senior citizens from the anchor communities |  |  | 150
4b | Please use the following table to record the requested values for indicators of community broadband adoption. The field "Other outcome not listed here:" may be edited to record an indicator of community adoption you wish to provide to NTIA that may not have been specifically requested.
| Community Adoption Indicator |  | Baseline |  |  |  | Current
| Number of participants enrolled in community-based |  | 125 |  |  |  | 250
| Number of participants who have completed community-based programs |  | N/A |  |  |  | The program is ongoing
| If applicable, number of participants who have obtained jobs following completion of a community-based program |  | N/A |  |  |  | The program will be completed May 2023
| Number of anchor community members with a broadband subscription |  | 200 |  |  |  | 680
| Other outcome not listed here: |  | N/A |  |  |  | N/A
4c | Did the 15-mile radius present any barriers or challenges in the delivery of services, scope of the project, project outcomes, etc.?
No. The only challenge was a delay in the delivery of equipment for the training programs. The scope of the project and project outcome will not be affected.
How were these barriers or challenges resolved to meet the project's expected goals?
Once the computer equipment were delivered, we do not anticipate any additional back order of the necessary computer equipment. In the future, we will utilize multiple vendors where we can purchase additonal equipment.
BROADBAND INTERNET AND DEVICES
5a | Describe the Internet Devices which have been acquired with CMC-provided funds.
| Number of Devices Purchased | Loaned or Donated? | Device Type |  |  | Total Cost |  |  | Recipient
| 100 | Loaned | WiFi Hotspot |  |  | 27000 |  |  | Student
| 100 | Donated | Other (Please Explain) |  |  | 15500 |  |  | College/University Staff
5b | If you defined any Device Type as "Other," please explain.
Routers were purchased and placed in various offices across the campus.
5c | Describe the Broadband Subscriptions which have been acquired with CMC-provided funds.
| Number of Subscriptions | Provider Type | Average Cost to Recipient |  | Total Cost to Institution (If Applicable) |  | Recipient |  | Speed
| 100 | Mobile (i.e. Hotspot) | 40 |  | 18000 |  | Student |  | 30 Mbps
| 100 | Fiber | 50 |  | 22000 |  | College/University Staff |  | 25/3 Mbps
| 3 | Satellite | 6000 |  | 18000 |  | Not-for-Profit 501(c)3 Employees |  | 100 Mbps
| 100 | Cable | 150 |  | 180000 |  | Faculty |  | 500 Mbps
5d | Describe the Broadband Deployments which have been undertaken with CMC-provided funds.
| Location | Location Type | Network Type |  | Deployment Cost |  | Ongoing Cost |  | Description
| Science and Tech Branch | On-Campus | Fixed Wireless |  | 11000 |  | College/University Staff |  | Upgrade from 3G to 5G
5e | What barriers or challenges have you encountered in the course of implementing project elements associated with the purchase and distribution of Internet Devices?
We encountered a slight delay in purchasing the latest iPads and Dell Desktop PCs. Due to these products being on back order, the purchasing was delayed by six weeks. Once we made the purchase, we encountered shipping delays from the vendors as one shipment was inadvertently shipped to one of our satellite campuses. This caused a further delay by one week.
5f | What barriers or challenges have you encountered in the course of implementing project elements associated with the purchase and distribution of broadband subscriptions?
One challenge is having the community to register/sign up for a broadband subscription. Participation has been low due to high smartphone usage. In addition, community members are uncomfortable sharing private information about themselves to sign up for subscriptions. In addition, the cost to maintain these services in dense populated areas is extremely high.
5g | What barriers or challenges have you encountered in the course of implementing project elements associated with the purchase and deployment of broadband networks?
One of the communities was in a rural area. This area did not have the necessary infrastructure to support and provide Internet connectivity. In order to upgrade the connectivity speed, this area will need to be developed to handle broadband network. We did not encounter any challenges associated with the purchase and deployment of broadband networks. We are in the process of upgrading the campus WiFi network to 5G through our current campus service provider, and there have been no barriers thus far.
DIGITAL SKILLS AND WORKFORCE DEVELOPMENT
6a | What types of digital skills or workforce development were offered?
| Type of Training | Number of Participants | Participants Who Completed Training |  | Participant Type |  | Training Objectives |  | Training Objectives Met? | College Credit Awarded?
| Computer Fundamentals | 300 | 440 |  | At-Risk Youth |  | Teaching inner-city students the core functions of a computer |  | Yes | No
| Digital Marketing | 200 | 150 |  | College Student |  | Teaching college students how to leverage digital channels to connect with current or prospective customers |  | Yes | Yes
| UX/UI | 225 | 225 |  | K-12 Student |  | 6 week bootcamp course teaching all stages of design process |  | Yes | Yes
6b | Were participants awarded a certification upon completion of training? If so, describe the certification and the number of recipients?
225 Students that completed the UX/UI Bootcamp received a Google UX Design Certificate.
6c | What barriers or challenges have you encountered in the course of implementing project elements associated with digital skills training?
We were fortunate to not encounter any challenges or barriers as the demand was extremely high. We were pleased of the high interest of at-risk youth to participate in the computer fundamentals training. The students that took the UX/UI training were excited to learn that they would receive a Goggle UX Design Certificate.
MEASUREMENT AND EVALUATION
7a | Describe performance measurements utilized to evaluate the project’s effectiveness or the benefits delivered to project beneficiaries
| Project Purpose |  | Benefit |  |  | Beneficiary |  |  | How Was This Measured?
| Increase Digital and Technical Workforce |  | Prepare students and youth to be able to effectively secure employment in the IT Field. |  |  | Students |  |  | Tracking the number of students that completed the course and secured a job in IT within 6-8 months.
| Remote Learning |  | Students will be able to take classes virtually increasing enrollment (hybrid). |  |  | Institution |  |  | Data showing how many students are hybrid and how many are FT remote students.
7b | Describe performance measurements utilized to evaluate the project's impact on digital equity.
| Project Purpose |  | Benefit |  |  | Beneficiary |  |  | How Was This Measured?
| Internet-connected devices - laptops, tablets, computers |  | Providing equipment to underserved community |  |  | Community Members |  |  | Digital Landscape Metric - measures the presence of tech components that allow people within a community to fully participate digitally.
| High Speed Internet Access |  | Upgrade current internet access |  |  | Institution |  |  | Students, faculty, and staff utilization of faster internet access.
7c | How did these activities align with your CMC project narrative goals?
The primary goals for this project are to 1) Increase the digital and technical workforce 2) Enhance Digital Inclusion and Awareness 3) Enhance Community Connectivity and Broadband Adoption 4) Enhance Remote Learning and Work by upgrading the university IT infrastructure 5) Enhance Employment Outcomes in the anchor community 6) Strengthen Minority Business Enterprises. We were able to align these activities to the project narrative goals.
7d | Are these activities on track to meet these goals within the timeline? If not, what is the plan to meet these activities' goals within the timeline?
Yes, we are on track to meet these goals within the timeline. We will be launching applications for digital skills training, small business training, as well as digital bootcamps and the purchasing of laptops and desktop PCs.
7e | If not, what steps will be implemented to meet those goals and outcomes over the next 6 months and/or by the end of the period of performance?
N/A
7f | Describe any best practices or lessons-learned obtained at this point in the period of performance of the project.
1. Establish Required Features and Resources-identify a well-defined process plan that identifies technology requirements. 2. Understanding students, community, and faculty's needs-conducting internal audits to determine how new deployment will serve the students, community, and faculty. 3. Settingintegration parameters-we fully recognized what level of integration was required during implementation by reviewing the current technology stack and identifying its associated benefits, challenges, and costs.
8 | Please provide details below on your total budget and total funding expended to date for each budget element, including detailed disbursements of federal funds obligated from project inception through end of this reporting period. Figures should be reported cumulatively from the award start date to the end of the applicable reporting period.
| Grant Program, Function, or Activity |  |  |  | ACTUAL BUDGET |  |  | Total Funds Expended
| 8a. Personnel |  |  |  | 240000 |  |  | 100000
| 8b. Fringe Benefits |  |  |  | 61542 |  |  | 32000
| 8c. Travel |  |  |  | 10250 |  |  | 3000
| 8d. Equipment |  |  |  | 1533000 |  |  | 358159
| 8e. Supplies |  |  |  | 45000 |  |  | 15000
| 8f. Contractual |  |  |  | 1345000 |  |  | 250000
| 8g. Construction |  |  |  | 0 |  |  | 0
| 8h. Other |  |  |  | 4200 |  |  | 0
| 8i. Total Direct Charges (sum of 8a thru 8h) |  |  |  | 3238992 |  |  | 758159
| 8j. Indirect Charges |  |  |  | 840290 |  |  | 325000
| 8k. Totals (sum of 8i+8j) |  |  |  | 4079282 |  |  | 1083159
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: |  |  |  |  | Telephone (area code, number, and extension): |  | 555-313-1212
Jim Shoe
| Signature of Certifying Official: |  |  |  |  | Email Address: |  | jim.shoe@motown.edu
[6 empty] | Date: |  | 2022-10-28