## Performance Report Form Cover
Connecting Minority Communities Pilot Program (CMC) Performance (Technical) Report Form Overview
This Connecting Minority Communities Pilot Program (CMC) report form will serve as a tool to capture indicators highlighting broadband infrastructure, and adoption and use activities from the award's inception to the award's closeout. The form contains the Performance (Technical) Report.
Performance (Technical) Report: The Performance (Technical) Report is submitted semi-annually for periods ending March 31 and September 30 and captures project performance and outcomes. You will use the Performance (Technical) Report to provide your actual completed goals and planned activities from award inception to the current reporting period. You will submit the semi-annual report twice a year until you expend all CMC grant funds, as well as upon closeout of the award. The Performance Report is due 30 calendar days after the closing period. The final closeout report is due 120 calendar days after the last Performance Technical Report.
PAPERWORK REDUCTION ACT (PRA) OF 1995 (Public Law 104-13) STATEMENT OF PUBLIC BURDEN: An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information subject to the requirements of the Paperwork Reduction Act unless that collection of information displays a currently valid OMB Control Number: 0660-0048. Public reporting burden for this report is estimated to average 2.5 hours per response. This burden includes time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate to Dominique Harrison, Director, Office of Minority Broadband Initiatives, National Telecommunications and Information Administration, U.S Department of Commerce, 1401 Constitution Avenue, Room 73023R, Washington, DC 20230 via telephone at (202) 734-2354 or by email at dharrison@ntia.gov.

## Performance (Technical) Report
OMB Control No. 0660-0048 Expiration Date: 06/30/2027
CONNECTING MINORITY COMMUNITIES PILOT PROGRAM PERFORMANCE (TECHNICAL) REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: | Recipient A | [5 empty] | Award Identification Number: |  |  |  |  | 05-03-C14005
| Recipient Street Address: | 123 Street Lane | [5 empty] | Report Submission Date (MM/DD/YYYY): |  |  |  |  | 2024-10-30
| City, State, Zip Code: | Washington, DC 20001 | [5 empty] | Final Report? |  |  |  | Yes | FALSE
| DUNS/UEI Number: | 7796WER57798 | [9 empty] | No | TRUE
| Period of Performance Start Date (MM/DD/YYYY): | 2022-08-01 | [5 empty] | Period of Performance End Date (MM/DD/YYYY): |  |  |  |  | 2025-07-31
| Report Period Start Date (MM/DD/YYYY): | 2024-04-01 | [5 empty] | Report Period End Date (MM/DD/YYYY): |  |  |  |  | 2024-09-30
GENERAL PROJECT INFORMATION
1a | To date, what key milestones have been achieved, cumulatively?
In the first 6 months of the grant, Recipient A has finalized contractual agreements and expenses: Training, Technology, Laptops, and Broadband. In 2023, we implemented new IT infrastructure, including hiring 2 new IT assistants, training all new and existing IT employees, and beginning steps to upgrade the campus WiFi network. In February 2024, we procured and distributed 100 laptops to students in need after completing a survey to identify the students most in need of broadband connectivity equipment. For the Fall 2024 semester, we launched 4 courses for the IT & Digital Skills Training Program.
1b | What barriers or challenges have you encountered in the course of achieving your project milestones? If you did encounter barriers or challenges, what approaches were taken in order to overcome these obstacles and achieve project milestones?
More than 20% of households in our county--almost 60,000 households -- have no internet access at all. About 9% (5,400) have only mobile internet or dial-up service. The Recipient A network infrastructure has not been updated significantly since 2013, resulting in most network devices being end-of-life or outdated. Currently, Recipient A is leveraging a 2G bandwidth from its internet service provider to support its IT infrastructure, Learning Management System, and business applications. Beginning other project activities, including launching the laptop and hotspot distribution program and launching new training courses before the campus WiFi network has been fully upgraded, has proven challenging. To help the hotspot distribution program and the new training course launch, we hired more IT staff.
1c | Please describe any issues anticipated during the next reporting period that may impact planned progress against the project milestones. In particular, please identify any areas or issues where technical assistance from NTIA may be useful.
We did not anticipate servicing the 60,000 households with the upgrading of internet access. Shortage of workers, supply chain delays, and weather disruptions will prevent us from providing this upgrade. We anticipate within the next six months to service an estimated 10,000-12,000 households. However, with fall and winter coming, there will be issues completing this milestone. In addition to providing loaner laptops to students, we have also purchased a cache of hotspots for students to "check out" from the library for mobile and home use. We have not determined a plan to manage these hotspots, address any problems that may occur, or identified an employee to manage the devices. We may require technical assistance from NTIA to do so.
1d | To date, what notable successes have been achieved in the project, cumulatively?
Students at Recipient A now have increased access to devices, remote access via Close2Home, and access to a 24/7 support facility. Additionally, students in the Cybersecurity program have access to laptops, and all students have the ability to access a cache of hot spots for home and mobile use. Students now can connect to on-campus and remote educational resources and services. Lastly, the IT Infrastructure network is currently being upgraded to 5G and we have purchased 300 laptops to assist students with remote learning.
1e | Please describe significant project milestones planned for completion during the next reporting period.
During the next reporting period, we will host an Artificial Intelligence Symposium for faculty, a Tech Apprenticeship Technical Assistance for campus students, and a Geek Squad Academy for Middle School and High School students.
1f | Is this project a consortium project? |  | No
ORGANIZATIONAL PARTNERS
2a | Please use the following table to list all of your organizational partners, the type of organization, the type of partner you are collaborating with, the partner's role in completion of project activities, and whether or not the partner has changed their involvement or role in the project within the past six months.
| PARTNER NAME |  | Organization Type |  |  |  |  | Partner Type |  |  | Partner Role |  |  |  |  | Change in Past Six Months?
| Digital Network Support Coalition |  | Not-for-Profit 501(c)3 |  |  |  |  | Subrecipient |  |  | Provides subscriptions to students and community members |  |  |  |  | No
| Supreme Consulting (MBE) |  | Private Entity |  |  |  |  | Contractor |  |  | Advise on new training curriculum and also evaluates success of training program |  |  |  |  | No
| City Public Library |  | Community Anchor Institution |  |  |  |  | Unfunded Collaborator |  |  | Hosts numerous training opportunities, rents laptops and other IT equipment, and offers online trainings for community members |  |  |  |  | No
2b | If you selected "Community Anchor Institution" or "Community-Based Organization" for any of the listed partner organizations, please specify.
The City Public Library will serve as a partner for Recipient A's project, Inclusive-Tech Innovation Plan, which will create a vibrant and connected community that leverages broadband to support economic growth and prosperity within anchor communities. The library will serve as an extension of Recipient A as it will host numerous training opportunities for the communityat their facility. The community will be able to take online classes and training linked to Recipient A and will have the opportunity to rent laptops and other IT equipment for training-related projects.
2c | What barriers or challenges have you encountered in the course of working with any of these project partners that may impact the goals or outcomes of the project? If barriers or challenges were encountered, what approaches were taken in order to overcome these obstacles?
Initially, the library did not have have enough computers or laptops to handle the volume of individuals that will be utilizing the training opportunities. In addition, some of the computers were older and couldn't handle the capacity of work that would need to be completed. The library needed an additional 15 computers to replace six older computers and nine brand new computers to support the training. There was a backorder for desktop PCs causing a six-week delay. We don't anticipate any further delays.
REMOTE LEARNING INFRASTRUCTURE
3a | To date, what types of technology (hardware, software, online platforms) have you deployed, cumulatively, to facilitate and improve remote learning infrastructure?
| TECHNOLOGY NAME |  | Technology Type |  |  |  |  | Technology Description | [5 empty] | Total Cost
| Desktop Computer |  | Hardware |  |  |  |  | 8 Dell Inspiron Desktop ($649 per desktop) | [5 empty] | 64900
| Operating Systems |  | Software |  |  |  |  | Microsoft Windows ($199) | [5 empty] | 199
| Server |  | Online Platform |  |  |  |  | Microsoft Azure ($65 per month) | [5 empty] | 1690
3b | What percentage of classes were offered remotely before the start of the grant project? |  | 43%
3c | What percentage of classes are currently offered using a hybrid model? |  | 57%
3d | What barriers or challenges have you encountered in the course of implementing project elements associated with the purchase and distribution of Technology Types?
There was a backorder for desktop PCs causing a six-week delay. We don't anticipate any further delays. In addition, we had to hire more IT staff, so there was a slight delay in procuring and implementing the new software due to the hiring and onboarding process taking longer than expected.
3e | To date, which types of professional development training have you implemented, cumulatively, to facilitate and improve remote learning infrastructure and IT management?
| Professional Development Training Type |  |  | Total Number of Participants | [5 empty] | Professional Development Training Description
| Data Analytics |  |  | 100 | [5 empty] | Participants will earn badges from IBM, Google, Amazon (AWS), SAP and Microsoft. Students will learn about digital literacy, web design, programming, and artificial intelligence.
| Cloud Computing Training |  |  | 250 | [5 empty] | Participants will understand the convergence of development, security, and operations to seamlessly integrate security within a continuous delivery pipeline.
| SAP Administration |  |  | 75 | [5 empty] | Participants will learn SAP Architecture, Managing SAP System Administration Daily Tasks, Configuration and Administration of SAP systems, and SAP Basic Administration.
ANCHOR COMMUNITY ADOPTION
4a | List the anchor community activities your project has completed cumulatively, and the results of those activities. More Information on census tracts can be found at: https://broadbandusa.maps.arcgis.com/apps/dashboards/1725df85c8b94d0ab91f5807bcc91c39
| Anchor Community Activity |  | Census Tract |  |  |  |  | Target Beneficiary |  |  |  | Target Output for Next Six Months |  |  | Total Number of Activity
| Digital Literacy and Software Applications Training |  | 6019000100, 6019005408 |  |  |  |  | Returning Citizen |  |  |  | 150 |  |  | 325
4b | Please use the following table to record the requested values for indicators of community broadband adoption to date/cumulatively. The field "Other outcome not listed here:" may be edited to record an indicator of community adoption you wish to provide to NTIA that may not have been specifically requested. Use the Baseline column to note the target number that was used in the grant recipient’s application materials, and use the Current column to note the values achieved cumulatively. For the purposes of this section, new position created refers to a position that was created or funded by your CMC grant, including any part-time or seasonal positions, to administer and oversee the CMC project. Once you hire for a new position and have somebody actively fulfilling the job, the role becomes a new position filled. Community-based program refers to any training event funded by the CMC grant with the purpose of providing existing and potential workers with the necessary skills to meet current/future business needs.
| Community Adoption Indicator |  | Baseline | [7 empty] | To Date/Cumulatively
| Number of participants enrolled in community-based programs |  | 125 | [7 empty] | 325
| Number of participants who have completed community-based programs |  | 0 | [7 empty] | 0
| If applicable, number of participants who have obtained jobs following completion of a community-based program |  | 0 | [7 empty] | 0
| Number of new positions created through CMC funds |  | 3 | [7 empty] | 5
| Number of new positions filled through CMC funds |  | 1 | [7 empty] | 5
| Number of anchor community members with a broadband subscription |  | 200 | [7 empty] | 680
Other outcome not listed here:
4c | Did the 15-mile radius present any barriers or challenges in the delivery of services, scope of the project, project outcomes, etc.?
No. The only challenge was a delay in the delivery of equipment for the training programs. The scope of the project and project outcome will not be affected.
4d | How were these barriers or challenges resolved to meet the project's expected goals?
Since the computer equipment has been delivered, we do not anticipate any additional back order of the necessary computer equipment. In the future, we will utilize multiple vendors where we can purchase additional equipment.
BROADBAND INTERNET AND DEVICES
5a | Describe the Internet Devices which have been acquired with CMC-provided funds cumulatively. More Information on census tracts can be found at: https://broadbandusa.maps.arcgis.com/apps/dashboards/1725df85c8b94d0ab91f5807bcc91c39
| Total Number of Devices Purchased | Loaned or Donated? | Device Type |  |  |  |  | Total Cost |  | Recipient |  |  | Company Name |  |  | Census Tract
| 100 | Loaned | WiFi Hotspot |  |  |  |  | 27000 |  | College Student |  |  | Company A |  |  | 6019000100, 6019005408
| 100 | Donated | Other (Please Explain) |  |  |  |  | 15500 |  | College/University Staff |  |  | Company B |  |  | 6019000100, 6019005408
5b | If you defined any Device Type as "Other," please explain.
Routers were purchased and placed in various offices across the campus.
5c | Describe the Broadband Subscriptions which have been acquired with CMC-provided funds cumulatively.
| Total Number of Subscriptions | Broadband Network Type | Average Cost to Recipient |  | Total Cost to Institution (If Applicable) |  |  | Recipient |  |  | Speed of Broadband Service |  | Provider Type |  | ISP Provider Name
| 100 | Hotspot | 40 |  | 18000 |  |  | College Student |  |  | 30 Mbps |  | Other |  | Digital Network Support Coalition
| 100 | Fiber | 50 |  | 22000 |  |  | College/University Staff |  |  | 25/3 Mbps |  | Municipal Providers |  | Fiber Company
| 3 | Satellite | 6000 |  | 18000 |  |  | Not-for-Profit 501(c)3 Employees |  |  | 100 Mbps |  | Cable Companies |  | Business C
| 100 | Cable | 150 |  | 100000 |  |  | College/University Staff |  |  | 500 Mbps |  | Cable Companies |  | Cable4You
If you defined any Partner Type as "Other," please explain.
A not-for-profit agency paid for the subscription service for the distributed hotspots.
5d | Describe the Broadband Deployments which have been undertaken with CMC-provided funds cumulatively. Examples of deployments include installation, upgrades, maintenance, etc. More Information on census tracts can be found at: https://broadbandusa.maps.arcgis.com/apps/dashboards/1725df85c8b94d0ab91f5807bcc91c39
| Name of Deployment Site | Location Type | Broadband Network Type |  |  | Deployment Cost |  |  | Ongoing Cost |  | Purpose of Deployment |  |  | Address of Deployment SIte |  | Census Tract
| Science and Tech Branch | On-Campus | Fixed Wireless |  |  | 11000 |  |  | 5000 |  | Upgrade from 3G to 5G |  |  | 123 A Street, Washington, DC 20001 |  | 6019000100, 6019005408
5e | What barriers or challenges have you encountered in the course of implementing project elements associated with the purchase and distribution of broadband subscriptions? If barriers or challenges were encountered, what approaches were taken in order to overcome these obstacles?
One challenge is having the community to register/sign up for a broadband subscription. Participation has been low due to lack of marketing. In addition, community members are uncomfortable sharing private information about themselves to sign up for subscriptions. Furthermore, the cost to maintain these services in dense populated areas is extremely high. To overcome the reticence of sharing private information, we improved our marketing of the program to make it clear we would not be using individual's private information.
5f | What barriers or challenges have you encountered in the course of implementing project elements associated with the purchase and deployment of broadband networks? If barriers or challenges were encountered, what approaches were taken in order to overcome these obstacles?
One of the communities was in a rural area. This area did not have the necessary infrastructure to support and provide internet connectivity. In order to upgrade the connectivity speed, this area will need to be developed to handle the broadband network. We did not encounter any challenges associated with the purchase and deployment of broadband networks. We are in the process of upgrading the campus WiFi network to 5G through our current campus service provider, and there have been no barriers thus far.
DIGITAL SKILLS AND WORKFORCE DEVELOPMENT
6a | Cumulatively, what types of digital skills or workforce development trainings have been offered?
| Type of Training | Total Number of Participants | Total Number of Participants Who Completed Training |  |  |  | Participant Type |  |  |  | Average Number of Hours per Participant |  |  | Training Objectives Met? |  | College Credit Awarded?
| Computer Fundamentals | 300 | 250 |  |  |  | At-Risk Youth |  |  |  | 15 |  |  | Yes |  | No
| Digital Marketing | 300 | 150 |  |  |  | College Student |  |  |  | 15 |  |  | Yes |  | Yes
| UX/UI | 300 | 225 |  |  |  | K-12 Student |  |  |  | 10 |  |  | Yes |  | Yes
6b | If participants are awarded a certification upon completion of training, describe the certification.
225 Students that completed the UX/UI Bootcamp received a Google UX Design Certificate.
6c | What barriers or challenges have you encountered in the course of implementing project elements associated with digital skills or workforce development training? If barriers or challenges were encountered, what approaches were taken in order to overcome these obstacles?
We were fortunate to not encounter any challenges or barriers as the demand was extremely high. We were pleased with the high interest of senior community memebers to participate in the computer fundamentals training. The students that took the UX/UI training were excited to learn that they would receive a Google UX Design Certificate.
MEASUREMENT AND EVALUATION
7a | Describe performance measurements used to evaluate the project’s effectiveness or the benefits delivered to project beneficiaries.
| Project Purpose |  | Benefit |  |  |  |  | Beneficiary | [5 empty] | How Was This Measured?
| Increase Digital and Technical Workforce |  | Prepare senior population to be able to effectively secure employment in the IT Field. |  |  |  |  | Senior | [5 empty] | Tracking the number of senior community members that completed the course and secured a job in IT within 6-8 months.
| Remote Learning |  | Students will be able to take classes virtually increasing enrollment (hybrid). |  |  |  |  | College Student | [5 empty] | Data showing how many students are hybrid and how many are FT remote students. Survey to assess student feedback.
7b | Describe performance measurements utilized to evaluate the project's impact on digital opportunities or broadband adoption and use.
| Project Purpose |  | Benefit |  |  |  |  | Beneficiary | [5 empty] | How Was This Measured?
| Internet-connected devices - laptops, tablets, computers |  | Providing equipment to underserved community |  |  |  |  | Anchor Community Resident | [5 empty] | Digital Landscape Metric - measures the presence of tech components that allow people within a community to fully participate digitally.
| High Speed Internet Access |  | Upgrade current internet access |  |  |  |  | Institution | [5 empty] | Survey of students, faculty, and staff utilization of faster internet access.
7c | How did these activities align with your CMC project narrative goals?
The primary goals for this project are to 1) Increase the Digital and Technical Workforce 2) Enhance Digital Inclusion and Awareness 3) Enhance Community Connectivity and Broadband Adoption 4) Enhance Remote Learning and Work by upgrading the university IT infrastructure 5) Enhance Employment Outcomes in the anchor community 6) Strengthen Minority Business Enterprises. We were able to align these activities to the project narrative goals.
7d | Are these activities on track to meet these goals within the timeline? If not, what is the plan to meet these activities' goals within the timeline?
Yes, we are on track to meet these goals within the timeline. We will be launching applications for digital skills training, small business training, as well as digital bootcamps and purchase laptops.
7e | If not, what steps will be implemented to meet those goals and outcomes over the next 6 months and/or by the end of the period of performance?
N/A
7f | Describe any best practices or lessons-learned obtained at this point in the period of performance of the project.
1. Establish Required Features and Resources-identify a well-defined process plan that identifies technology requirements. 2. Assess students, community, and faculty broadband needs-conducting surveys to determine how new deployment will serve the students, community, and faculty is essential. 3. Setting integration parameters-we fully recognized what level of integration was required during implementation by reviewing the current technology stack and identifying its associated benefits, challenges, and costs.
8 | Please provide details below on your total budget and total funding expended to date for each budget element, including detailed disbursements of federal funds obligated from project inception through end of this reporting period. Figures should be reported cumulatively from the award start date to the end of the applicable reporting period.
| Grant Program, Function, or Activity |  |  |  |  | Actual Budget | [6 empty] | Total Funds Expended
| 8a. Personnel |  |  |  |  | 240000 | [6 empty] | 100000
| 8b. Fringe Benefits |  |  |  |  | 61542 | [6 empty] | 32000
| 8c. Travel |  |  |  |  | 10250 | [6 empty] | 3000
| 8d. Equipment |  |  |  |  | 1533000 | [6 empty] | 358159
| 8e. Supplies |  |  |  |  | 45000 | [6 empty] | 15000
| 8f. Contractual |  |  |  |  | 1345000 | [6 empty] | 250000
8g. Construction
| 8h. Other |  |  |  |  | 4200
| 8i. Total Direct Charges (sum of 8a thru 8h) |  |  |  |  | 3238992 | [6 empty] | 758159
| 8j. Indirect Charges |  |  |  |  | 840290 | [6 empty] | 325000
| 8k. Totals (sum of 8i+8j) |  |  |  |  | 4079282 | [6 empty] | 1083159
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | [6 empty] | Telephone (area code, number, and extension): |  |  |  |  | 123-456-7890 ext. 1
Quincy Tippe, President
| Signature of Certifying Official: | [6 empty] | Email Address: |  |  |  |  | president@RA.edu
[8 empty] | Date: |  |  |  |  | 2024-10-29

## Version Control (hidden)
Document Review and Approval History
Version Control
Date | Version | Version Name | Description | Author(s)
2025-05-22 | 1 | V01 | Initial Draft | Deloitte Team
2025-06-13 | 1 | V01 | QA/ QC | Deloitte Team
2025-06-18 | 1.2 | V01.2 | Reformat to match NTIA guidelines | Deloitte Team
2025-07-01 | 1.2 | V01.2 | Revisions made by Deloitte | Dominique Harrison
Document Review/ Approval History
Date | Name | Organization/ Title | Comments