## Baseline Scenario
Sample Infrastructure Deployment Report Scenario
Sample Infrastructure Deployment Scenario – BASELINE REPORT
Recipient A received $15 million under the second TBCP Notice of Funding Opportunity (NOFO) to construct a hybrid fiber and wireless, middle- and last-mile broadband network over four years. The network will connect 150 tribal households, which is every tribal household within Recipient A's funded service area.
Recipient A's period of performance begins on January 1, 2025, so the first period of the Baseline Report will only encompass three months (1/1/25–3/31/25). Subsequent reporting periods will each cover six months and correspond to the federal fiscal year semi-annual periods of April 1–September 30 and October 1–March 31. The period of performance ends December 31, 2028, so the final reporting period ending will encompass the final 3 months of the project (10/01/28–12/31/28). Note that while this is a four year project, the Baseline Report extends into the Year 5 column due to the semi-annual reporting periods.
The fiber portion of the network consists of 40 miles of middle-mile (backbone) fiber and 60 miles of last-mile (fiber-to-the-home) fiber. The entire fiber network will be newly constructed (none of the fiber miles will be leased and no existing fiber will be upgraded) and all fiber will be buried below ground (no aerial or subsea fiber). The last-mile (fiber-to-the-home) portion of the network will connect 120 unserved tribal households, 8 unserved tribal businesses, and 2 unserved tribal community anchor institutions (CAIs) (a tribal government building and a health clinic) to broadband at speeds of 500 Mbps (500/500 Mbps) symmetrical or greater.
In addition to the fiber network, Recipient A will construct two monopole towers to connect tribal households in outlying, hard-to-reach areas. The two new towers will provide wireless service to 30 unserved tribal households at speeds of 50/5 Mbps, utilizing the 2.5 GHz spectrum band that the recipient acquired during the FCC’s 2.5 GHz tribal window.
The middle-mile network will connect from an upstream site to 1) a hub location on Recipient A's land, from which the fiber-to-the-home network will originate, and 2) to the two newly constructed towers. The recipient plans to sign a pre-negotiated five-year IRU with a middle-mile broadband provider, Speedy Service 4U, for backhaul service at speeds of at least 1000 Mbps symmetrical (1000/1000 Mbps) as soon as the network build is complete. End-use service will be provided to the tribal homes, businesses, and CAIs via a separate ISP, Friendly Neighborhood Broadband. The terms of this agreement will be negotiated as the network is constructed; Recipient A anticipates that they will sign an agreement with the last-mile provider in the final month of the project. The Recipient is not requesting funding to cover middle- and last-mile service costs.
To deploy the proposed network, Recipient A will need to obtain 3 right-of-way agreements and 1 construction permit. The tribe will also need to conduct site preparation work to clear the ground on which the two wireless towers will be constructed.
Recipient A’s Notice of Award (NoA) lists their period of performance as four years. In their application, the recipient anticipated that the Environmental Assessment process would take around one year and that the network build would take an additional three years. However, environmental clearances were not received until a year and half into the period of performance. Receipt of environmental clearances triggered the Baseline Report due date 30 calendar days later. The recipient received approval to begin procuring equipment while the Environmental Assessment was underway via an initial expenditure plan. Final network design will occur during the first year of the project. Network testing will occur once the network build is complete.
Recipient A will hire two contractors: EZ Build, which will be responsible for equipment procurement and network construction, and Internet Engineering, Inc., which will be in charge of the network architecture and design. Recipient A also planned to hire one administrative assistant to help with administering the grant. The administrative assistant will be onboarded as soon as the project begins.
Simplified Project Plan
| Year 1 - Report Period Ending |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
| 2025-03-31 | 2025-09-30 | 2026-03-31 | 2026-09-30 | 2027-03-31 | 2027-09-30 | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
Conduct Environmental Assessment | bar: 2025-03-31 to 2026-09-30
Network Design | bar: 2025-03-31 to 2026-03-31
Negotiate Right-of-Way Agreements | bar: 2026-03-31
Obtain Construction Permit | bar: 2025-09-30
Negotiate ISP Agreement | bar: 2026-09-30
Procure Equipment | bar: 2025-03-31 to 2027-03-31
Site Preparation Work | bar: 2026-09-30 to 2027-03-31
Construct Towers | bar: 2027-03-31 to 2027-09-30
Construct Middle-Mile Network | bar: 2027-03-31 to 2027-09-30
Construct Last-Mile Network | bar: 2027-03-31 to 2027-09-30
Install Customer Premise Equipment | bar: 2028-03-31 to 2028-09-30
Network Testing | bar: 2028-09-30 to 2029-03-31
Summary of Infrastructure Deployment Solution Deployments and Outcomes:
● 100 total new fiber miles (40 miles of middle-mile fiber and 60 miles of last-mile fiber)
● 2 new towers
● 2 wireless links
● 1 interconnection point
● 1 signed agreement (IRU with middle-mile provider)
● 1 potential service agreements (ISP agreement, under negotiation)
● 3 right-of-way (ROW) agreements
● 1 construction permit
● Site preparation work for the new towers
● 120 unserved tribal households, 8 unserved businesses, & 2 unserved CAIs served by fiber at speeds of 500/500 Mbps
● 30 unserved households served by wireless at speeds of 50/5 Mbps
● 1 position funded by TBCP funds

## Baseline Report
|  | Select Project Type Below | [10 empty] | End Period
|  | Infrastructure Deployment | [10 empty] | 2029-03-31
OMB Control No. 0690-0039 Expiration Date: 6/30/2028
TRIBAL BROADBAND CONNECTIVITY PROGRAM BASELINE REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: | Recipient A |  |  |  |  | Award Identification Number: |  |  |  | NT25TBC0000000
| Recipient Street Address: | 123 Street Lane |  |  |  |  | Report Submission Date (MM/DD/YYYY): |  |  |  | 2026-07-15
| City, State, Zip Code: | Washington, DC 20001
| UEI Number: | 123456789
| Period of Performance Start Date (MM/DD/YYYY): | 2025-01-01 |  |  |  |  | Period of Performance End Date (MM/DD/YYYY): |  |  |  | 2028-12-31
| Report Period Start Date (MM/DD/YYYY): | 2025-01-01 |  |  |  |  | Report Period End Date (MM/DD/YYYY): |  |  |  | 2028-12-31
BROADBAND USE & ADOPTION AND INFRASTRUCTURE MILESTONES/KEY INDICATORS
INFRASTRUCTURE DEPLOYMENT AND PLANNING PROJECT MILESTONE CATEGORIES
1 | Use the following table to indicate the anticipated percent completion for all Infrastructure Deployment and/or Planning activities. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. Report this information cumulatively for all applicable project periods. Each row should end with 100% completion. Once the 100% mark is reached, continue to enter 100% for each subsequent cell in the row until you reach the Year and Period in which your project’s period of performance ends. For additional explanation, see the Reporting Guidance and Instructions document. For the purposes of this section, equipment procurement refers to activities associated with identifying and procuring necessary equipment for your project. Equipment deployment refers to all activities associated with the installation of equipment purchased as part of your TBCP project. If you are using milestone 1k. Other (please specify), include a brief description of the milestone by typing over the portion that reads (please specify).
| MILESTONE CATEGORIES |  | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
|  |  | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
| 1a. Overall Project |  | 10% | 20% |  | 25% | 40% | 55% |  | 70% |  | 80% | 95% | 100%
| 1b. Environmental Assessment |  | 5% | 25% |  | 50% | 100% | 100% |  | 100% |  | 100% | 100% | 100%
| 1c. Network Design |  | 10% | 50% |  | 100% | 100% | 100% |  | 100% |  | 100% | 100% | 100%
| 1d. Rights Of Way |  | 10% | 10% |  | 50% | 100% | 100% |  | 100% |  | 100% | 100% | 100%
| 1e. Construction Permits And Other Approvals |  | 10% | 100% |  | 100% | 100% | 100% |  | 100% |  | 100% | 100% | 100%
| 1f. Site Preparation |  | 0% | 0% |  | 0% | 0% | 60% |  | 100% |  | 100% | 100% | 100%
| 1g. Equipment Procurement |  | 0% | 30% |  | 30% | 60% | 80% |  | 100% |  | 100% | 100% | 100%
| 1h. Network Build (all components - owned, leased, Indefeasible Rights of Use, etc.) |  | 0% | 0% |  | 0% | 0% | 40% |  | 80% |  | 90% | 100% | 100%
| 1i. Equipment Deployment |  | 0% | 0% |  | 0% | 0% | 30% |  | 70% |  | 90% | 100% | 100%
| 1j. Network Testing |  | 0% | 0% |  | 0% | 0% | 0% |  | 0% |  | 50% | 95% | 100%
| 1k. Other (please specify) |  | NA | NA |  | NA | NA | NA |  | NA |  | NA | NA | NA
INFRASTRUCTURE DEPLOYMENT NETWORK BUILD PROGRESS
2 | Use the following table to provide information about the progress of your Infrastructure Deployment and/or Planning project. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. Except for 2h, report information cumulatively for all applicable project periods. For additional explanation, see the Reporting Guidance and Instructions document. For the purposes of this section, new wireless links refers to the number of new wireless transmissions—comprised of a source node (transmitter) to a destination node (receiver)—that exist due to TBCP funding; wireless links may be middle or last mile. New towers refers to any towers that are constructed, leased, and/or upgraded or retrofitted with grant funds; this includes in-situ vertical structures that are outfitted with network equipment (water towers, rooftops, steeples, etc.). New interconnection points refers to any new physical connections where traffic is routed from one network to another created as a result of TBCP funds. If using the milestones 2j. Other (please specify), include a brief description of the milestone by typing over the portion that reads (please specify).
| NETWORK BUILD PROGRESS | MIDDLE OR LAST MILE | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
|  |  | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
| 2a. Number of new fiber miles (aerial or underground) constructed or upgraded with TBCP funds | Both | 0 | 0 |  | 0 | 0 | 20 |  | 60 |  | 60 | 100 | 100
| 2b. Number of fiber miles leased with TBCP funds | NA | NA | NA |  | NA | NA | NA |  | NA |  | NA | NA | NA
| 2c. Number of existing fiber miles upgraded with TBCP funds | NA | NA | NA |  | NA | NA | NA |  | NA |  | NA | NA | NA
| 2d. Number of new wireless links created through TBCP funds | Last-Mile | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 2 | 2
| 2e. Number of new towers constructed with TBCP funds | Both | 0 | 0 |  | 0 | 0 | 0 |  | 1 |  | 2 | 2 | 2
| 2f. Number of new interconnection points created through TBCP funds | Middle-Mile | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 1 | 1
| 2g. Number of signed agreements with broadband wholesalers or last mile providers from TBCP funds | Both | 1 | 1 |  | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1
| 2h. Number of potential agreements (i.e., agreements currently being negotiated) with broadband wholesalers or last mile providers from TBCP funds (This number should NOT be reported cumulatively) | Last-Mile | 1 | 1 |  | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1
| 2i. Obtained licenses: 2.5 (EBS), 3.5 (CBRS) from TBCP funds | NA | NA | NA |  | NA | NA | NA |  | NA |  | NA | NA | NA
| 2j. Other (please specify) | NA | NA | NA |  | NA | NA | NA |  | NA |  | NA | NA | NA
INFRASTRUCTURE DEPLOYMENT KEY INDICATORS
3 | Use the following table to provide the number of unserved tribal households, unserved tribal households at or below 150% of the poverty line, unserved tribal businesses, and unserved tribal community anchor institutions (CAIs) connected to broadband infrastructure through your Infrastructure Deployment project. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. Report information cumulatively for all applicable project periods. For additional explanation, see the Reporting Guidance and Instructions document. Provide the number of structures connected according to connectivity speed (100/20 and 25/3) and connectivity type (wireless, fiber).
| PROJECTED NUMBER OF SUBSCRIBERS AND SPEED |  | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
| SUBSCRIBER TYPE | SPEED TYPE | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
| 3a. Unserved Tribal Households | Number of Unserved Tribal Households connected to broadband infrastructure
|  | Number of previously Unserved Tribal Households with broadband availability at speeds of at least 100/20 Mbps through TBCP funds | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 120 | 120
|  | Number of previously Unserved Tribal Households with broadband availability at speeds of at least 25/3 Mbps through TBCP funds | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 150 | 150
Number of Unserved Tribal Households connected to broadband infrastructure by copper or DSL cable line
|  | Number of previously Unserved Tribal Households with broadband availability by wireless connection through TBCP funds | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 30 | 30
|  | Number of previously Unserved Tribal Households with broadband availability by fiber optic connection through TBCP funds | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 120 | 120
| 3b. Tribal Households | Number of Tribal Households connected to broadband infrastructure
Number of Tribal Households connected to broadband infrastructure at speeds of at least 100/20
Number of Tribal Households connected to broadband infrastructure at speeds of at least 25/3
Number of Tribal Households connected to broadband infrastructure by copper or DSL cable line
Number of Tribal Households connected to broadband infrastructure by wireless connection
Number of Tribal Households connected to broadband infrastructure by fiber optic connection
| 3c. Unserved Tribal Households At or Below 150% of the Poverty Line | Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure
|  | Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at speeds of at least 100/20 Mbps through TBCP funds | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 60 | 60
|  | Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at speeds of 25/3 Mbps through TBCP funds | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 60 | 60
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by copper or DSL cable line
|  | Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by wireless connection through TBCP funds | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 60 | 60
|  | Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by fiber optic connection through TBCP funds | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 60 | 60
| 3d. Unserved Tribal Businesses | Number of Unserved Tribal Businesses connected to broadband infrastructure
|  | Number of previously Unserved Tribal Businesses with broadband availability at speeds of at least 100/20 Mbps through TBCP funds | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 8 | 8
|  | Number of previously Unserved Tribal Businesses with broadband availability at speeds of at least 25/3 Mbps through TBCP funds | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 8 | 8
Number of Unserved Tribal Businesses connected to broadband infrastructure by copper or DSL cable line
|  | Number of Unserved Tribal Businesses connected to broadband infrastructure by wireless connection through TBCP funds | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
|  | Number of Unserved Tribal Businesses connected to broadband infrastructure by fiber optic connection through TBCP funds | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 8 | 8
| 3e. Unserved Tribal Community Anchor Institutions (CAIs) | Number of Unserved Tribal CAIs connected to broadband infrastructure
|  | Number of previously Unserved Tribal CAIs with broadband availability at speeds of at least 100/20 Mbps through TBCP funds | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 2 | 2
|  | Number of previously Unserved Tribal CAIs with broadband availability at speeds of at least 25/3 Mbps through TBCP funds | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 2 | 2
Number of Unserved Tribal CAIs connected to broadband infrastructure by copper or DSL cable line
|  | Number of Unserved Tribal CAIs connected to broadband infrastructure by wireless connection through TBCP funds | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0
|  | Number of Unserved Tribal CAIs connected to broadband infrastructure by fiber optic connection through TBCP funds | 0 | 0 |  | 0 | 0 | 0 |  | 0 |  | 0 | 2 | 2
BROADBAND USE & ADOPTION KEY INDICATORS
4 | Use the following table to provide the number of unserved tribal households, unserved tribal businesses, and unserved tribal community anchor institutions (CAIs) that receive new access to broadband through your Use and Adoption project. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. Report information cumulatively for all applicable project periods. For additional explanation, see the Reporting Guidance and Instructions document. For the purposes of this section, passed/serviceable refers to structures within the service area that have the physical infrastructure in place to connect to the internet. Structures that are "passed/serviceable" may be served (if they have an internet connection at speeds of 25/3 Mbps or greater) or unserved (if they do not have a broadband subscription or if they have an internet connection that is slower than 25/3 Mbps). New access refers to tribal households, businesses, and CAIs within your service area that received access to qualifying broadband service (25/3 Mbps or greater) for the first time (i.e., previously had no broadband connectivity or connectivity of less than 25/3 Mbps) as a result of TBCP funds.
| PROJECTED NUMBER OF SUBSCRIBERS AND SPEED |  | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
| BENEFICIARY TYPE | ACCESS TYPE | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
| 4a. Unserved Tribal Households | Number of Unserved Tribal Households passed/serviceable
Number of previously unserved Tribal Households with new access through TBCP-funded broadband subscriptions (i.e. prepayment)
| 4b. Tribal Households | Number of Tribal Households passed/serviceable
Number of Tribal Households with new access
| 4c. Unserved Tribal Households At or Below 150% of the Poverty Line | Number of Unserved Tribal Households At or Below 150% of the Poverty Line passed/serviceable
Number of previously unserved Tribal Households At or Below 150% of the Poverty Line with new access through TBCP funds
| 4d. Unserved Tribal Businesses | Number of Unserved Tribal Businesses passed/serviceable
Number of previously unserved Tribal Businesses with new access through TBCP funds
| 4e. Unserved Tribal Community Anchor Institutions | Number of Unserved Tribal Community Anchor Institutions passed/serviceable
Number of previously unserved Tribal Community Anchor Institutions with new access through TBCP funds
BROADBAND USE & ADOPTION DEMOGRAPHIC INDICATORS
5
| DEMOGRAPHIC INDICATORS |  | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
| SUBSCRIBER TYPE | ESTIMATED POPULATION IN SERVICE AREA | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
| 5a. Unserved Tribal Population | Number of Unserved Native American/Alaska Native/Native Hawaiian Households in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Tribal Businesses in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Community Anchor Institutions in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Households At or Below 150% of the Poverty Line in funded service area
| 5b. Tribal Population | Number of Tribal Households in funded service area
Number of Tribal Businesses in funded service area
Number of Tribal Community Anchor Institutions in funded service area
Number of Tribal Households At or Below 150% of the Poverty Line in funded service area
INFRASTRUCTURE DEPLOYMENT, PLANNING, AND BROADBAND USE & ADOPTION WORKFORCE INDICATORS
6 | Use the following table to provide workforce data for your Infrastructure Deployment, Planning, or Use and Adoption project. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. Report information cumulatively for all applicable project periods. For additional explanation, see the Reporting Guidance and Instructions document.
| WORKFORCE INDICATORS |  | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
| OUTCOMES | QUESTIONS | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
| 6a. Telework | Number of individuals with ability to telework prior to receiving TBCP grant funds
Number of individuals with ability to telework after receiving TBCP grant funds
| 6b. New Positions | Number of positions funded by TBCP funds | 1 | 1 |  | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1
|  | Number of new positions filled through TBCP funds | 1 | 1 |  | 1 | 1 | 1 |  | 1 |  | 1 | 1 | 1
| 6c. Participation in Workforce Development Trainings | Number of individuals who attended a TBCP-funded workforce development training event | NA | NA |  | NA | NA | NA |  | NA |  | NA | NA | NA
| 6d. Workforce Development Trainings | Number of workforce development training events held with TBCP funds | NA | NA |  | NA | NA | NA |  | NA |  | NA | NA | NA
BROADBAND USE & ADOPTION EDUCATIONAL SUCCESS INDICATORS
7 | Use the following table to provide educational data for your Use and Adoption project. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. Report information cumulatively for all applicable project periods. For additional explanation, see the Reporting Guidance and Instructions document.
| EDUCATIONAL SUCCESS INDICATORS |  | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
| OUTCOMES | QUESTIONS | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
| 7a. Access to Online Learning | Number of individuals with ability to participate in online learning prior to receiving TBCP grant funds
Number of individuals with ability to participate in online learning after receiving TBCP grant funds
| 7b. Participation in Online Learning | Number of individuals who attend online learning classes
Number of individuals who attend virtual/in-person school activities
| 7c. Parental Participation in School Activities | Number of parents/legal guardians who attend virtual/in-person school activities
| 7d. High School Enrollment and Completion | Number of individuals enrolled in high school
Number of individuals who successfully exited high school program with degree (diploma/GED)
| 7e. School Participation in Remote or Hybrid Learning | Number of schools in program
Number of schools engaged in remote or hybrid learning model through TBCP funds
| 7f. School Participation in In-Person Learning | Number of schools in program
Number of schools engaged in in-person learning model through TBCP funds
| 7g. School Participation in Hybrid Learning | Number of schools in program
Number of schools engaged in hybrid learning model through TBCP funds
BROADBAND USE & ADOPTION TELEHEALTH INDICATORS
8 | Use the following table to provide telehealth data for your Use and Adoption project. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. Report information cumulatively for all applicable project periods. For additional explanation, see the Reporting Guidance and Instructions document.
| TELEHEALTH INDICATORS |  | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
| OUTCOMES | QUESTIONS | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
| 8a. Access to Telehealth Services | Number of individuals with ability to participate in telehealth services prior to receiving TBCP grant funds
Number of individuals with ability to participate in telehealth service after receiving TBCP grant funds
| 8b. New Access to Telehealth Services | Number of individuals with new access to telehealth services
| 8c. Telehealth Appointments Scheduled | Estimated number of telehealth appointments scheduled
BROADBAND USE & ADOPTION DIGITAL INCLUSION INDICATORS
9 | Use the following table to provide digital inclusion data for your Use and Adoption project. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. Report information cumulatively for all applicable project periods. For additional explanation, see the Reporting Guidance and Instructions document.
| DIGITAL INDICATORS |  | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
| OUTCOMES | QUESTIONS | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
| 9a. Participation in Affordable Broadband Connectivity Program | Number of households in affordable broadband connectivity programs
| 9b. Digital Literacy Trainings | Number of digital literacy training events held with TBCP funds
| 9c. Tribal Programs Transitioned to Online Platform | Number of Tribal programs transitioned to online platform with TBCP funds
| 9d. Devices Distributed to Individuals | Number of individuals given device
| 9e. Devices Distributed to Households | Number of households given device
| 9f. Devices Distributed to Other Entities (i.e., community anchor institutions, schools, Tribal businesses) | Number of other entities given device
BROADBAND USE & ADOPTION TYPE OF INTERNET DEVICES
10 | Use the following table to record the internet connectivity devices that you plan to acquired for your Use and Adoption project. All devices that you plan to purchase and distribute throughout your award should appear in this table. For additional explanation, see the Reporting Guidance and Instructions document. For each row, select the appropriate device from the dropdown menu in the Device Type column, provide the number of units purchased with grant funds under the Number of Devices column, and provide the total cost under the Total Cost column. If you select the device type Other, provide a brief description of the device in the Total Cost column.
| Device Type |  | Number of Devices |  |  |  |  | Total Cost
INFRASTRUCTURE DEPLOYMENT, PLANNING, AND BROADBAND USE & ADOPTION TYPE OF COLLABORATORS
11 | Use the following table to provide information about the contractors, subrecipients, and unfunded collaborators involved in your TBCP project. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. All contractors, subrecipients, and collaborators that you plan to work with throughout your award should appear in this table. For additional explanation, see the Reporting Guidance and Instructions document. In the Collaborator Organization Type column, indicate whether the participating organization is a Contractor, Subrecipient, or Informal Unfunded Collaborator by selecting an option from the dropdown menu, then put the organization's name into the Collaborator Organization Name column. Enter the full name of the participating organization’s point of contact (POC) in the Collaborator POC Name, and the point of contact’s email address in the Collaborator POC Email column. Indicate whether the participant is Funded or Unfunded by selecting an option from the dropdown menu in the Funded or Unfunded Collaboration column.
COLLABORATORS
| Collaborator Organization Type | Collaborator Organization Name | Collaborator POC Name |  | Collaborator POC Email |  |  |  | Funded or Unfunded Collaboration
| Contractor | EZ Build | John Doe |  | John.Doe@EZBuild.com |  |  |  | Funded
| Contractor | Internet Engineering, Inc. | Jane Public |  | Jane.Public@IEI.com |  |  |  | Funded
| Non-funded Collaborator | Recipient A IT Department | Sam Jones |  | Sam.Jones@RAIT.com |  |  |  | Unfunded
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | [5 empty] | Telephone (area code, number and extension): |  |  |  | 123-456-7890 ext 1
John Smith
| Signature of Certifying Official: | [5 empty] | Email Address: |  |  |  | JohnSmith@RA.org
/s/ John Smith
[7 empty] | Date: |  |  |  | 2026-07-10
PAPERWORK REDUCTION ACT (PRA) OF 1995 (Public Law 104-13) STATEMENT OF PUBLIC BURDEN: An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information subject to the requirements of the Paperwork Reduction Act unless that collection of information displays a currently valid OMB Control Number 0690-0039. Public reporting burden for these reports is estimated to average 40 hours per response. This burden includes time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate to Margaret Gutierrez, Director, Tribal Broadband Connectivity Program, National Telecommunications and Information Administration, U.S Department of Commerce, 1401 Constitution Avenue, Room 4887, Washington, DC 20230 via telephone at 202-235-5467 or by email at mgutierrez@ntia.gov.
Formulas:
Year 2 - Report Period Ending = EOMONTH([NA],6)
Award Identification Number: = EOMONTH([Year 2 - Report Period Ending],6)
Year 3 - Report Period Ending = EOMONTH([Award Identification Number:],6)
Year 4 - Report Period Ending = EOMONTH([NA],6)
Year 5 - Report Period Ending = EOMONTH([NA],6)
NA = EOMONTH([Year 1 - Report Period Ending],6)

## Performance (Tech) Scenario
Sample Infrastructure Deployment Report Scenario
Sample Infrastructure Deployment Scenario – Performance (Technical) REPORT
Recipient A is now two years and three months into their four-year project. The Tribe is preparing to submit their Year 3, reporting period ending 3/31/2027 Performance (Technical) Report.
As planned and outlined in the Baseline Report, the Recipient's environmental assessment, network design, rights-of-way, and construction permits were all completed in Year 2, reporting period ending 3/31/2026. The Tribe planned to be 60% complete with site preparation for the new towers by the end of Year 3, reporting period ending 3/31/2027 but, due to unseasonably rainy weather, was only able to complete 40% of the site prep work.
The Tribe had also planned to procure 80% of the equipment needed to complete the network build by the end of Year 3, reporting period ending 3/31/2027. However, because of logistical delays, equipment procurement is only 60% complete. Unfortunately, the delayed equipment had the knock-on effect of holding up the initial stages of the network build and equipment deployment. At the conclusion of Year 3, reporting period ending 3/31/2027, network build and equipment deployment stood at 20% and 25% completion, respectively. The planned completion percentages for these indicators were 40% and 30%.
In the Baseline Report, Recipient A anticipated deploying 20 miles of fiber, signing one agreement with a middle-mile provider, and being in negotiation with one last-mile provider by the end of Year 3, reporting period ending 3/31/2027. Because of rainy weather and delays in procuring a piece of vital construction equipment, the Tribe was only able to build out 16 miles of fiber. As planned, the Tribe has signed the middle-mile agreement and is in negotiation for the last-mile agreement.
Recipient A funded one new position with TBCP funds for an administrative assistant during the very first semi-annual reporting period of the project, but since the Performance (Technical) Report is cumulative, is still reported in the Year 3, reporting period ending 3/31/2027 report.
As stated in the Baseline Report, Recipient A does not anticipate any Tribal households, businesses, or community anchor institutions will be connected until the final year of the project.
Because Recipient A received a TBCP NOFO 2 award, they completed the BABA Addendum attached to the Performance (Technical) Report. If they had received funds under the first TBCP NOFO, they would have left the BABA Addendum blank.

## Performance (Technical) Rep
Select Project Type Below
Infrastructure Deployment
OMB Control No. 0690-0039 Expiration Date: 6/30/2028
TRIBAL BROADBAND CONNECTIVITY PROGRAM PERFORMANCE (TECHNICAL) REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: | Recipient A |  |  |  | Award Identification Number: |  |  |  | NT25TBC0000000
| Recipient Street Address: | 123 Street Lane |  |  |  | Report Submission Date (MM/DD/YYYY): |  |  |  | 2027-04-14
| City, State, Zip Code: | Washington, DC 20001 |  |  |  | Final Report:
| UEI Number: | 123456789 | [7 empty] | No
| Period of Performance Start Date (MM/DD/YYYY): | 2025-01-01 |  |  |  | Period of Performance End Date (MM/DD/YYYY): |  |  |  | 2028-12-31
| Report Period Start Date (MM/DD/YYYY): | 2026-10-01 |  |  |  | Report Period End Date (MM/DD/YYYY): |  |  |  | 2027-03-31
BROADBAND USE & ADOPTION AND INFRASTRUCTURE MILESTONES/KEY INDICATORS
INFRASTRUCTURE DEPLOYMENT AND PLANNING PROJECT MILESTONE CATEGORIES
1 | Use the following table to indicate the percent completion for all Infrastructure Deployment and/or Planning activities. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Percent Complete column, provide the percent of completion for all infrastructure activities conducted with TBCP funds. Determine the percent completion based on the actual completion of activities (not by expenditure of budget). If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular milestone, enter “NA" in both the Percent Complete and Narrative columns. For the purposes of this section, equipment procurement refers to activities associated with identifying and procuring necessary equipment for your project. Equipment deployment refers to all activities associated with the installation of equipment purchased as part of your TBCP project. If you are using milestone 1k Other (please specify), include a brief description of the milestone by typing over the portion that reads (please specify). For milestones 1l and 1m, describe accomplishments and challenges faced during the last semi-annual (6 month) period.
MILESTONE CATEGORIES
|  |  | Percent Complete |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 1a. Overall Project |  | 25% |  |  |  | Delays due to weather conditions and supply chain disruptions.
| 1b. Environmental Assessment |  | 100% |  |  |  | NA
| 1c. Network Design |  | 100% |  |  |  | NA
| 1d. Rights Of Way |  | 100% |  |  |  | NA
| 1e. Construction Permits And Other Approvals |  | 100% |  |  |  | NA
| 1f. Site Preparation |  | 40% |  |  |  | Site preparation delayed due to unseasonably rainy weather. We estimate that site prep work for the two new monopole towers is ~40% complete and that the remaining 60% of work will be finalized in the first few weeks of Year 3, Period 2.
| 1g. Equipment Procurement |  | 60% |  |  |  | Delays in equipment procurement were due to supply chain disruptions. Specifically, network equipment has taken longer to procure and ship than anticipated.
| 1h. Network Build (all components - owned, leased, Indefeasible Rights of Use, etc.) |  | 20% |  |  |  | Network build is slightly behind schedule due to weather conditions and delays in procuring a rock borer.
| 1i. Equipment Deployment |  | 25% |  |  |  | Equipment deployment is behind schedule as a result of delays in equipment procurement.
| 1j. Network Testing |  | 0% |  |  |  | NA
| 1k. Other (please specify) |  | NA |  |  |  | NA
1l. Please describe significant project accomplishments during this reporting period funded through TBCP grant. (600 words or less)
Recipient A began Site Preparation work for the 2 new monopole towers that will be constructed as part of the network build, procured equipment, and began constructing the middle-mile fiber network. Site preparation work included clearing land of debris, uprooting trees, and creating an access road. Equipment procured during the past reporting period includes Customer Premise Equipment, network build equipment (including GPON switches), and equipment needed to deploy fiber optic cable (trenching equipment, rock borer, etc.). Sixteen miles of middle-mile fiber were also laid.
1m. Please describe any challenges to achieving project accomplishments during this reporting period funded through TBCP grant. (600 words or less)
During the reporting period, Recipient A was unable to reach the projected completion percentages for Site Preparation, Equipment Procurement, Equipment Deployment, and Network Build. This was the result of weather- and supply chain-related challenges. Unseasonably rainy weather flooded the new tower sites, which prevented the Tribe from completing site clearing activities. Supply chain disruptions caused delays in equipment procurement, which had a knock-on effect on equipment deployment. Network build was delayed as a result of weather and supply chain congestion.
INFRASTRUCTURE DEPLOYMENT NETWORK BUILD PROGRESS
2 | Use the following table to provide information about the progress of your Infrastructure Deployment and/or Planning project. Except for 2h, report information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the completion figure for all infrastructure deployment activities conducted with TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular milestone, enter “NA" in the Total and Narrative columns. For the purposes of this section new wireless links refers to the number of new wireless transmissions–comprised of a source node (transmitter) to a destination node (receiver)--that exist due to TBCP funding; wireless links may be middle or last mile. New towers refers to any towers that are constructed, leased, and/or upgraded or retrofitted with grant funds; this includes in-situ vertical structures that are outfitted with network equipment (water towers, rooftops, steeples, etc.). New interconnection points refers to any new physical connections where traffic is routed from one network to another created as a result of TBCP funds. If using the milestones 2j Other (please specify), include a brief description of the milestone by typing over the portion that reads (please specify).
NETWORK BUILD PROGRESS
|  |  | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 2a. Number of new fiber miles (aerial or underground) constructed or upgraded with TBCP funds |  | 16 |  |  |  | Recipient A anticipated deploying 20 fiber miles but was only able to complete 16. This variance was due to a combination of rainy weather, which limited the amount of time that the Tribe's construction contractor was able to dig fiber trenches, and delays in procuring a rock borer, which was required to lay cable in rough terrain.
| 2b. Number of fiber miles leased with TBCP funds |  | NA |  |  |  | NA
| 2c. Number of existing fiber miles upgraded with TBCP funds |  | NA
| 2d. Number of new wireless links created through TBCP funds |  | 0 |  |  |  | NA
| 2e. Number of new towers constructed with TBCP funds |  | 0 |  |  |  | NA
| 2f. Number of new interconnection points created through TBCP funds |  | 0 |  |  |  | NA
| 2g. Number of signed agreements with broadband wholesalers or last mile provider from TBCP funds |  | 1 |  |  |  | NA
| 2h. Number of potential agreements (i.e., agreements currently being negotiated) with broadband wholesalers or last mile providers from TBCP funds (This number should NOT be reported cumulatively) |  | 1 |  |  |  | NA
| 2i. Obtained licenses: 2.5 (EBS), 3.5 (CBRS) from TBCP funds |  | NA |  |  |  | NA
| 2j. Other (please specify) |  | NA |  |  |  | NA
INFRASTRUCTURE DEPLOYMENT KEY INDICATORS
3 | Use the following table to provide the number of unserved tribal households, unserved tribal households at or below 150% of the poverty line, unserved tribal businesses, and unserved tribal community anchor institutions (CAIs) connected to broadband infrastructure through your Infrastructure Deployment project. Report all information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the completion figure for all connections made as a result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns. In each section, provide the number of structures connected according to connectivity speed (100/20 and 25/3) and connectivity type (wireless, fiber).
PROJECTED NUMBER OF SUBSCRIBERS AND SPEED
| SUBSCRIBER TYPE | SPEED TYPE | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 3a. Unserved Tribal Households | Number of Unserved Tribal Households connected to broadband infrastructure
|  | Number of previously Unserved Tribal Households with broadband availability at speeds of at least 100/20 Mbps through TBCP funds | 0 |  |  |  | NA
|  | Number of previously Unserved Tribal Households with broadband availability at speeds of at least 25/3 Mbps through TBCP funds | 0 |  |  |  | NA
Number of Unserved Tribal Households connected to broadband infrastructure by copper or DSL cable line
|  | Number of previously Unserved Tribal Households with broadband availability by wireless connection through TBCP funds | 0 |  |  |  | NA
|  | Number of previously Unserved Tribal Households with broadband availability by fiber optic connection through TBCP funds | 0 |  |  |  | NA
| 3b. Tribal Households | Number of Tribal Households connected to broadband infrastructure
Number of Tribal Households connected to broadband infrastructure at speeds of at least 100/20
Number of Tribal Households connected to broadband infrastructure at speeds of at least 25/3
Number of Tribal Households connected to broadband infrastructure by copper or DSL cable line
Number of Tribal Households connected to broadband infrastructure by wireless connection
Number of Tribal Households connected to broadband infrastructure by fiber optic connection
| 3c. Unserved Tribal Households At or Below 150% of the Poverty Line | Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure
|  | Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at speeds of at least 100/20 Mbps through TBCP funds | 0 |  |  |  | NA
|  | Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at speeds of 25/3 Mbps through TBCP funds | 0 |  |  |  | NA
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by copper or DSL cable line
|  | Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by wireless connection through TBCP funds | 0 |  |  |  | NA
|  | Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by fiber optic connection through TBCP funds | 0 |  |  |  | NA
| 3d. Unserved Tribal Businesses | Number of Unserved Tribal Businesses connected to broadband infrastructure
|  | Number of previously Unserved Tribal Businesses with broadband availability at speeds of at least 100/20 Mbps through TBCP funds | 0 |  |  |  | NA
|  | Number of previously Unserved Tribal Businesses with broadband availability at speeds of at least 25/3 Mbps through TBCP funds | 0 |  |  |  | NA
Number of Unserved Tribal Businesses connected to broadband infrastructure by copper or DSL cable line
|  | Number of Unserved Tribal Businesses connected to broadband infrastructure by wireless connection through TBCP funds | 0 |  |  |  | NA
|  | Number of Unserved Tribal Businesses connected to broadband infrastructure by fiber optic connection through TBCP funds | 0 |  |  |  | NA
| 3e. Unserved Tribal Community Anchor Institutions | Number of Unserved Tribal Community Anchor Institutions connected to broadband infrastructure
|  | Number of previously Unserved Tribal CAIs with broadband availability at speeds of at least 100/20 Mbps through TBCP funds | 0 |  |  |  | NA
|  | Number of previously Unserved Tribal CAIs with broadband availability at speeds of at least 25/3 Mbps through TBCP funds | 0 |  |  |  | NA
Number of Unserved Tribal Community Anchor Institutions connected to broadband infrastructure by copper or DSL cable line
|  | Number of Unserved Tribal CAIs connected to broadband infrastructure by wireless connection through TBCP funds | 0 |  |  |  | NA
|  | Number of Unserved Tribal CAIs connected to broadband infrastructure by fiber optic connection through TBCP funds | 0 |  |  |  | NA
BROADBAND USE & ADOPTION KEY INDICATORS
4 | Use the following table to provide the number of unserved tribal households, unserved tribal businesses, and unserved tribal community anchor institutions (CAIs) that receive new access to broadband through your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the completion figure for the number of structures passed/serviceable and the number of structures with new access to broadband as a result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns. For the purposes of this section, new access refers to tribal households, businesses, and CAIs within your service area that received access to qualifying broadband services (25/3 Mbps or greater) for the first time (i.e., previously had no broadband connectivity or connectivity of less than 25/3 Mbps) as a result of TBCP funds.
PROJECTED NUMBER OF SUBSCRIBERS AND SPEED
| BENEFICIARY TYPE | ACCESS TYPE | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 4a. Unserved Tribal Households | Number of Unserved Tribal Households passed/serviceable
Number of previously unserved Tribal Households with new access through TBCP-funded broadband subscriptions (i.e. prepayment)
| 4b. Tribal Households | Number of Tribal Households passed/serviceable
Number of Tribal Households with new access
| 4c. Unserved Tribal Households At or Below 150% of the Poverty Line | Number of Unserved Tribal Households At or Below 150% of the Poverty Line passed/serviceable
Number of previously unserved Tribal Households At or Below 150% of the Poverty Line with new access through TBCP funds
| 4d. Unserved Tribal Businesses | Number of Unserved Tribal Businesses passed/serviceable
Number of previously unserved Tribal Businesses with new access through TBCP funds
| 4e. Unserved Tribal Community Anchor Institutions | Number of Unserved Tribal Community Anchor Institutions passed/serviceable
Number of previously unserved Tribal Community Anchor Institutions with new access through TBCP funds
BROADBAND USE & ADOPTION DEMOGRAPHIC INDICATORS
5 | Use the following table to provide demographic data for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the Tribal demographic data for your service area. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns. In most instances, demographic indicators will not change throughout the lifetime of your project.
DEMOGRAPHIC INDICATORS
| SUBSCRIBER TYPE | ESTIMATED POPULATION IN SERVICE AREA | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 5a. Unserved Tribal Population | Number of Unserved Native American/Alaska Native/Native Hawaiian Households in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Tribal Businesses in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Community Anchor Institutions in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Households At or Below 150% of the Poverty Line in funded service area
| 5b. Tribal Population | Number of Tribal Households in funded service area
Number of Tribal Businesses in funded service area
Number Tribal Community Anchor Institutions in funded service area
Number of Tribal Households At or Below 150% of the Poverty Line in funded service area
INFRASTRUCTURE DEPLOYMENT, PLANNING, AND BROADBAND USE & ADOPTION WORKFORCE INDICATORS
6 | Use the following table to provide workforce data for your Infrastructure Deployment, Planning, or Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the figures for telework access, positions created and filled, and workforce development trainings held as a result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns. For the purposes of this section, new position created refers to a workforce position that was created or funded by your TBCP grant, including any part-time or seasonal positions. Once you hire for a new position and have somebody actively fulfilling the job, the role becomes a new position filled. Workforce development trainings refers to any training event funded by the TBCP grant with the purpose of providing existing and potential workers with the necessary skills to meet current/future business needs. Note: only Use and Adoption projects need to fill out the Telework indicator (6a). All project types must fill out the indicators New Positions (6b), Participation in Workforce Development Trainings (6c), and Workforce Development Trainings (6d).
WORKFORCE INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 6a. Telework | Number of individuals with ability to telework prior to receiving TBCP grant funds
Number of individuals with ability to telework after receiving TBCP grant funds
| 6b. New Positions | Number of positions funded by TBCP funds | 1 |  |  |  | NA
|  | Number of new positions filled through TBCP funds | 1 |  |  |  | NA
| 6c. Participation in Workforce Development Trainings | Number of individuals who attended a TBCP-funded workforce development training event | NA
| 6d. Workforce Development Trainings | Number of workforce development training events held with TBCP funds | NA
BROADBAND USE & ADOPTION EDUCATIONAL SUCCESS INDICATORS
7 | Use the following table to provide digital inclusion data for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the figures for any digital inclusion indicators achieved as result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns.
EDUCATIONAL SUCCESS INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 7a. Access to Online Learning | Number of individuals with ability to participate in online learning prior to receiving TBCP grant funds
Number of individuals with ability to participate in online learning after receiving TBCP grant funds
| 7b. Participation in Online Learning | Number of individuals who attended online learning classes
Number of individuals who attended virtual/in-person school activities
| 7c. Parental Participation in School Activities | Number of parents/legal-guardians who attended virtual/in-person school activities
| 7d. High School Enrollment and Completion | Number of individuals enrolled in high school
Number of individuals who successfully exited high school program with degree (diploma/GED)
| 7e. School Participation in Remote or Hybrid Learning | Number of schools in program
Number of schools engaged in remote or hybrid learning model through TBCP funds
| 7f. School Participation in In-Person Learning | Number of schools in program
Number of schools engaged in in-person learning model through TBCP funds
| 7g. School Participation in Hybrid Learning | Number of schools in program
Number of schools engaged in hybrid learning model through TBCP funds
BROADBAND USE & ADOPTION TELEHEALTH INDICATORS
8 | Use the following table to provide telehealth data for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the figures for any telehealth indicators achieved as result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns.
TELEHEALTH INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 8a. Access to Telehealth Services | Number of individuals with ability to participate in telehealth services prior to receiving TBCP grant funds
Number of individuals with ability to participate in telehealth service after receiving TBCP grant funds
| 8b. New Access to Telehealth Services | Number of individuals with new access to telehealth services
| 8c. Telehealth Appointments Scheduled | Estimated number of telehealth appointments scheduled
BROADBAND USE & ADOPTION DIGITAL INCLUSION INDICATORS
9 | Use the following table to provide digital inclusion data for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the figures for any digital inclusion indicators achieved as result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns.
DIGITAL INCLUSION INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 9a. Participation in Affordable Broadband Connectivity Program | Number of households in affordable broadband connectivity program
| 9b. Digital Literacy Trainings | Number of digital literacy training events held with TBCP funds
| 9c. Tribal Programs Transitioned to Online Platform | Number of Tribal programs transitioned to online platform previously (before receiving TBCP grant funds)
Number of Tribal programs transitioned to online platform with TBCP funds
| 9d. Devices Distributed to Individuals | Number of individuals given device
| 9e. Devices Distributed to Households | Number of households given device
| 9f. Devices Distributed to Other Entities (i.e., community anchor institutions, schools, Tribal businesses) | Number of other entities given device
BROADBAND USE & ADOPTION TYPE OF INTERNET DEVICES
10 | Use the following table to provide the internet connectivity devices that you have acquired for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. For each row, select the appropriate device from the dropdown menu in the Device Type column, provide the number of units purchased with grant funds under the Number of Devices column, and provide the total cost under the Total Cost column. If you select the device type Other, provide a brief description of the device in the Total Cost column.
| Device Type |  | Number of Devices |  |  |  | Total Cost
INFRASTRUCTURE DEPLOYMENT, PLANNING, AND BROADBAND USE & ADOPTION TYPE OF COLLABORATORS
11 | Use the following table to provide information about the contractors, subrecipients, and unfunded collaborators involved in your TBCP project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Collaborator Organization Type column, indicate whether the participating organization is a Contractor, Subrecipient, or Informal Unfunded Collaborator by selecting an option from the dropdown menu. Enter the full name of the participating organization’s point of contact (POC) in the Collaborator POC Name, and the point of contact’s email address in the Collaborator POC Email column. Indicate whether the participant is Funded or Unfunded by selecting an option from the dropdown menu in the Funded or Unfunded Collaboration column.
COLLABORATORS
| Collaborator Organization Type | Collaborator Organization Name | Collaborator POC Name | Collaborator POC Email |  |  |  | Funded or Unfunded Collaboration
| Contractor | EZ Build | John Doe | John.Doe@EZBuild.com |  |  |  | Funded
| Contractor | Internet Engineering, Inc. | Jane Public | Jane.Public@IEI.com |  |  |  | Funded
| Non-funded Collaborator | Recipient A IT Dept. | Sam Jones | Sam.Jones@RAIT.com |  |  |  | Unfunded
INFRASTRUCTURE DEPLOYMENT BUDGET EXECUTION DETAILS
12 | Use the following table to provide budget execution details for your Infrastructure Deployment and/or Planning project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Actual Budget column, record the budgeted totals from your most recently approved SF-424C. In the Total Funds Expended column, list the amount of grant funds expended to date per each cost category. The total listed at the bottom of the Total Funds Expended column should match the Federal expenditures reported in your SF-425.
| COST CLASSIFICATION |  |  |  | Actual Budget |  |  |  |  | Total Funds Expended
| 12a. Administrative and legal expenses |  |  |  | 200000 |  |  |  |  | 150000
| 12b. Land, structures, rights-of way, appraisals, etc. |  |  |  | 500000 |  |  |  |  | 500000
| 12c. Relocation expenses and payments |  |  |  | 0 |  |  |  |  | 0
| 12d. Architectural and engineering fees |  |  |  | 700000 |  |  |  |  | 700000
| 12e. Other architectural and engineering fees |  |  |  | 0 |  |  |  |  | 0
| 12f. Project inspection fees |  |  |  | 0 |  |  |  |  | 0
| 12g. Site work |  |  |  | 700000 |  |  |  |  | 600000
| 12h. Demolition and removal |  |  |  | 0 |  |  |  |  | 0
| 12i. Construction |  |  |  | 11000000 |  |  |  |  | 3400000
| 12j. Equipment |  |  |  | 1200000 |  |  |  |  | 500000
| 12k. Miscellaneous |  |  |  | 200000 |  |  |  |  | 0
| Subtotal |  |  |  | 14500000 |  |  |  |  | 3650000
| 12l. Contingencies |  |  |  | 500000 |  |  |  |  | 50000
| Totals |  |  |  | 15000000 |  |  |  |  | 3700000
BROADBAND USE & ADOPTION BUDGET EXECUTION DETAILS
13 | Use the following table to provide budget execution details for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Actual Budget column, record the budgeted totals from your most recently approved SF-424A. In the Total Funds Expended column, list the amount of grant funds expended to date per each cost category. The total listed at the bottom of the Total Funds Expended column should match the Federal expenditures reported in your SF-425.
| GRANT PROGRAM, FUNCTION, OR ACTIVITY |  |  |  | Actual Budget |  |  |  |  | Total Funds Expended
13a. Personnel
13b. Fringe Benefits
13c. Travel
13d. Equipment
13e. Supplies
13f. Contractual
13g. Construction
13h. Other
| 13i. Total Direct Charges (sum of 13a thru 13h) |  |  |  | 0 |  |  |  |  | 0
13j. Indirect Charges
| 13k. Totals (sum of 13i+13j) |  |  |  | 0 |  |  |  |  | 0
INFRASTRUCTURE DEPLOYMENT OTHER INDICATORS
14 | Use the following table to provide the maximum download and upload speeds in Megabits per second (Mbps) available as a result of TBCP funds. This information should not be reported cumulatively. Report the highest speeds available as of the end of the semi-annual reporting period captured in this report. For the purposes of this section, eligible area refers to your proposed service area.
| Project Speed | [7 empty] | Download |  | Upload
| Outcome |  | Questions
| 14a. Maximum available speed upon project completion |  | What is the maximum available speeds for Tribal Households in your eligible area?
What is the maximum available speeds for Tribal Businesses in your eligible area?
What is the maximum available speeds for Tribal CAIs in your eligible area?
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: |  |  |  |  | Telephone (area code, number and extension): |  |  |  | 123-456-7890 ext 1
John Smith
| Signature of Certifying Official: |  |  |  |  | Email Address: |  |  |  | JohnSmith@RA.org
/s/ John Smith
[6 empty] | Date: |  |  |  | 2027-04-14
PAPERWORK REDUCTION ACT (PRA) OF 1995 (Public Law 104-13) STATEMENT OF PUBLIC BURDEN: An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information subject to the requirements of the Paperwork Reduction Act unless that collection of information displays a currently valid OMB Control Number 0690-0039. Public reporting burden for these reports is estimated to average 40 hours per response. This burden includes time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate to Margaret Gutierrez, Director, Tribal Broadband Connectivity Program, National Telecommunications and Information Administration, U.S Department of Commerce, 1401 Constitution Avenue, Room 4887, Washington, DC 20230 via telephone at 202-235-5467 or by email at mgutierrez@ntia.gov.

## Performance BABA Addendum
OMB Control No. 0660-0047 Expiration Date: 7/31/2028
TBCP II BABA Compliance: Recipient Reporting Tracker for Finished Waived Electronics
Recipient Organization: |  | Recipient A |  | Award Identification Number: | NT25TBC0000000
Recipient Street Address: |  | 123 Street Lane |  | Report Submission Date (MM/DD/YYYY): | 2027-04-14
City, State, Zip Code: |  | Washington, DC 20001 |  | UEI Number: | 123456789
Reporting Period Start Date (MM/DD/YYYY): |  | 2026-10-01 |  | Report Type: | Performance (Technical) Report BABA Addendum
Reporting Period End Date (MM/DD/YYYY): |  | 2027-03-31
Finished Waived Electronics
Manufacturer | Electronic Category | HS Code (10 digit) | Product Identifier (e.g., SKU, Product ID, etc.) | Common language description of product function | Country of Origin | Quantity
USA Router Company | Router | 1234567899 | 123456 | A networking device that directs network traffic and connects your local network to the internet. | USA | 10
ACME Radio Co. | Radio | 7485693240 | 486421 | A device used to communicate or send a message. | USA | 25
CERTIFICATION | I hereby certify that to the best of my knowledge and belief all Iron, Steel, Manufactured Products, and Construction Materials installed on this project by my company and by any and all subcontractors and suppliers for this project comply with the Build America, Buy America Act (BABA) requirements of the Infrastructure Investment and Jobs Act of 2021 (Pub. L. 117- 58, §§ 70901-70952), or are the subject of a waiver approved by the U.S. Department of Commerce.
| Typed or Printed Name and Title of Authorized Certifying Official | John Smith |  | Telephone (Area code, number, and extension): | 123-456-7890 ext 1
| Signature of Certifying Official | /s/ John Smith |  | Email address: | JohnSmith@RA.org
|  |  |  | Date: | 2027-04-15
Paperwork Reduction Act Statement
PAPERWORK REDUCTION ACT (PRA) OF 1995 (Public Law 104-13) STATEMENT OF PUBLIC BURDEN: An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information subject to the requirements of the Paperwork Reduction Act unless that collection of information displays a currently valid OMB Control Number 0690-0039. Public reporting burden for this report is estimated to average 5 hours per response. This burden includes time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate to Jennifer Duane, Director, Grants Management, Administration, and Compliance, Office of Internet Connectivity and Growth, National Telecommunications and Information Administration, U.S Department of Commerce, 1401 Constitution Avenue, Room 4887, Washington, DC 20230 via telephone at (202) 482-2048 or by email at jduane@ntia.gov.

## Annual Scenario
Sample Infrastructure Deployment Report Scenario
Sample Infrastructure Deployment Scenario – Annual REPORT
Recipient A has now entered the final year of their project and is preparing to submit their fourth Annual Report.
In the past year, Recipient A completed site preparation work, procured network equipment, deployed 55 miles of middle- and last-mile fiber, continued construction on two wireless towers, and signed an IRU agreement with a middle-mile provider.
One contractor (EZ Build) was involved in project activities during Year 3. EZ Build, a construction contractor, procured construction and network equipment, deployed 55 miles of fiber (40 miles of middle-mile fiber and 15 miles of last-mile fiber), and began erecting the wireless towers.
The deployment of last-mile fiber has resulted in the connection of 4 households, 8 businesses, and 2 CAIs (a tribal government building and a health clinic) at speeds of 500/500 Mbps, which Recipient A reported on the Annual Report Addendums.
In addition, Recipient A took care not to include any Personally Identifiable Information (PII) or other sensitive data in their Annual Report, since this report is considered public and will be shared with Congress.

## Annual Report
Does your project contain an infrastructure build component?
Yes
OMB Control No. 0690-0039 Expiration Date: 6/30/2028
TRIBAL BROADBAND CONNECTIVITY PROGRAM ANNUAL REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: | Recipient A | Award Identification Number: |  | NT25TBC0000000
| Recipient Street Address: | 123 Street Lane | Report Submission Date (MM/DD/YYYY): |  | 2028-04-30
| City, State, Zip Code: | Washington, DC 20001
| UEI Number: | 123456789
| Period of Performance Start Date (MM/DD/YYYY): | 2025-01-01 | Period of Performance End Date (MM/DD/YYYY): |  | 2028-12-31
| Report Period Start Date (MM/DD/YYYY): | 2027-04-01 | Report Period End Date (MM/DD/YYYY): |  | 2028-03-31
1 | Infrastructure Deployment Recipients: Provide the total number of project locations (Tribal households, businesses, and community anchor institutions) that are passed/serviceable due to TBCP grant funds. Attach shapefiles for the connected locations and service area. (600 words or less) Use and Adoption Recipients: N/a Planning Recipients: N/a
Recipient A connected 4 Tribal households, 8 Tribal businesses, and 2 CAIs in Year 3 of the project, ahead of schedule.
2 | Describe all project activities completed with grant funds during the past annual report period. (600 words or less)
3 | List all contractors that received grant funds and briefly explain what the funds were used for. Report this item cumulatively from the start of the award through the end of the annual report period captured in this report. If your project does not include contractors, write “NA”. (600 words or less)
Recipient A's contractor EZ Build, a construction firm, received grant funds in Year 3. Over the past year, EZ Build procured construction and network build equipment, including but not limited to 24 and 42 count fiber cable, a rock borer, a fusions splicer, and RAN equipment. EZ Build deployed 55 miles of fiber optic cable (40 miles of middle-mile fiber and 15 miles of last-mile fiber), and initiated construction on the monopole towers, including but not limited to digging tower foundations and erecting the tower superstructures.
4 | Describe how your organization (i.e. the grant recipient) expended grant funds. Report this item cumulatively from the start of the award through the end of the annual report period captured in this report. (600 words or less)
During the past year, Recipient A expended funds by conducting project oversight and performing grant administration tasks. The recipient met with EZ Build, the project's construction contractor, on a biweekly basis to review construction progress and, when necessary, revise project timelines.
5 | List all subrecipients that received grant funds and briefly explain what the funds were used for. Report this item cumulatively from the start of the award through the end of the annual report period captured in this report. If your project does not include subrecipients, write “NA”. (600 words or less)
NA
6 | Describe any challenges your organization experienced while conducting your TBCP project during the past annual report period. Explain how you addressed those challenges. (600 words or less)
Challenges included permitting delays and access to qualified workforce. To combat the permitting backlog, our organization increased coordination with agencies and utilities between planning and zoning construction department. Improving project management strategies by implementing digital permitting systems improved efficiency. There were also delays due to weather conditions, equipment procurement, and supply chain disruption. Respectively, resolutions from these issues included executing contingency plans during severe weather, investing in reliable equipment, and maintaining clear communications with suppliers.
7 | Describe how your organization met and maintained broadband requirements, as outlined in the NOFO purpose areas below. (600 words or less) Infrastructure Deployment: Broadband infrastructure deployment, including (but not limited to) support for the establishment of carrier-neutral submarine cable landing stations. Use and Adoption: Projects that promote the adoption and use of broadband services, including: affordable broadband programs, such as providing free or reduced-cost broadband service and preventing disconnection of existing broadband service; distance learning; telehealth; digital inclusion efforts; and broadband adoption activities. Planning: Proposals to conduct planning, engineering, feasibility, or sustainability studies as part of the necessary steps to develop a technological solution for broadband deployment.
Recipient A conducted broadband infrastructure deployment via the construction of 2 wireless towers and middle- and last-mile fiber networks.
8 | Describe all project achievements during the annual reporting period. (600 words or less)
During the past year, the recipient's infrastructure deployment project accomplished the following goals: completed site preparation work (ground clearing and creation of an access road) for the deployment of 2 monopole towers, signed a 5-year IRU with a middle-mile network provider, procured construction and network equipment, deployed equipment to build sites, installed 55 miles of buried fiber (40 miles of middle-mile fiber and 15 miles of last-mile fiber), and initiated construction on 2 monopole towers (foundation digging and tower superstructure installation). Ahead of schedule, Recipient A was also able to connect 4 Tribal households, 8 businesses, and 2 CAIs to the last-mile fiber network at speeds of 500/500 Mbps.
9 | INFRASTRUCTURE DEPLOYMENT PROJECTS: Using the Excel spreadsheet template titled "TBCP Reports Addendum A", please provide an updated count of Households within each of the eligible census block groups along with their Location ID that you connected to your network. The locations should match and conform to the Federal Communications Commission (FCC) Broadband Serviceable Location Fabric, which is a unique identifier for the geographic coordinates and the address(es) associated with each location.
10 | INFRASTRUCTURE DEPLOYMENT PROJECTS: Using the Excel spreadsheet template titled "TBCP Reports Addendum B", please provide an updated count of Tribal Businesses within each of the eligible census block groups along with their Location ID that you connected to your network. The locations should match and conform to the Federal Communications Commission (FCC) Broadband Serviceable Location Fabric, which is a unique identifier for the geographic coordinate and the address(es) associated with each location.
11 | INFRASTRUCTURE DEPLOYMENT PROJECTS: Using the Excel spreadsheet template titled "TBCP Reports Addendum C", please provide an updated count of Community Anchor Institutions (CAIs) within each of the eligible census block groups along with their Location ID that you connected to your network. The locations should match and conform to the Federal Communications Commission (FCC) Broadband Serviceable Location Fabric, which is a unique identifier for the geographic coordinates and the address(es) associated with each location.
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: |  |  | Telephone (area code, number and extension): |  | 123-456-7890 ext 1
John Smith
| Signature of Certifying Official: |  |  | Email Address: |  | JohnSmith@RA.org
/s/ John Smith
|  |  |  | Date: |  | 2028-04-28
PAPERWORK REDUCTION ACT (PRA) OF 1995 (Public Law 104-13) STATEMENT OF PUBLIC BURDEN: An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information subject to the requirements of the Paperwork Reduction Act unless that collection of information displays a currently valid OMB Control Number 0690-0039. Public reporting burden for these reports is estimated to average 40 hours per response. This burden includes time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate to Margaret Gutierrez, Director, Tribal Broadband Connectivity Program, National Telecommunications and Information Administration, U.S Department of Commerce, 1401 Constitution Avenue, Room 4887, Washington, DC 20230 via telephone at 202-235-5467 or by email at mgutierrez@ntia.gov.

## TBCP Reports Addendum A
Does your project contain an infrastructure build component?
Yes
OMB Control No. 0690-0039 Expiration Date: 06/30/2028
TRIBAL BROADBAND CONNECTIVITY PROGRAM REPORTS ADDENDUM A
Recipient Organization: |  | Recipient A |  |  | Award Identification Number: | [7 empty] | NT25TBC0000000
Recipient Street Address: |  | 123 Street Lane |  |  | Report Submission Date (MM/DD/YYYY): | [7 empty] | 2028-04-30
City, State, Zip Code: |  | Washington, DC 20001 |  |  | UEI Number: | [7 empty] | 123456789
Reporting Period Start Date (MM/DD/YYYY): |  | 2027-04-01 |  |  | Report Type: |  |  |  | Baseline Report
Reporting Period End Date (MM/DD/YYYY): |  | 2028-03-31 | [6 empty] | Annual Report
Household Locations in the Service Area
The Location ID is the Fabric ID associated with the Federal Communications Commission maps required by the Broadband Deployment Broadband Deployment Accuracy and Technology Availability (DATA) Act, Pub. L. No. 116-130, 134 Stat. 228 (2020) (codified at 47 U.S.C. §§ 641-646) (Broadband DATA Maps). The “location_id” data element is a unique identifier for the location served. A Location ID should be included for each location in the Broadband Serviceable Location Fabric when the Fabric is made available to filers. Number of units refers to one location that has multiple units within that one location. Infrastructure Deployment projects should insert rows at the bottom of the table to report additional location data if needed.
Location ID | Street Address | City | State | ZIP |  | Latitude |  | Longitude |  | Census Block Group | # of Units | Fixed Technology Code | Open For Sale (OFS) Date | Deployed Date | Provider ID |  |  | Brand Name | Maxdown | Maxup
123456789 | 1 Highway 4 | Indian Country | USA | 12345 |  | 38.8883 |  | -77.0168 |  | 110019800001080 | 1 | 50 | 2028-02-01 | 2028-02-15 | XYZABC123 |  |  | Friendly Neighborhood Broadband | 500 | 500
123456788 | 2 Highway 4 | Indian Country | USA | 12345 |  | 38.8883 |  | -77.0168 |  | 110019800001080 | 1 | 50 | 2028-02-01 | 2028-02-15 | XYZABC123 | XYZABC123 | XYZABC123 | Friendly Neighborhood Broadband | 500 | 500
123456787 | 3 Highway 4 | Indian Country | USA | 12345 |  | 38.8883 |  | -77.0168 |  | 110019800001080 | 2 | 50 | 2028-02-01 | 2028-02-15 | XYZABC123 | XYZABC123 | XYZABC123 | Friendly Neighborhood Broadband | 500 | 500
123456786 | 4 Highway 4 | Indian Country | USA | 12345 |  | 38.8883 |  | -77.0168 |  | 110019800001080 | 1 | 50 | 2028-02-01 | 2028-02-15 | XYZABC123 | XYZABC123 | XYZABC123 | Friendly Neighborhood Broadband | 500 | 500
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | John Smith |  |  |  |  | Telephone (area code, number and extension): | [5 empty] | 123-456-7890 ext 1
| Signature of Certifying Official: | /s/ John Smith |  |  |  |  | Email Address: | [5 empty] | JohnSmith@RA.org
[7 empty] | Date: | [5 empty] | 2028-04-28
PAPERWORK REDUCTION ACT (PRA) OF 1995 (Public Law 104-13) STATEMENT OF PUBLIC BURDEN: An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information subject to the requirements of the Paperwork Reduction Act unless that collection of information displays a currently valid OMB Control Number 0690-0039. Public reporting burden for these reports is estimated to average 40 hours per response. This burden includes time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate to Margaret Gutierrez, Director, Tribal Broadband Connectivity Program, National Telecommunications and Information Administration, U.S Department of Commerce, 1401 Constitution Avenue, Room 4887, Washington, DC 20230 via telephone at 202-235-5467 or by email at mgutierrez@ntia.gov.

## TBCP Reports Addendum B
Does your project contain an infrastructure build component?
Yes
OMB Control No. 0690-0039 Expiration Date: 06/30/2028
TRIBAL BROADBAND CONNECTIVITY PROGRAM REPORTS ADDENDUM B
Recipient Organization: |  | Recipient A |  |  | Award Identification Number: | [7 empty] | NT25TBC0000000
Recipient Street Address: |  | 123 Street Lane |  |  | Report Submission Date (MM/DD/YYYY): | [7 empty] | 2028-04-30
City, State, Zip Code: |  | Washington, DC 20001 |  |  | UEI Number: | [7 empty] | 123456789
Reporting Period Start Date (MM/DD/YYYY): |  | 2027-04-01 |  |  | Report Type: |  |  |  | Baseline Report
Reporting Period End Date (MM/DD/YYYY): |  | 2028-03-31 | [6 empty] | Annual Report
Tribal Business Locations in the Service Area
The Location ID is the Fabric ID associated with the Federal Communications Commission maps required by the Broadband Deployment Broadband Deployment Accuracy and Technology Availability (DATA) Act, Pub. L. No. 116-130, 134 Stat. 228 (2020) (codified at 47 U.S.C. §§ 641-646) (Broadband DATA Maps). The “location_id” data element is a unique identifier for the location served. A Location ID should be included for each location in the Broadband Serviceable Location Fabric when the Fabric is made available to filers. Number of units refers to one location that has multiple units within that one location. Infrastructure Deployment projects should insert rows at the bottom of the table to report additional location data if needed.
Location ID | Street Address | City | State | ZIP |  | Latitude |  | Longitude |  | Census Block Group | # of Units | Fixed Technology Code | Open For Sale (OFS) Date | Deployed Date | Provider ID | Brand Name | Maxdown | Maxup
123456789 | 1 Highway 4 | Indian Country | USA | 12345 |  | 38.8883 |  | -77.0168 |  | 110019800001080 | 1 | 50 | 2028-02-01 | 2028-02-26 | XYZABC123 | Friendly Neighborhood Broadband | 500 | 500 | 100 | 100
123456788 | 2 Highway 4 | Indian Country | USA | 12345 |  | 38.8883 |  | -77.0168 |  | 110019800001080 | 1 | 50 | 2028-02-01 | 2028-02-26 | XYZABC123 | Friendly Neighborhood Broadband | 500 | 500 | 100 | 100
123456787 | 3 Highway 4 | Indian Country | USA | 12345 |  | 38.8883 |  | -77.0168 |  | 110019800001080 | 1 | 50 | 2028-02-01 | 2028-02-26 | XYZABC123 | Friendly Neighborhood Broadband | 500 | 500 | 100 | 100
123456786 | 4 Highway 4 | Indian Country | USA | 12345 |  | 38.8883 |  | -77.0168 |  | 110019800001080 | 1 | 50 | 2028-02-01 | 2028-02-26 | XYZABC123 | Friendly Neighborhood Broadband | 500 | 500 | 100 | 100
123456785 | 5 Highway 4 | Indian Country | USA | 12345 |  | 38.8883 |  | -77.0168 |  | 110019800001080 | 1 | 50 | 2028-02-01 | 2028-02-26 | XYZABC123 | Friendly Neighborhood Broadband | 500 | 500
123456784 | 6 Highway 4 | Indian Country | USA | 12345 |  | 38.8883 |  | -77.0168 |  | 110019800001080 | 1 | 50 | 2028-02-01 | 2028-02-26 | XYZABC123 | Friendly Neighborhood Broadband | 500 | 500
123456783 | 7 Highway 4 | Indian Country | USA | 12345 |  | 38.8883 |  | -77.0168 |  | 110019800001080 | 1 | 50 | 2028-02-01 | 2028-02-26 | XYZABC123 | Friendly Neighborhood Broadband | 500 | 500
123456782 | 8 Highway 4 | Indian Country | USA | 12345 |  | 38.8883 |  | -77.0168 |  | 110019800001080 | 1 | 50 | 2028-02-01 | 2028-02-26 | XYZABC123 | Friendly Neighborhood Broadband | 500 | 500
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | John Smith |  |  |  |  | Telephone (area code, number and extension): | [5 empty] | 123-456-7890 ext 1
| Signature of Certifying Official: | /s/ John Smith |  |  |  |  | Email Address: | [5 empty] | JohnSmith@RA.org
[7 empty] | Date: | [5 empty] | 2028-04-28
PAPERWORK REDUCTION ACT (PRA) OF 1995 (Public Law 104-13) STATEMENT OF PUBLIC BURDEN: An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information subject to the requirements of the Paperwork Reduction Act unless that collection of information displays a currently valid OMB Control Number 0690-0039. Public reporting burden for these reports is estimated to average 40 hours per response. This burden includes time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate to Margaret Gutierrez, Director, Tribal Broadband Connectivity Program, National Telecommunications and Information Administration, U.S Department of Commerce, 1401 Constitution Avenue, Room 4887, Washington, DC 20230 via telephone at 202-235-5467 or by email at mgutierrez@ntia.gov.

## TBCP Reports Addendum C
Does your project contain an infrastructure build component?
Yes
OMB Control No. 0690-0039 Expiration Date: 06/30/2028
TRIBAL BROADBAND CONNECTIVITY PROGRAM REPORTS ADDENDUM C
Recipient Organization: |  | Recipient A |  |  | Award Identification Number: | [7 empty] | NT25TBC0000000
Recipient Street Address: |  | 123 Street Lane |  |  | Report Submission Date (MM/DD/YYYY): | [7 empty] | 2028-04-30
City, State, Zip Code: |  | Washington, DC 20001 |  |  | UEI Number: | [7 empty] | 123456789
Reporting Period Start Date (MM/DD/YYYY): |  | 2027-04-01 |  |  | Report Type: |  |  |  | Baseline Report
Reporting Period End Date (MM/DD/YYYY): |  | 2028-03-31 | [6 empty] | Annual Report
Community Anchor Institution (CAI) Locations in the Service Area
The Location ID is the Fabric ID associated with the Federal Communications Commission maps required by the Broadband Deployment Broadband Deployment Accuracy and Technology Availability (DATA) Act, Pub. L. No. 116-130, 134 Stat. 228 (2020) (codified at 47 U.S.C. §§ 641-646) (Broadband DATA Maps). The “location_id” data element is a unique identifier for the location served. A Location ID should be included for each location in the Broadband Serviceable Location Fabric when the Fabric is made available to filers. Number of units refers to one location that has multiple units within that one location. Infrastructure Deployment projects should insert rows at the bottom of the table to report additional location data if needed.
Location ID | Street Address | City | State | ZIP |  | Latitude |  | Longitude |  | Census Block Group | # of Units | Fixed Technology Code | Open For Sale (OFS) Date | Deployed Date | Provider ID | Brand Name | Maxdown | Maxup | CAI Type
123456789 | 1 Highway 4 | Indian Country | USA | 12345 |  | 38.8883 |  | -77.0168 |  | 110019800001080 | 1 | 50 | 2028-02-01 | 2028-02-26 | XYZABC123 | Friendly Neighborhood Broadband | 500 | 500 | G | 100 | 100
123456788 | 2 Highway 4 | Indian Country | USA | 12345 |  | 38.8883 |  | -77.0168 |  | 110019800001080 | 1 | 50 | 2028-02-01 | 2028-02-26 | XYZABC123 | Friendly Neighborhood Broadband | 500 | 500 | H | 100 | 100
[20 empty] | 100 | 100
[20 empty] | 100 | 100
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | John Smith |  |  |  |  | Telephone (area code, number and extension): | [5 empty] | 123-456-7890 ext 1
| Signature of Certifying Official: | /s/ John Smith |  |  |  |  | Email Address: | [5 empty] | JohnSmith@RA.org
[7 empty] | Date: | [5 empty] | 2028-04-28
PAPERWORK REDUCTION ACT (PRA) OF 1995 (Public Law 104-13) STATEMENT OF PUBLIC BURDEN: An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information subject to the requirements of the Paperwork Reduction Act unless that collection of information displays a currently valid OMB Control Number 0690-0039. Public reporting burden for these reports is estimated to average 40 hours per response. This burden includes time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate to Margaret Gutierrez, Director, Tribal Broadband Connectivity Program, National Telecommunications and Information Administration, U.S Department of Commerce, 1401 Constitution Avenue, Room 4887, Washington, DC 20230 via telephone at 202-235-5467 or by email at mgutierrez@ntia.gov.