## Baseline Scenario
Sample Use and Adoption Report Scenario
Sample Use and Adoption Scenario – BASELINE REPORT
Recipient A received $275,000 to conduct a Use and Adoption grant. With the funds, the recipient plans to provide broadband education, purchase Internet capable devices, and conduct trainings.
Because Recipient A's period of performance begins on January 1, 2025, the first period reported in their Baseline Report will only cover three months instead of six. The Year 1, Period 1 column will reflect the following dates: 1/1/2025–3/31/2025. The Year 1, Period 2 column will encompass the next six months, and the Year 2, Period 1 column will encompass the final three months of their project, which ends 12/31/2025.
There are 80 tribal households, 5 tribal businesses, and 6 tribal community anchor institutions (CAIs) within Recipient A's service area. With TBCP funds, the Recipient A will purchase one year of subsidized broadband for all 80 tribal households, 2 tribal businesses (a gas station and convenience shop), and 3 CAIs (the tribe’s government office, community center, and health center). All 80 households are passed/serviceable (have the ability to connect to broadband infrastructure), but 50 do not currently have service due to an inability to afford customer premise equipment (CPE), monthly Internet payments, and/or Internet capable devices. All tribal businesses and CAIs within the funded service area are serviceable but do not have access to minimum qualifying service. The subsidized service will provide speeds of 100/20 Mbps or greater.
Recipient A also plans to purchase and distribute broadband devices. All 80 households will receive one $1,000 laptop. Each of the 50 households that do not currently have broadband service, 2 businesses, and 3 CAIs will receive a router and other customer premise equipment necessary to connect to the Internet ($100 per household, business, or CAI). Eight desktop computers ($1,500 each) will be procured for the CAIs: 3 computers for the government office, 4 computers for the community center, and 1 computer for the health center. Finally, Recipient A will purchase 20 tablets (each worth $300) for staff.
Two new positions—an IT Director and an IT Assistant—will be created as part of the grant. Recipient A plans to hold one workforce development training for staff (estimated attendance of 25) and three digital literacy trainings for tribal members (estimated attendance of 100 per training).
Recipient A will hire contractors to install the CPE and conduct the workforce development and digital literacy trainings.
Simplified Project Plan
|  | Year 1 Period 1 | Year 1 Period 2 | Year 2 Period 1
| Procure and distribute laptops | X
| Procure and distribute computers | X
| Procure and distribute routers/CPE | X
| Procure and distribute tablets | X
| Install CPE | X | X
| Purchase Internet subscriptions |  | X
| Conduct workforce development training | X
| Conduct digital literacy training | X | X | X
| Hire IT Director and IT Assistant | X
Summary of Use & Adoption Solutions and Outcomes:
● 80 broadband subscriptions for tribal households for a period of one year
● 2 broadband subscriptions for tribal businesses
● 3 broadband subscriptions for tribal CAIs
● 80 laptops for tribal households at $1,000 per unit
● 55 routers/CPE for unserved tribal households, businesses, and CAIs at $100 per unit
● 8 computers for tribal CAIs at $1,500 per unit
● 20 tablets for tribal staff at $300 per unit
● 2 new positions
● 1 workforce development training with an estimated attendance of 25
● 3 digital literacy trainings with an estimated attendance of 100 for each training

## Baseline Report
|  | Select Project Type Below | [10 empty] | End Period
|  | Use and Adoption | [10 empty] | 2026-03-31
OMB Control No. 0690-0039 Expiration Date: 6/30/2028
TRIBAL BROADBAND CONNECTIVITY PROGRAM BASELINE REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: | Recipient A |  |  |  |  | Award Identification Number: |  |  |  | NT25TBC0000000
| Recipient Street Address: | 123 Street Lane |  |  |  |  | Report Submission Date (MM/DD/YYYY): |  |  |  | 2025-02-14
| City, State, Zip Code: | Washington, DC 20001
| UEI Number: | 123456789
| Period of Performance Start Date (MM/DD/YYYY): | 2025-01-01 |  |  |  |  | Period of Performance End Date (MM/DD/YYYY): |  |  |  | 2025-12-31
| Report Period Start Date (MM/DD/YYYY): | 2025-01-01 |  |  |  |  | Report Period End Date (MM/DD/YYYY): |  |  |  | 2025-12-31
BROADBAND USE & ADOPTION AND INFRASTRUCTURE MILESTONES/KEY INDICATORS
INFRASTRUCTURE DEPLOYMENT AND PLANNING PROJECT MILESTONE CATEGORIES
1 | Use the following table to indicate the anticipated percent completion for all Infrastructure Deployment and/or Planning activities. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. Report this information cumulatively for all applicable project periods. Each row should end with 100% completion. Once the 100% mark is reached, continue to enter 100% for each subsequent cell in the row until you reach the Year and Period in which your project’s period of performance ends. For additional explanation, see the Reporting Guidance and Instructions document. For the purposes of this section, equipment procurement refers to activities associated with identifying and procuring necessary equipment for your project. Equipment deployment refers to all activities associated with the installation of equipment purchased as part of your TBCP project. If you are using milestone 1k. Other (please specify), include a brief description of the milestone by typing over the portion that reads (please specify).
| MILESTONE CATEGORIES |  | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
|  |  | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
1a. Overall Project
1b. Environmental Assessment
1c. Network Design
1d. Rights Of Way
1e. Construction Permits And Other Approvals
1f. Site Preparation
1g. Equipment Procurement
1h. Network Build (all components - owned, leased, Indefeasible Rights of Use, etc.)
1i. Equipment Deployment
1j. Network Testing
1k. Other (please specify)
INFRASTRUCTURE DEPLOYMENT NETWORK BUILD PROGRESS
2 | Use the following table to provide information about the progress of your Infrastructure Deployment and/or Planning project. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. Except for 2h, report information cumulatively for all applicable project periods. For additional explanation, see the Reporting Guidance and Instructions document. For the purposes of this section, new wireless links refers to the number of new wireless transmissions--comprised of a source node (transmitter) to a destination node (receiver)--that exist due to TBCP funding; wireless links may be middle or last mile. New towers refers to any towers that are constructed, leased, and/or upgraded or retrofitted with grant funds; this includes in-situ vertical structures that are outfitted with network equipment (water towers, rooftops, steeples, etc.). New interconnection points refers to any new physical connections where traffic is routed from one network to another created as a result of TBCP funds. If using the milestones 2j. Other (please specify), include a brief description of the milestone by typing over the portion that reads (please specify).
| NETWORK BUILD PROGRESS | MIDDLE OR LAST MILE | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
|  |  | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
2a. Number of new fiber miles (aerial or underground) constructed or upgraded with TBCP funds
2b. Number of fiber miles leased with TBCP funds
2c. Number of existing fiber miles upgraded with TBCP funds
2d. Number of new wireless links created through TBCP funds
2e. Number of new towers constructed with TBCP funds
2f. Number of new interconnection points created through TBCP funds
2g. Number of signed agreements with broadband wholesalers or last mile providers from TBCP funds
2h. Number of potential agreements (i.e., agreements currently being negotiated) with broadband wholesalers or last mile providers from TBCP funds (This number should NOT be reported cumulatively)
2i. Obtained licenses: 2.5 (EBS), 3.5 (CBRS) from TBCP funds
2j. Other (please specify)
INFRASTRUCTURE DEPLOYMENT KEY INDICATORS
3 | Use the following table to provide the number of unserved tribal households, unserved tribal households at or below 150% of the poverty line, unserved tribal businesses, and unserved tribal community anchor institutions (CAIs) connected to broadband infrastructure through your Infrastructure Deployment project. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. Report information cumulatively for all applicable project periods. For additional explanation, see the Reporting Guidance and Instructions document. Provide the number of structures connected according to connectivity speed (100/20 and 25/3) and connectivity type (wireless, fiber).
| PROJECTED NUMBER OF SUBSCRIBERS AND SPEED |  | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
| SUBSCRIBER TYPE | SPEED TYPE | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
| 3a. Unserved Tribal Households | Number of Unserved Tribal Households connected to broadband infrastructure
Number of previously Unserved Tribal Households with broadband availability at speeds of at least 100/20 Mbps through TBCP funds
Number of previously Unserved Tribal Households with broadband availability at speeds of at least 25/3 Mbps through TBCP funds
Number of Unserved Tribal Households connected to broadband infrastructure by copper or DSL cable line
Number of previously Unserved Tribal Households with broadband availability by wireless connection through TBCP funds
Number of previously Unserved Tribal Households with broadband availability by fiber optic connection through TBCP funds
| 3b. Tribal Households | Number of Tribal Households connected to broadband infrastructure
Number of Tribal Households connected to broadband infrastructure at speeds of at least 100/20
Number of Tribal Households connected to broadband infrastructure at speeds of at least 25/3
Number of Tribal Households connected to broadband infrastructure by copper or DSL cable line
Number of Tribal Households connected to broadband infrastructure by wireless connection
Number of Tribal Households connected to broadband infrastructure by fiber optic connection
| 3c. Unserved Tribal Households At or Below 150% of the Poverty Line | Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at speeds of at least 100/20 Mbps through TBCP funds
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at speeds of 25/3 Mbps through TBCP funds
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by copper or DSL cable line
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by wireless connection through TBCP funds
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by fiber optic connection through TBCP funds
| 3d. Unserved Tribal Businesses | Number of Unserved Tribal Businesses connected to broadband infrastructure
Number of previously Unserved Tribal Businesses with broadband availability at speeds of at least 100/20 Mbps through TBCP funds
Number of previously Unserved Tribal Businesses with broadband availability at speeds of at least 25/3 Mbps through TBCP funds
Number of Unserved Tribal Businesses connected to broadband infrastructure by copper or DSL cable line
Number of Unserved Tribal Businesses connected to broadband infrastructure by wireless connection through TBCP funds
Number of Unserved Tribal Businesses connected to broadband infrastructure by fiber optic connection through TBCP funds
| 3e. Unserved Tribal Community Anchor Institutions (CAIs) | Number of Unserved Tribal CAIs connected to broadband infrastructure
Number of previously Unserved Tribal CAIs with broadband availability at speeds of at least 100/20 Mbps through TBCP funds
Number of previously Unserved Tribal CAIs with broadband availability at speeds of at least 25/3 Mbps through TBCP funds
Number of Unserved Tribal CAIs connected to broadband infrastructure by copper or DSL cable line
Number of Unserved Tribal CAIs connected to broadband infrastructure by wireless connection through TBCP funds
Number of Unserved Tribal CAIs connected to broadband infrastructure by fiber optic connection through TBCP funds
BROADBAND USE & ADOPTION KEY INDICATORS
4 | Use the following table to provide the number of unserved tribal households, unserved tribal businesses, and unserved tribal community anchor institutions (CAIs) that receive new access to broadband through your Use and Adoption project. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. Report information cumulatively for all applicable project periods. For additional explanation, see the Reporting Guidance and Instructions document. For the purposes of this section, passed/serviceable refers to structures within the service area that have the physical infrastructure in place to connect to the internet. Structures that are "passed/serviceable" may be served (if they have an internet connection at speeds of 25/3 Mbps or greater) or unserved (if they do not have a broadband subscription or if they have an internet connection that is slower than 25/3 Mbps). New access refers to tribal households, businesses, and CAIs within your service area that received access to qualifying broadband service (25/3 Mbps or greater) for the first time (i.e., previously had no broadband connectivity or connectivity of less than 25/3 Mbps) as a result of TBCP funds.
| PROJECTED NUMBER OF SUBSCRIBERS AND SPEED |  | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
| BENEFICIARY TYPE | ACCESS TYPE | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
| 4a. Unserved Tribal Households | Number of Unserved Tribal Households passed/serviceable | 80
|  | Number of previously unserved Tribal Households with new access through TBCP-funded broadband subscriptions (i.e. prepayment) | 0 | 80 |  | 80
| 4b. Tribal Households | Number of Tribal Households passed/serviceable
Number of Tribal Households with new access
| 4c. Unserved Tribal Households At or Below 150% of the Poverty Line | Number of Unserved Tribal Households At or Below 150% of the Poverty Line passed/serviceable
Number of previously unserved Tribal Households At or Below 150% of the Poverty Line with new access through TBCP funds
| 4d. Unserved Tribal Businesses | Number of Unserved Tribal Businesses passed/serviceable
Number of previously unserved Tribal Businesses with new access through TBCP funds
| 4e. Unserved Tribal Community Anchor Institutions | Number of Unserved Tribal Community Anchor Institutions passed/serviceable
Number of previously unserved Tribal Community Anchor Institutions with new access through TBCP funds
BROADBAND USE & ADOPTION DEMOGRAPHIC INDICATORS
5
| DEMOGRAPHIC INDICATORS |  | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
| SUBSCRIBER TYPE | ESTIMATED POPULATION IN SERVICE AREA | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
| 5a. Unserved Tribal Population | Number of Unserved Native American/Alaska Native/Native Hawaiian Households in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Tribal Businesses in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Community Anchor Institutions in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Households At or Below 150% of the Poverty Line in funded service area
| 5b. Tribal Population | Number of Tribal Households in funded service area
Number of Tribal Businesses in funded service area
Number of Tribal Community Anchor Institutions in funded service area
Number of Tribal Households At or Below 150% of the Poverty Line in funded service area
INFRASTRUCTURE DEPLOYMENT, PLANNING, AND BROADBAND USE & ADOPTION WORKFORCE INDICATORS
6 | Use the following table to provide workforce data for your Infrastructure Deployment, Planning, or Use and Adoption project. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. Report information cumulatively for all applicable project periods. For additional explanation, see the Reporting Guidance and Instructions document.
| WORKFORCE INDICATORS |  | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
| OUTCOMES | QUESTIONS | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
| 6a. Telework | Number of individuals with ability to telework prior to receiving TBCP grant funds
Number of individuals with ability to telework after receiving TBCP grant funds
| 6b. New Positions | Number of positions funded by TBCP | 2 | 2 |  | 2
Number of new positions filled through TBCP funds
| 6c. Participation in Workforce Development Trainings | Number of individuals who attended a TBCP-funded workforce development training event | 25 | 25 |  | 25
| 6d. Workforce Development Trainings | Number of workforce development training events held with TBCP funds | 1 | 1 |  | 1
BROADBAND USE & ADOPTION EDUCATIONAL SUCCESS INDICATORS
7 | Use the following table to provide educational data for your Use and Adoption project. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. Report information cumulatively for all applicable project periods. For additional explanation, see the Reporting Guidance and Instructions document.
| EDUCATIONAL SUCCESS INDICATORS |  | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
| OUTCOMES | QUESTIONS | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
| 7a. Access to Online Learning | Number of individuals with ability to participate in online learning prior to receiving TBCP grant funds
Number of individuals with ability to participate in online learning after receiving TBCP grant funds
| 7b. Participation in Online Learning | Number of individuals who attend online learning classes
Number of individuals who attend virtual/in-person school activities
| 7c. Parental Participation in School Activities | Number of parents/legal guardians who attend virtual/in-person school activities
| 7d. High School Enrollment and Completion | Number of individuals enrolled in high school
Number of individuals who successfully exited high school program with degree (diploma/GED)
| 7e. School Participation in Remote or Hybrid Learning | Number of schools in program
Number of schools engaged in remote or hybrid learning model through TBCP funds
| 7f. School Participation in In-Person Learning | Number of schools in program
Number of schools engaged in in-person learning model through TBCP funds
| 7g. School Participation in Hybrid Learning | Number of schools in program
Number of schools engaged in hybrid learning model through TBCP funds
BROADBAND USE & ADOPTION TELEHEALTH INDICATORS
8 | Use the following table to provide telehealth data for your Use and Adoption project. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. Report information cumulatively for all applicable project periods. For additional explanation, see the Reporting Guidance and Instructions document.
| TELEHEALTH INDICATORS |  | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
| OUTCOMES | QUESTIONS | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
| 8a. Access to Telehealth Services | Number of individuals with ability to participate in telehealth services prior to receiving TBCP grant funds
Number of individuals with ability to participate in telehealth service after receiving TBCP grant funds
| 8b. New Access to Telehealth Services | Number of individuals with new access to telehealth services
| 8c. Telehealth Appointments Scheduled | Estimated number of telehealth appointments scheduled
BROADBAND USE & ADOPTION DIGITAL INCLUSION INDICATORS
9 | Use the following table to provide digital inclusion data for your Use and Adoption project. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. Report information cumulatively for all applicable project periods. For additional explanation, see the Reporting Guidance and Instructions document.
| DIGITAL INDICATORS |  | Year 1 - Report Period Ending |  |  | Year 2 - Report Period Ending |  | Year 3 - Report Period Ending |  |  |  | Year 4 - Report Period Ending |  | Year 5 - Report Period Ending
| OUTCOMES | QUESTIONS | 2025-03-31 | 2025-09-30 |  | 2026-03-31 | 2026-09-30 | 2027-03-31 |  | 2027-09-30 |  | 2028-03-31 | 2028-09-30 | 2029-03-31 | 2029-09-30
| 9a. Participation in Affordable Broadband Connectivity Program | Number of households in affordable broadband connectivity programs
| 9b. Digital Literacy Trainings | Number of digital literacy training events held with TBCP funds | 1 | 2 |  | 3
| 9c. Tribal Programs Transitioned to Online Platform | Number of Tribal programs transitioned to online platform with TBCP funds
| 9d. Devices Distributed to Individuals | Number of individuals given device
| 9e. Devices Distributed to Households | Number of households given device
| 9f. Devices Distributed to Other Entities (i.e., community anchor institutions, schools, Tribal businesses) | Number of other entities given device
BROADBAND USE & ADOPTION TYPE OF INTERNET DEVICES
10 | Use the following table to record the internet connectivity devices that you plan to acquired for your Use and Adoption project. All devices that you plan to purchase and distribute throughout your award should appear in this table. For additional explanation, see the Reporting Guidance and Instructions document. For each row, select the appropriate device from the dropdown menu in the Device Type column, provide the number of units purchased with grant funds under the Number of Devices column, and provide the total cost under the Total Cost column. If you select the device type Other, provide a brief description of the device in the Total Cost column.
| Device Type |  | Number of Devices |  |  |  |  | Total Cost
| Laptop |  | 80 |  |  |  |  | 80000
| Computer |  | 8 |  |  |  |  | 12000
| Router |  | 55 |  |  |  |  | 5500
| Tablet |  | 20 |  |  |  |  | 6000
INFRASTRUCTURE DEPLOYMENT, PLANNING, AND BROADBAND USE & ADOPTION TYPE OF COLLABORATORS
11 | Use the following table to provide information about the contractors, subrecipients, and unfunded collaborators involved in your TBCP project. Throughout this report, the dates at the top of each section correspond with report period end dates. In each column, provide the expected completion figures for the previous six months. For example, if the date at the top of a column is 9/30/2024, that column should include anticipated completion data for the report period 4/1/2024 through 9/30/2024. Repeat this process for all report periods of your project. Note that the initial and final report periods for your project may not equal a full six months. All contractors, subrecipients, and collaborators that you plan to work with throughout your award should appear in this table. For additional explanation, see the Reporting Guidance and Instructions document. In the Collaborator Organization Type column, indicate whether the participating organization is a Contractor, Subrecipient, or Informal Unfunded Collaborator by selecting an option from the dropdown menu, then put the organization's name into the Collaborator Organization Name column. Enter the full name of the participating organization’s point of contact (POC) in the Collaborator POC Name, and the point of contact’s email address in the Collaborator POC Email column. Indicate whether the participant is Funded or Unfunded by selecting an option from the dropdown menu in the Funded or Unfunded Collaboration column.
COLLABORATORS
| Collaborator Organization Type | Collaborator Organization Name | Collaborator POC Name |  | Collaborator POC Email |  |  |  | Funded or Unfunded Collaboration
| Contractor | CPE Installers, Inc | Adam Smith |  | Asmith@CPEInstallers.com |  |  |  | Funded
| Contractor | Technology Training Solutions | Jane Train |  | Jtrain@TTS.org |  |  |  | Funded
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | [5 empty] | Telephone (area code, number and extension): |  |  |  | 123-456-7890 ext 1
John Smith
| Signature of Certifying Official: | [5 empty] | Email Address: |  |  |  | JohnSmith@RA.org
/s/ John Smith
[7 empty] | Date: |  |  |  | 2025-02-13
PAPERWORK REDUCTION ACT (PRA) OF 1995 (Public Law 104-13) STATEMENT OF PUBLIC BURDEN: An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information subject to the requirements of the Paperwork Reduction Act unless that collection of information displays a currently valid OMB Control Number 0690-0039. Public reporting burden for these reports is estimated to average 40 hours per response. This burden includes time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate to Margaret Gutierrez, Director, Tribal Broadband Connectivity Program, National Telecommunications and Information Administration, U.S Department of Commerce, 1401 Constitution Avenue, Room 4887, Washington, DC 20230 via telephone at 202-235-5467 or by email at mgutierrez@ntia.gov.
Formulas:
Award Identification Number: = EOMONTH([Year 2 - Report Period Ending],6)
Year 3 - Report Period Ending = EOMONTH([Award Identification Number:],6)

## Performance (Tech) Scenario
Sample Use and Adoption Report Scenario
Sample Use and Adoption Scenario – PERFORMANCE (TECHNICAL) REPORT
Recipient A is now three months into their one-year project. They are preparing to submit their Year 1, Period 1 Performance (Technical) Report, due 4/30/2025.
As planned and outlined in the Baseline Report, Recipient A was able to procure and distribute all 80 laptops, 8 desktop computers, and 20 tablets in Year 1, Period 1. Due to vendor delays, Recipient A has only received 25 of the 55 units of CPE. Broadband subscriptions have not yet been purchased; therefore, no unserved households, businesses, or CAIs have received new access.
Recipient A anticipated that two new positions—an IT Director and IT Assistant—would be created and filled by the end of Year 1, Period 1. The recipient initiated both positions but was only able to hire an IT Director. More applications were received than expected for the IT Assistant position and interviews were not concluded as of the end of the semi-annual period. However, Recipient A will still report that 2 positions were funded in 6b. New Positions.
In the Baseline Report, Recipient A also anticipated holding one workforce development training (with an estimated attendance of 25) and one digital literacy training (estimated attendance of 100) during Year 1, Period 1. Both trainings occurred according to schedule. However, attendance at the workforce development training was lower than expected (actual attendance of 19) due to severe weather that prevented some staff from attending the in-person event. Interest in the digital literacy training was higher than expected, leading to a larger attendance than anticipated (actual attendance of 164).
Recipient A had their Finance Director cross-check the Budget Execution section of their Performance (Technical) Report with their Federal Financial Report (SF-425) before submission. Recipient A pulled the Actual Budget column data from their application's SF-424A, which is the most recently approved budget.

## Performance (Tech) Rep
Select Project Type Below
Use and Adoption
OMB Control No. 0669-0039 Expiration Date: 06/30/2028
TRIBAL BROADBAND CONNECTIVITY PROGRAM PERFORMANCE (TECHNICAL) REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: | Recipient A |  |  |  | Award Identification Number: |  |  |  | NT25TBC0000000
| Recipient Street Address: | 123 Street Lane |  |  |  | Report Submission Date (MM/DD/YYYY): |  |  |  | 2025-04-01
| City, State, Zip Code: | Washington, DC 20001 |  |  |  | Final Report:
| UEI Number: | 123456789 | [7 empty] | No
| Period of Performance Start Date (MM/DD/YYYY): | 2025-01-01 |  |  |  | Period of Performance End Date (MM/DD/YYYY): |  |  |  | 2025-12-31
| Report Period Start Date (MM/DD/YYYY): | 2025-01-01 |  |  |  | Report Period End Date (MM/DD/YYYY): |  |  |  | 2025-03-31
BROADBAND USE & ADOPTION AND INFRASTRUCTURE MILESTONES/KEY INDICATORS
INFRASTRUCTURE DEPLOYMENT AND PLANNING PROJECT MILESTONE CATEGORIES
1 | Use the following table to indicate the percent completion for all Infrastructure Deployment and/or Planning activities. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Percent Complete column, provide the percent of completion for all infrastructure activities conducted with TBCP funds. Determine the percent completion based on the actual completion of activities (not by expenditure of budget). If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular milestone, enter “NA" in both the Percent Complete and Narrative columns. For the purposes of this section, equipment procurement refers to activities associated with identifying and procuring necessary equipment for your project. Equipment deployment refers to all activities associated with the installation of equipment purchased as part of your TBCP project. If you are using milestone 1k Other (please specify), include a brief description of the milestone by typing over the portion that reads (please specify). For milestones 1l and 1m, describe accomplishments and challenges faced during the last semi-annual (6 month) period.
MILESTONE CATEGORIES
|  |  | Percent Complete |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
1a. Overall Project
1b. Environmental Assessment
1c. Network Design
1d. Rights Of Way
1e. Construction Permits And Other Approvals
1f. Site Preparation
1g. Equipment Procurement
1h. Network Build (all components - owned, leased, Indefeasible Rights of Use, etc.)
1i. Equipment Deployment
1j. Network Testing
1k. Other (please specify)
1l. Please describe significant project accomplishments during this reporting period funded through TBCP grant. (600 words or less)
1m. Please describe any challenges to achieving project accomplishments during this reporting period funded through TBCP grant. (600 words or less)
INFRASTRUCTURE DEPLOYMENT NETWORK BUILD PROGRESS
2 | Use the following table to provide information about the progress of your Infrastructure Deployment and/or Planning project. Except for 2h, report information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the completion figure for all infrastructure deployment activities conducted with TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular milestone, enter “NA" in the Total and Narrative columns. For the purposes of this section new wireless links refers to the number of new wireless transmissions--comprised of a source node (transmitter) to a destination node (receiver)--that exist due to TBCP funding; wireless links may be middle or last mile. New towers refers to any towers that are constructed, leased, and/or upgraded or retrofitted with grant funds; this includes in-situ vertical structures that are outfitted with network equipment (water towers, rooftops, steeples, etc.). New interconnection points refers to any new physical connections where traffic is routed from one network to another created as a result of TBCP funds. If using the milestones 2j Other (please specify), include a brief description of the milestone by typing over the portion that reads (please specify).
NETWORK BUILD PROGRESS
|  |  | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
2a. Number of new fiber miles (aerial or underground) constructed or upgraded with TBCP funds
2b. Number of fiber miles leased with TBCP funds
2c. Number of existing fiber miles upgraded with TBCP funds
2d. Number of new wireless links created through TBCP funds
2e. Number of new towers constructed with TBCP funds
2f. Number of new interconnection points created through TBCP funds
2g. Number of signed agreements with broadband wholesalers or last mile provider from TBCP funds
2h. Number of potential agreements (i.e., agreements currently being negotiated) with broadband wholesalers or last mile providers from TBCP funds (This number should NOT be reported cumulatively)
2i. Obtained licenses: 2.5 (EBS), 3.5 (CBRS) from TBCP funds
2j. Other (please specify)
INFRASTRUCTURE DEPLOYMENT KEY INDICATORS
3 | Use the following table to provide the number of unserved tribal households, unserved tribal households at or below 150% of the poverty line, unserved tribal businesses, and unserved tribal community anchor institutions (CAIs) connected to broadband infrastructure through your Infrastructure Deployment project. Report all information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the completion figure for all connections made as a result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns. In each section, provide the number of structures connected according to connectivity speed (100/20 and 25/3) and connectivity type (wireless, fiber).
PROJECTED NUMBER OF SUBSCRIBERS AND SPEED
| SUBSCRIBER TYPE | SPEED TYPE | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 3a. Unserved Tribal Households | Number of Unserved Tribal Households connected to broadband infrastructure
Number of previously Unserved Tribal Households with broadband availability at speeds of at least 100/20 Mbps through TBCP funds
Number of previously Unserved Tribal Households with broadband availability at speeds of at least 25/3 Mbps through TBCP funds
Number of Unserved Tribal Households connected to broadband infrastructure by copper or DSL cable line
Number of previously Unserved Tribal Households with broadband availability by wireless connection through TBCP funds
Number of previously Unserved Tribal Households with broadband availability by fiber optic connection through TBCP funds
| 3b. Tribal Households | Number of Tribal Households connected to broadband infrastructure
Number of Tribal Households connected to broadband infrastructure at speeds of at least 100/20
Number of Tribal Households connected to broadband infrastructure at speeds of at least 25/3
Number of Tribal Households connected to broadband infrastructure by copper or DSL cable line
Number of Tribal Households connected to broadband infrastructure by wireless connection
Number of Tribal Households connected to broadband infrastructure by fiber optic connection
| 3c. Unserved Tribal Households At or Below 150% of the Poverty Line | Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at speeds of at least 100/20 Mbps through TBCP funds
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at speeds of 25/3 Mbps through TBCP funds
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by copper or DSL cable line
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by wireless connection through TBCP funds
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by fiber optic connection through TBCP funds
| 3d. Unserved Tribal Businesses | Number of Unserved Tribal Businesses connected to broadband infrastructure
Number of previously Unserved Tribal Businesses with broadband availability at speeds of at least 100/20 Mbps through TBCP funds
Number of previously Unserved Tribal Businesses with broadband availability at speeds of at least 25/3 Mbps through TBCP funds
Number of Unserved Tribal Businesses connected to broadband infrastructure by copper or DSL cable line
Number of Unserved Tribal Businesses connected to broadband infrastructure by wireless connection through TBCP funds
Number of Unserved Tribal Businesses connected to broadband infrastructure by fiber optic connection through TBCP funds
| 3e. Unserved Tribal Community Anchor Institutions | Number of Unserved Tribal Community Anchor Institutions connected to broadband infrastructure
Number of previously Unserved Tribal CAIs with broadband availability at speeds of at least 100/20 Mbps through TBCP funds
Number of previously Unserved Tribal CAIs with broadband availability at speeds of at least 25/3 Mbps through TBCP funds
Number of Unserved Tribal Community Anchor Institutions connected to broadband infrastructure by copper or DSL cable line
Number of Unserved Tribal CAIs connected to broadband infrastructure by wireless connection through TBCP funds
Number of Unserved Tribal CAIs connected to broadband infrastructure by fiber optic connection through TBCP funds
BROADBAND USE & ADOPTION KEY INDICATORS
4 | Use the following table to provide the number of unserved tribal households, unserved tribal businesses, and unserved tribal community anchor institutions (CAIs) that receive new access to broadband through your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the completion figure for the number of structures passed/serviceable and the number of structures with new access to broadband as a result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns. For the purposes of this section, new access refers to tribal households, businesses, and CAIs within your service area that received access to qualifying broadband services (25/3 Mbps or greater) for the first time (i.e., previously had no broadband connectivity or connectivity of less than 25/3 Mbps) as a result of TBCP funds.
PROJECTED NUMBER OF SUBSCRIBERS AND SPEED
| BENEFICIARY TYPE | ACCESS TYPE | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 4a. Unserved Tribal Households | Number of Unserved Tribal Households passed/serviceable
|  | Number of previously unserved Tribal Households with new access through TBCP-funded broadband subscriptions (i.e. prepayment) | 0 |  |  |  | NA
| 4b. Tribal Households | Number of Tribal Households passed/serviceable
Number of Tribal Households with new access
| 4c. Unserved Tribal Households At or Below 150% of the Poverty Line | Number of Unserved Tribal Households At or Below 150% of the Poverty Line passed/serviceable
Number of previously unserved Tribal Households At or Below 150% of the Poverty Line with new access through TBCP funds
| 4d. Unserved Tribal Businesses | Number of Unserved Tribal Businesses passed/serviceable
Number of previously unserved Tribal Businesses with new access through TBCP funds
| 4e. Unserved Tribal Community Anchor Institutions | Number of Unserved Tribal Community Anchor Institutions passed/serviceable
Number of previously unserved Tribal Community Anchor Institutions with new access through TBCP funds
BROADBAND USE & ADOPTION DEMOGRAPHIC INDICATORS
5 | Use the following table to provide demographic data for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the Tribal demographic data for your service area. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns. In most instances, demographic indicators will not change throughout the lifetime of your project.
DEMOGRAPHIC INDICATORS
| SUBSCRIBER TYPE | ESTIMATED POPULATION IN SERVICE AREA | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 5a. Unserved Tribal Population | Number of Unserved Native American/Alaska Native/Native Hawaiian Households in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Tribal Businesses in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Community Anchor Institutions in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Households At or Below 150% of the Poverty Line in funded service area
| 5b. Tribal Population | Number of Tribal Households in funded service area
Number of Tribal Businesses in funded service area
Number Tribal Community Anchor Institutions in funded service area
Number of Tribal Households At or Below 150% of the Poverty Line in funded service area
INFRASTRUCTURE DEPLOYMENT, PLANNING, AND BROADBAND USE & ADOPTION WORKFORCE INDICATORS
6 | Use the following table to provide workforce data for your Infrastructure Deployment, Planning, or Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the figures for telework access, positions created and filled, and workforce development trainings held as a result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns.
WORKFORCE INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 6a. Telework | Number of individuals with ability to telework prior to receiving TBCP grant funds
Number of individuals with ability to telework after receiving TBCP grant funds
| 6b. New Positions | Number of positions funded by TBCP funds | 2 |  |  |  | NA
Number of new positions filled through TBCP funds
| 6c. Participation in Workforce Development Trainings | Number of individuals who attended a TBCP-funded workforce development training event | 19 |  |  |  | Severe weather prevented some staff from attending.
| 6d. Workforce Development Trainings | Number of workforce development training events held with TBCP funds | 1 |  |  |  | NA
BROADBAND USE & ADOPTION EDUCATIONAL SUCCESS INDICATORS
7 | Use the following table to provide educational data for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the figures for any educational success indicators achieved as result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns.
EDUCATIONAL SUCCESS INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 7a. Access to Online Learning | Number of individuals with ability to participate in online learning prior to receiving TBCP grant funds
Number of individuals with ability to participate in online learning after receiving TBCP grant funds
| 7b. Participation in Online Learning | Number of individuals who attended online learning classes
Number of individuals who attended virtual/in-person school activities
| 7c. Parental Participation in School Activities | Number of parents/legal-guardians who attended virtual/in-person school activities
| 7d. High School Enrollment and Completion | Number of individuals enrolled in high school
Number of individuals who successfully exited high school program with degree (diploma/GED)
| 7e. School Participation in Remote or Hybrid Learning | Number of schools in program
Number of schools engaged in remote or hybrid learning model through TBCP funds
| 7f. School Participation in In-Person Learning | Number of schools in program
Number of schools engaged in in-person learning model through TBCP funds
| 7g. School Participation in Hybrid Learning | Number of schools in program
Number of schools engaged in hybrid learning model through TBCP funds
BROADBAND USE & ADOPTION TELEHEALTH INDICATORS
8 | Use the following table to provide telehealth data for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the figures for any telehealth indicators achieved as result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns.
TELEHEALTH INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 8a. Access to Telehealth Services | Number of individuals with ability to participate in telehealth services prior to receiving TBCP grant funds
Number of individuals with ability to participate in telehealth service after receiving TBCP grant funds
| 8b. New Access to Telehealth Services | Number of individuals with new access to telehealth services
| 8c. Telehealth Appointments Scheduled | Estimated number of telehealth appointments scheduled
BROADBAND USE & ADOPTION DIGITAL INCLUSION INDICATORS
9 | Use the following table to provide digital inclusion data for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the figures for any digital inclusion indicators achieved as result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns.
DIGITAL INCLUSION INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 9a. Participation in Affordable Broadband Connectivity Program | Number of households in affordable broadband connectivity program
| 9b. Digital Literacy Trainings | Number of digital literacy training events held with TBCP funds | 1 |  |  |  | NA
| 9c. Tribal Programs Transitioned to Online Platform | Number of Tribal programs transitioned to online platform previously (before receiving TBCP grant funds)
Number of Tribal programs transitioned to online platform with TBCP funds
| 9d. Devices Distributed to Individuals | Number of individuals given device
| 9e. Devices Distributed to Households | Number of households given device
| 9f. Devices Distributed to Other Entities (i.e., community anchor institutions, schools, Tribal businesses) | Number of other entities given device
BROADBAND USE & ADOPTION TYPE OF INTERNET DEVICES
10 | Use the following table to provide the internet connectivity devices that you have acquired for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. For each row, select the appropriate device from the dropdown menu in the Device Type column, provide the number of units purchased with grant funds under the Number of Devices column, and provide the total cost under the Total Cost column. If you select the device type Other, provide a brief description of the device in the Total Cost column.
| Device Type |  | Number of Devices |  |  |  | Total Cost
| Laptop |  | 80 |  |  |  | 80000
| Computer |  | 8 |  |  |  | 12000
| Router |  | 25 |  |  |  | 2500
| Tablet |  | 20 |  |  |  | 6000
INFRASTRUCTURE DEPLOYMENT, PLANNING, AND BROADBAND USE & ADOPTION TYPE OF COLLABORATORS
11 | Use the following table to provide information about the contractors, subrecipients, and unfunded collaborators involved in your TBCP project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Collaborator Organization Type column, indicate whether the participating organization is a Contractor, Subrecipient, or Informal Unfunded Collaborator by selecting an option from the dropdown menu. Enter the full name of the participating organization’s point of contact (POC) in the Collaborator POC Name, and the point of contact’s email address in the Collaborator POC Email column. Indicate whether the participant is Funded or Unfunded by selecting an option from the dropdown menu in the Funded or Unfunded Collaboration column.
COLLABORATORS
| Collaborator Organization Type | Collaborator Organization Name | Collaborator POC Name | Collaborator POC Email |  |  |  | Funded or Unfunded Collaboration
| Contractor | CPE Installers, Inc | Adam Smith | Asmith@CPEInstallers.com |  |  |  | Funded
| Contractor | Technology Training Solutions | Jane Train | Jtrain@TTS.org |  |  |  | Funded
INFRASTRUCTURE DEPLOYMENT BUDGET EXECUTION DETAILS
12 | Use the following table to provide budget execution details for your Infrastructure Deployment and/or Planning project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Actual Budget column, record the budgeted totals from your most recently approved SF-424C. In the Total Funds Expended column, list the amount of grant funds expended to date per each cost category. The total listed at the bottom of the Total Funds Expended column should match the Federal expenditures reported in your SF-425.
| COST CLASSIFICATION |  |  |  | Actual Budget |  |  |  |  | Total Funds Expended
12a. Administrative and legal expenses
12b. Land, structures, rights-of way, appraisals, etc.
12c. Relocation expenses and payments
12d. Architectural and engineering fees
12e. Other architectural and engineering fees
12f. Project inspection fees
12g. Site work
12h. Demolition and removal
12i. Construction
12j. Equipment
12k. Miscellaneous
| Subtotal |  |  |  | 0 |  |  |  |  | 0
12l. Contingencies
| Totals |  |  |  | 0 |  |  |  |  | 0
BROADBAND USE & ADOPTION BUDGET EXECUTION DETAILS
13 | Use the following table to provide budget execution details for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Actual Budget column, record the budgeted totals from your most recently approved SF-424A. In the Total Funds Expended column, list the amount of grant funds expended to date per each cost category. The total listed at the bottom of the Total Funds Expended column should match the Federal expenditures reported in your SF-425.
| GRANT PROGRAM, FUNCTION, OR ACTIVITY |  |  |  | Actual Budget |  |  |  |  | Total Funds Expended
| 13a. Personnel |  |  |  | 60000 |  |  |  |  | 25000
| 13b. Fringe Benefits |  |  |  | 6000 |  |  |  |  | 2500
| 13c. Travel |  |  |  | 0 |  |  |  |  | 0
| 13d. Equipment |  |  |  | 103500 |  |  |  |  | 0
| 13e. Supplies |  |  |  | 20000 |  |  |  |  | 15000
| 13f. Contractual |  |  |  | 2000 |  |  |  |  | 1000
| 13g. Construction |  |  |  | 0 |  |  |  |  | 0
| 13h. Other |  |  |  | 83500 |  |  |  |  | 82500
| 13i. Total Direct Charges (sum of 13a thru 13h) |  |  |  | 275000 |  |  |  |  | 126000
| 13j. Indirect Charges |  |  |  | 0 |  |  |  |  | 0
| 13k. Totals (sum of 13i+13j) |  |  |  | 275000 |  |  |  |  | 126000
INFRASTRUCTURE DEPLOYMENT OTHER INDICATORS
14 | Use the following table to provide the maximum download and upload speeds in Megabits per second (Mbps) available as a result of TBCP funds. This information should not be reported cumulatively. Report the highest speeds available as of the end of the semi-annual reporting period captured in this report. For the purposes of this section, eligible area refers to your proposed service area.
| Project Speed | [7 empty] | Download |  | Upload
| Outcome |  | Questions
| 14a. Maximum available speed upon project completion |  | What is the maximum available speeds for Tribal Households in your eligible area?
What is the maximum available speeds for Tribal Businesses in your eligible area?
What is the maximum available speeds for Tribal CAIs in your eligible area?
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: |  |  |  |  | Telephone (area code, number and extension): |  |  |  | 123-456-7890 ext 1
John Smith
| Signature of Certifying Official: |  |  |  |  | Email Address: |  |  |  | JohnSmith@RA.org
/s/ John Smith
[6 empty] | Date: |  |  |  | 2025-04-01
PAPERWORK REDUCTION ACT (PRA) OF 1995 (Public Law 104-13) STATEMENT OF PUBLIC BURDEN: An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information subject to the requirements of the Paperwork Reduction Act unless that collection of information displays a currently valid OMB Control Number 0690-0039. Public reporting burden for these reports is estimated to average 40 hours per response. This burden includes time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate to Margaret Gutierrez, Director, Tribal Broadband Connectivity Program, National Telecommunications and Information Administration, U.S Department of Commerce, 1401 Constitution Avenue, Room 4887, Washington, DC 20230 via telephone at 202-235-5467 or by email at mgutierrez@ntia.gov.

## Annual Scenario
Sample Use and Adoption Report Scenario
Sample Use and Adoption Scenario – ANNUAL REPORT
Recipient A is now one year into their one-year project and all grant activities are complete. The recipient is preparing to submit their Year 1 Annual Report. Because they are a one year project, this will be Recipient A's first and only Annual Report.
Over the past year, Recipient A has procured and distributed 80 laptops to tribal households; 55 routers/CPE to unserved tribal households, businesses, and CAIs; 8 computers to tribal CAIs; and 20 tablets to tribal staff.
Recipient A also purchased broadband subscriptions for 80 tribal households, 2 tribal businesses, and 3 tribal CAIs. Thirty of these households had an Internet connection at speeds of 25/3 prior to the receipt of grant funds. The remaining 50 households, 2 businesses, and 3 CAIs were previously unserved. A contractor (CPE Installers, Inc) installed customer premise equipment in the 50 unserved households, 2 unserved businesses, and 3 unserved CAIs. At the end of Year 1, all 80 households, 2 businesses, and 3 CAIs were connected to broadband at speeds of 100/20 Mbps or greater.
During Year 1, Recipient A held one workforce development training for Tribal staff and three digital literacy trainings. The Tribe hired the contractor Technology Training Solutions to design and implement the trainings. Two positions–an IT Director and IT Assistant–were funded by the TBCP grant.
Use and Adoption projects do not require addendums; therefore, Recipient A wrote "NA" in Addendums A, B, and C.
In addition, Recipient A took care not to include any Personally Identifiable Information (PII) or other sensitive data in their Annual Report, since this report is considered public and will be shared with Congress.

## Annual Report
Does your project contain an infrastructure build component?
No
OMB Control No. 0690-0039 Expiration Date: 06/30/2028
TRIBAL BROADBAND CONNECTIVITY PROGRAM ANNUAL REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: | Recipient A | Award Identification Number: |  | NT25TBC0000000
| Recipient Street Address: | 123 Street Lane | Report Submission Date (MM/DD/YYYY): |  | 2026-01-01
| City, State, Zip Code: | Washington, DC 20001
| UEI Number: | 123456789
| Period of Performance Start Date (MM/DD/YYYY): | 2025-01-01 | Period of Performance End Date (MM/DD/YYYY): |  | 2025-12-31
| Report Period Start Date (MM/DD/YYYY): | 2025-01-01 | Report Period End Date (MM/DD/YYYY): |  | 2025-12-31
1 | Infrastructure Deployment Recipients: Provide the total number of project locations (Tribal households, businesses, and community anchor institutions) that are passed/serviceable due to TBCP grant funds. Attach shapefiles for the connected locations and service area. (600 words or less) Use and Adoption Recipients: N/a Planning Recipients: N/a
2 | Describe all project activities completed with grant funds during the past annual report period. (600 words or less)
3 | List all contractors that received grant funds and briefly explain what the funds were used for. Report this item cumulatively from the start of the award through the end of the annual report period captured in this report. If your project does not include contractors, write “NA”. (600 words or less)
Two contractors received grant funds during the reporting period. CPE Installers, Inc. received grant funds to install Customer Premise Equipment in 50 households, 2 businesses, and 3 CAIs. Technology Training Solutions was hired to design and implement 1 workforce development training and 3 digital literacy trainings.
4 | Describe how your organization (i.e. the grant recipient) expended grant funds. Report this item cumulatively from the start of the award through the end of the annual report period captured in this report. (600 words or less)
Recipient A procured and distributed 80 laptops to tribal households; 55 routers/CPE to unserved tribal households, businesses, and CAIs; 8 computers to tribal CAIs; and 20 tablets to tribal staff. Recipient A also purchased broadband subscriptions for 80 tribal households, 2 tribal businesses, and 3 tribal CAIs.
5 | List all subrecipients that received grant funds and briefly explain what the funds were used for. Report this item cumulatively from the start of the award through the end of the annual report period captured in this report. If your project does not include subrecipients, write “NA”. (600 words or less)
NA
6 | Describe any challenges your organization experienced while conducting your TBCP project during the past annual report period. Explain how you addressed those challenges. (600 words or less)
Over the past year, barriers to broadband Use and Adoption activities included supply chain bottlenecks which delayed the delivery of CPE, severe weather which prevented several employees from attending the workforce development training, and a slower-than-anticipated timeline for CPE installation. There was little that Recipient A could do to address the CPE supply chain bottleneck. Instead, Recipient A took advantage of the procurement delay to meet with the contractor CPE Installers Inc. and hammer out an installation plan and timeline for tribal households, businesses, and CAIs. CPE installation itself was delayed by internal circumstances at CPE Installers, Inc. Fortunately, Recipient A and CPE Installers built sufficient lag time into the CPE installation plan that this did not require an extension of the project timeline. Recipient A estimated that 25 tribal employees would attend the workforce development training. However, due to severe weather, only 19 staff members were able to attend. To address this, Recipient A and Technology Training Solutions, the contractor that planned and conducted the workforce development training, agreed to record the training. The recording was then sent to all staff.
7 | Describe how your organization met and maintained broadband requirements, as outlined in the NOFO purpose areas below. (600 words or less) Infrastructure Deployment: Broadband infrastructure deployment, including (but not limited to) support for the establishment of carrier-neutral submarine cable landing stations. Use and Adoption: Projects that promote the adoption and use of broadband services, including: affordable broadband programs, such as providing free or reduced-cost broadband service and preventing disconnection of existing broadband service; distance learning; telehealth; digital inclusion efforts; and broadband adoption activities. Planning: Proposals to conduct planning, engineering, feasibility, or sustainability studies as part of the necessary steps to develop a technological solution for broadband deployment.
Recipient A promoted the adoption and use of broadband services by deploying a subsidized broadband program, organizing 3 digital literacy trainings, and equipping Tribal members with the technology to telework and access telehealth.
8 | Describe all project achievements during the annual reporting period. (600 words or less)
During the reporting period, Recipient A held three digital literacy trainings that were highly-attended (164 attendees at the first training, 113 at the second training, and 107 at the third training). The project also created two new jobs (IT Director and IT Assistant) which were both filled by tribal members. Grant funds were used to provide devices and subsidized broadband service to 80 households, 2 businesses, and 3 CAIs. Fifty of the households were previously unserved.
9 | INFRASTRUCTURE DEPLOYMENT PROJECTS: Using the Excel spreadsheet template titled "TBCP Reports Addendum A", please provide an updated count of Households within each of the eligible census block groups along with their Location ID that you connected to your network. The locations should match and conform to the Federal Communications Commission (FCC) Broadband Serviceable Location Fabric, which is a unique identifier for the geographic coordinates and the address(es) associated with each location.
10 | INFRASTRUCTURE DEPLOYMENT PROJECTS: Using the Excel spreadsheet template titled "TBCP Reports Addendum B", please provide an updated count of Tribal Businesses within each of the eligible census block groups along with their Location ID that you connected to your network. The locations should match and conform to the Federal Communications Commission (FCC) Broadband Serviceable Location Fabric, which is a unique identifier for the geographic coordinate and the address(es) associated with each location.
11 | INFRASTRUCTURE DEPLOYMENT PROJECTS: Using the Excel spreadsheet template titled "TBCP Reports Addendum C", please provide an updated count of Community Anchor Institutions (CAIs) within each of the eligible census block groups along with their Location ID that you connected to your network. The locations should match and conform to the Federal Communications Commission (FCC) Broadband Serviceable Location Fabric, which is a unique identifier for the geographic coordinates and the address(es) associated with each location.
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: |  |  | Telephone (area code, number and extension): |  | 123-456-7890 ext 1
John Smith
| Signature of Certifying Official: |  |  | Email Address: |  | JohnSmith@RA.org
/s/ John Smith
|  |  |  | Date: |  | 2025-12-31
PAPERWORK REDUCTION ACT (PRA) OF 1995 (Public Law 104-13) STATEMENT OF PUBLIC BURDEN: An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information subject to the requirements of the Paperwork Reduction Act unless that collection of information displays a currently valid OMB Control Number 0690-0039. Public reporting burden for these reports is estimated to average 40 hours per response. This burden includes time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate to Margaret Gutierrez, Director, Tribal Broadband Connectivity Program, National Telecommunications and Information Administration, U.S Department of Commerce, 1401 Constitution Avenue, Room 4887, Washington, DC 20230 via telephone at 202-235-5467 or by email at mgutierrez@ntia.gov.
In accordance with the Tribal Broadband Connectivity Program (TBCP) Notice of Funding Opportunity (NOFO), Section F.5.d Transmission of Reports to Congress, NTIA intends to post TBCP Annual Reports on its website to make available to applicable Committee members and the public. Recipients are offered the opportunity to object to disclosure of any specific portion of the Annual Report through a redaction process. Do not include personally identifiable information that you do not want to be disclosed or accessed outside of your organization.

## TBCP Reports Addendum A
Does your project contain an infrastructure build component?
No
OMB Control No. 0690-0039 Expiration Date: 06/30/2028
TRIBAL BROADBAND CONNECTIVITY PROGRAM REPORTS ADDENDUM A
Recipient Organization: |  | Recipient A |  |  | Award Identification Number: | [7 empty] | NT25TBC0000000
Recipient Street Address: |  | 123 Street Lane |  |  | Report Submission Date (MM/DD/YYYY): | [7 empty] | 2026-01-01
City, State, Zip Code: |  | Washington, DC 20001 |  |  | UEI Number: | [7 empty] | 123456789
Reporting Period Start Date (MM/DD/YYYY): |  | 2025-01-01 |  |  | Report Type: |  |  |  | Baseline Report
Reporting Period End Date (MM/DD/YYYY): |  | 2025-12-31 | [6 empty] | Annual Report
Household Locations in the Service Area
The Location ID is the Fabric ID associated with the Federal Communications Commission maps required by the Broadband Deployment Broadband Deployment Accuracy and Technology Availability (DATA) Act, Pub. L. No. 116-130, 134 Stat. 228 (2020) (codified at 47 U.S.C. §§ 641-646) (Broadband DATA Maps). The “location_id” data element is a unique identifier for the location served. A Location ID should be included for each location in the Broadband Serviceable Location Fabric when the Fabric is made available to filers. Number of units refers to one location that has multiple units within that one location. Infrastructure Deployment projects should insert rows at the bottom of the table to report additional location data if needed.
Location ID | Street Address | City | State | ZIP |  | Latitude |  | Longitude |  | Census Block Group | # of Units | Fixed Technology Code | Open For Sale (OFS) Date | Deployed Date | Provider ID | Brand Name | Maxdown | Maxup
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | John Smith |  |  |  |  | Telephone (area code, number and extension): | [5 empty] | 123-456-7890 ext 1
| Signature of Certifying Official: | /s/ John Smith |  |  |  |  | Email Address: | [5 empty] | JohnSmith@RA.org
[7 empty] | Date: | [5 empty] | 2025-12-31
PAPERWORK REDUCTION ACT (PRA) OF 1995 (Public Law 104-13) STATEMENT OF PUBLIC BURDEN: An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information subject to the requirements of the Paperwork Reduction Act unless that collection of information displays a currently valid OMB Control Number 0690-0039. Public reporting burden for these reports is estimated to average 40 hours per response. This burden includes time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate to Margaret Gutierrez, Director, Tribal Broadband Connectivity Program, National Telecommunications and Information Administration, U.S Department of Commerce, 1401 Constitution Avenue, Room 4887, Washington, DC 20230 via telephone at 202-235-5467 or by email at mgutierrez@ntia.gov.

## TBCP Reports Addendum B
Does your project contain an infrastructure build component?
No
OMB Control No. 0690-0039 Expiration Date: 06/30/2028
TRIBAL BROADBAND CONNECTIVITY PROGRAM REPORTS ADDENDUM B
Recipient Organization: |  | Recipient A |  |  | Award Identification Number: | [7 empty] | NT25TBC0000000
Recipient Street Address: |  | 123 Street Lane |  |  | Report Submission Date (MM/DD/YYYY): | [7 empty] | 2026-01-01
City, State, Zip Code: |  | Washington, DC 20001 |  |  | UEI Number: | [7 empty] | 123456789
Reporting Period Start Date (MM/DD/YYYY): |  | 2025-01-01 |  |  | Report Type: |  |  |  | Baseline Report
Reporting Period End Date (MM/DD/YYYY): |  | 2025-12-31 | [6 empty] | Annual Report
Tribal Business Locations in the Service Area
The Location ID is the Fabric ID associated with the Federal Communications Commission maps required by the Broadband Deployment Broadband Deployment Accuracy and Technology Availability (DATA) Act, Pub. L. No. 116-130, 134 Stat. 228 (2020) (codified at 47 U.S.C. §§ 641-646) (Broadband DATA Maps). The “location_id” data element is a unique identifier for the location served. A Location ID should be included for each location in the Broadband Serviceable Location Fabric when the Fabric is made available to filers. Number of units refers to one location that has multiple units within that one location. Infrastructure Deployment projects should insert rows at the bottom of the table to report additional location data if needed.
Location ID | Street Address | City | State | ZIP |  | Latitude |  | Longitude |  | Census Block Group | # of Units | Fixed Technology Code | Open For Sale (OFS) Date | Deployed Date | Provider ID | Brand Name | Maxdown | Maxup
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | John Smith |  |  |  |  | Telephone (area code, number and extension): | [5 empty] | 123-456-7890 ext 1
| Signature of Certifying Official: | /s/ John Smith |  |  |  |  | Email Address: | [5 empty] | JohnSmith@RA.org
[7 empty] | Date: | [5 empty] | 2025-12-31
PAPERWORK REDUCTION ACT (PRA) OF 1995 (Public Law 104-13) STATEMENT OF PUBLIC BURDEN: An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information subject to the requirements of the Paperwork Reduction Act unless that collection of information displays a currently valid OMB Control Number 0690-0039. Public reporting burden for these reports is estimated to average 40 hours per response. This burden includes time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate to Margaret Gutierrez, Director, Tribal Broadband Connectivity Program, National Telecommunications and Information Administration, U.S Department of Commerce, 1401 Constitution Avenue, Room 4887, Washington, DC 20230 via telephone at 202-235-5467 or by email at mgutierrez@ntia.gov.

## TBCP Reports Addendum C
Does your project contain an infrastructure build component?
No
OMB Control No. 0690-0039 Expiration Date: 06/30/2028
TRIBAL BROADBAND CONNECTIVITY PROGRAM REPORTS ADDENDUM C
Recipient Organization: |  | Recipient A |  |  | Award Identification Number: | [7 empty] | NT25TBC0000000
Recipient Street Address: |  | 123 Street Lane |  |  | Report Submission Date (MM/DD/YYYY): | [7 empty] | 2026-01-01
City, State, Zip Code: |  | Washington, DC 20001 |  |  | UEI Number: | [7 empty] | 123456789
Reporting Period Start Date (MM/DD/YYYY): |  | 2025-01-01 |  |  | Report Type: |  |  |  | Baseline Report
Reporting Period End Date (MM/DD/YYYY): |  | 2025-12-31 | [6 empty] | Annual Report
Community Anchor Institution (CAI) Locations in the Service Area
The Location ID is the Fabric ID associated with the Federal Communications Commission maps required by the Broadband Deployment Broadband Deployment Accuracy and Technology Availability (DATA) Act, Pub. L. No. 116-130, 134 Stat. 228 (2020) (codified at 47 U.S.C. §§ 641-646) (Broadband DATA Maps). The “location_id” data element is a unique identifier for the location served. A Location ID should be included for each location in the Broadband Serviceable Location Fabric when the Fabric is made available to filers. Number of units refers to one location that has multiple units within that one location. Infrastructure Deployment projects should insert rows at the bottom of the table to report additional location data if needed.
Location ID | Street Address | City | State | ZIP |  | Latitude |  | Longitude |  | Census Block Group | # of Units | Fixed Technology Code | Open For Sale (OFS) Date | Deployed Date | Provider ID | Brand Name | Maxdown | Maxup | CAI Type
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: | John Smith |  |  |  |  | Telephone (area code, number and extension): | [5 empty] | 123-456-7890 ext 1
| Signature of Certifying Official: | /s/ John Smith |  |  |  |  | Email Address: | [5 empty] | JohnSmith@RA.org
[7 empty] | Date: | [5 empty] | 2025-12-31
PAPERWORK REDUCTION ACT (PRA) OF 1995 (Public Law 104-13) STATEMENT OF PUBLIC BURDEN: An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information subject to the requirements of the Paperwork Reduction Act unless that collection of information displays a currently valid OMB Control Number 0690-0039. Public reporting burden for these reports is estimated to average 40 hours per response. This burden includes time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate to Margaret Gutierrez, Director, Tribal Broadband Connectivity Program, National Telecommunications and Information Administration, U.S Department of Commerce, 1401 Constitution Avenue, Room 4887, Washington, DC 20230 via telephone at 202-235-5467 or by email at mgutierrez@ntia.gov.