## Performance (Technical) Report
Select Project Type Below
OMB Control No. 0690-0039 Expiration Date: 06/30/2027
TRIBAL BROADBAND CONNECTIVITY PROGRAM PERFORMANCE (TECHNICAL) REPORT
GENERAL INFORMATION
GENERAL | Recipient Organization: |  |  |  |  | Award Identification Number:
| Recipient Street Address: |  |  |  |  | Report Submission Date (MM/DD/YYYY):
| City, State, Zip Code: |  |  |  |  | Final Report:
| UEI Number: | [8 empty] | No
| Period of Performance Start Date (MM/DD/YYYY): |  |  |  |  | Period of Performance End Date (MM/DD/YYYY):
| Report Period Start Date (MM/DD/YYYY): |  |  |  |  | Report Period End Date (MM/DD/YYYY):
BROADBAND USE & ADOPTION AND INFRASTRUCTURE MILESTONES/KEY INDICATORS
INFRASTRUCTURE DEPLOYMENT AND PLANNING PROJECT MILESTONE CATEGORIES
1 | Use the following table to indicate the percent completion for all Infrastructure Deployment and/or Planning activities. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Percent Complete column, provide the percent of completion for all infrastructure activities conducted with TBCP funds. Determine the percent completion based on the actual completion of activities (not by expenditure of budget). If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular milestone, enter “NA" in both the Percent Complete and Narrative columns. For the purposes of this section, equipment procurement refers to activities associated with identifying and procuring necessary equipment for your project. Equipment deployment refers to all activities associated with the installation of equipment purchased as part of your TBCP project. If you are using milestone 1k Other (please specify), include a brief description of the milestone by typing over the portion that reads (please specify). For milestones 1l and 1m, describe accomplishments and challenges faced during the last semi-annual (6 month) period.
MILESTONE CATEGORIES
|  |  | Percent Complete |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
1a. Overall Project
1b. Environmental Assessment
1c. Network Design
1d. Rights Of Way
1e. Construction Permits And Other Approvals
1f. Site Preparation
1g. Equipment Procurement
1h. Network Build (all components - owned, leased, Indefeasible Rights of Use, etc.)
1i. Equipment Deployment
1j. Network Testing
1k. Other (please specify)
1l. Please describe significant project accomplishments during this reporting period funded through TBCP grant. (600 words or less)
1m. Please describe any challenges to achieving project accomplishments during this reporting period funded through TBCP grant. (600 words or less)
INFRASTRUCTURE DEPLOYMENT NETWORK BUILD PROGRESS
2 | Use the following table to provide information about the progress of your Infrastructure Deployment and/or Planning project. Except for 2h, report information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the completion figure for all infrastructure deployment activities conducted with TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular milestone, enter “NA" in the Total and Narrative columns. For the purposes of this section new wireless links refers to the number of new wireless transmissions--comprised of a source node (transmitter) to a destination node (receiver)--that exist due to TBCP funding; wireless links may be middle or last mile. New towers refers to any towers that are constructed, leased, and/or upgraded or retrofitted with grant funds; this includes in-situ vertical structures that are outfitted with network equipment (water towers, rooftops, steeples, etc.). New interconnection points refers to any new physical connections where traffic is routed from one network to another created as a result of TBCP funds. If using the milestones 2j Other (please specify), include a brief description of the milestone by typing over the portion that reads (please specify).
NETWORK BUILD PROGRESS
|  |  | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
2a. Number of new fiber miles (aerial or underground) constructed or upgraded with TBCP funds
2b. Number of fiber miles leased with TBCP funds
2c. Number of existing fiber miles upgraded with TBCP funds
2d. Number of new wireless links created through TBCP funds
2e. Number of new towers constructed with TBCP funds
2f. Number of new interconnection points created through TBCP funds
2g. Number of signed agreements with broadband wholesalers or last mile provider from TBCP funds
2h. Number of potential agreements (i.e., agreements currently being negotiated) with broadband wholesalers or last mile providers from TBCP funds (This number should NOT be reported cumulatively)
2i. Obtained licenses: 2.5 (EBS), 3.5 (CBRS) from TBCP funds
2j. Other (please specify)
INFRASTRUCTURE DEPLOYMENT KEY INDICATORS
3 | Use the following table to provide the number of unserved tribal households, unserved tribal households at or below 150% of the poverty line, unserved tribal businesses, and unserved tribal community anchor institutions (CAIs) connected to broadband infrastructure through your Infrastructure Deployment project. Report all information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the completion figure for all connections made as a result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns. In each section, provide the number of structures connected according to connectivity speed (100/20 and 25/3) and connectivity type (wireless, fiber).
PROJECTED NUMBER OF SUBSCRIBERS AND SPEED
| SUBSCRIBER TYPE | SPEED TYPE | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 3a. Unserved Tribal Households | Number of Unserved Tribal Households connected to broadband infrastructure
Number of previously Unserved Tribal Households with broadband availability at speeds of at least 100/20 Mbps through TBCP funds
Number of previously Unserved Tribal Households with broadband availability at speeds of at least 25/3 Mbps through TBCP funds
Number of Unserved Tribal Households connected to broadband infrastructure by copper or DSL cable line
Number of Unserved Tribal Households with broadband availability by wireless connection through TBCP funds
Number of previously Unserved Tribal Households with broadband availability by fiber optic connection through TBCP funds
| 3b. Tribal Households | Number of Tribal Households connected to broadband infrastructure
Number of Tribal Households connected to broadband infrastructure at speeds of at least 100/20
Number of Tribal Households connected to broadband infrastructure at speeds of at least 25/3
Number of Tribal Households connected to broadband infrastructure by copper or DSL cable line
Number of Tribal Households connected to broadband infrastructure by wireless connection
Number of Tribal Households connected to broadband infrastructure by fiber optic connection
| 3c. Unserved Tribal Households At or Below 150% of the Poverty Line | Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at speeds of at least 100/20 Mbps through TBCP funds
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure at speeds of 25/3 Mbps through TBCP funds
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by copper or DSL cable line
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by wireless connection through TBCP funds
Number of Unserved Tribal Households At or Below 150% of the Poverty Line connected to broadband infrastructure by fiber optic connection through TBCP funds
| 3d. Unserved Tribal Businesses | Number of Unserved Tribal Businesses connected to broadband infrastructure
Number of previously Unserved Tribal Businesses with broadband availability at speeds of at least 100/20 Mbps through TBCP funds
Number of previously Unserved Tribal Businesses with broadband availability at speeds of at least 25/3 Mbps through TBCP funds
Number of Unserved Tribal Businesses connected to broadband infrastructure by copper or DSL cable line
Number of Unserved Tribal Businesses connected to broadband infrastructure by wireless connection through TBCP funds
Number of Unserved Tribal Businesses connected to broadband infrastructure by fiber optic connection through TBCP funds
| 3e. Unserved Tribal Community Anchor Institutions | Number of Unserved Tribal Community Anchor Institutions connected to broadband infrastructure
Number of previously Unserved Tribal CAIs with broadband availability at speeds of at least 100/20 Mbps through TBCP funds
Number of previously Unserved Tribal CAIs with broadband availability at speeds of at least 25/3 Mbps through TBCP funds
Number of Unserved Tribal Community Anchor Institutions connected to broadband infrastructure by copper or DSL cable line
Number of Unserved Tribal CAIs connected to broadband infrastructure by wireless connection through TBCP funds
Number of Unserved Tribal CAIs connected to broadband infrastructure by fiber optic connection through TBCP funds
BROADBAND USE & ADOPTION KEY INDICATORS
4 | Use the following table to provide the number of unserved tribal households, unserved tribal businesses, and unserved tribal community anchor institutions (CAIs) that receive new access to broadband through your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the completion figure for the number of structures passed/serviceable and the number of structures with new access to broadband as a result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns. For the purposes of this section, new access refers to tribal households, businesses, and CAIs within your service area that received access to qualifying broadband services (25/3 Mbps or greater) for the first time (i.e., previously had no broadband connectivity or connectivity of less than 25/3 Mbps) as a result of TBCP funds.
PROJECTED NUMBER OF SUBSCRIBERS AND SPEED
| BENEFICIARY TYPE | ACCESS TYPE | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 4a. Unserved Tribal Households | Number of Unserved Tribal Households passed/serviceable
Number of previously unserved Tribal Households with new access through TBCP-funded broadband subscriptions (i.e. prepayment)
| 4b. Tribal Households | Number of Tribal Households passed/serviceable
Number of Tribal Households with new access
| 4c. Unserved Tribal Households At or Below 150% of the Poverty Line | Number of Unserved Tribal Households At or Below 150% of the Poverty Line passed/serviceable
Number of previously unserved Tribal Households At or Below 150% of the Poverty Line with new access through TBCP funds
| 4d. Unserved Tribal Businesses | Number of Unserved Tribal Businesses passed/serviceable
Number of previously unserved Tribal Businesses with new access through TBCP funds
| 4e. Unserved Tribal Community Anchor Institutions | Number of Unserved Tribal Community Anchor Institutions passed/serviceable
Number of previously unserved Tribal Community Anchor Institutions with new access through TBCP funds
BROADBAND USE & ADOPTION DEMOGRAPHIC INDICATORS
5 | Use the following table to provide demographic data for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the Tribal demographic data for your service area. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns. In most instances, demographic indicators will not change throughout the lifetime of your project.
DEMOGRAPHIC INDICATORS
| SUBSCRIBER TYPE | ESTIMATED POPULATION IN SERVICE AREA | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 5a. Unserved Tribal Population | Number of Unserved Native American/Alaska Native/Native Hawaiian Households in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Tribal Businesses in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Community Anchor Institutions in funded service area
Number of Unserved Native American/Alaska Native/Native Hawaiian Households At or Below 150% of the Poverty Line in funded service area
| 5b. Tribal Population | Number of Tribal Households in funded service area
Number of Tribal Businesses in funded service area
Number Tribal Community Anchor Institutions in funded service area
Number of Tribal Households At or Below 150% of the Poverty Line in funded service area
INFRASTRUCTURE DEPLOYMENT, PLANNING, AND BROADBAND USE & ADOPTION WORKFORCE INDICATORS
6 | Use the following table to provide workforce data for your Infrastructure Deployment, Planning, or Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the figures for telework access, positions created and filled, and workforce development trainings held as a result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns.
WORKFORCE INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 6a. Telework | Number of individuals with ability to telework prior to receiving TBCP grant funds
Number of individuals with ability to telework after receiving TBCP grant funds
| 6b. New Positions | Number of positions funded by TBCP funds
Number of new positions filled through TBCP funds
| 6c. Participation in Workforce Development Trainings | Number of individuals who attended a TBCP-funded workforce development training event
| 6d. Workforce Development Trainings | Number of workforce development training events held with TBCP funds
BROADBAND USE & ADOPTION EDUCATIONAL SUCCESS INDICATORS
7 | Use the following table to provide educational data for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the figures for any educational success indicators achieved as result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns.
EDUCATIONAL SUCCESS INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 7a. Access to Online Learning | Number of individuals with ability to participate in online learning prior to receiving TBCP grant funds
Number of individuals with ability to participate in online learning after receiving TBCP grant funds
| 7b. Participation in Online Learning | Number of individuals who attended online learning classes
Number of individuals who attended virtual/in-person school activities
| 7c. Parental Participation in School Activities | Number of parents/legal-guardians who attended virtual/in-person school activities
| 7d. High School Enrollment and Completion | Number of individuals enrolled in high school
Number of individuals who successfully exited high school program with degree (diploma/GED)
| 7e. School Participation in Remote or Hybrid Learning | Number of schools in program
Number of schools engaged in remote or hybrid learning model through TBCP funds
| 7f. School Participation in In-Person Learning | Number of schools in program
Number of schools engaged in in-person learning model through TBCP funds
| 7g. School Participation in Hybrid Learning | Number of schools in program
Number of schools engaged in hybrid learning model through TBCP funds
BROADBAND USE & ADOPTION TELEHEALTH INDICATORS
8 | Use the following table to provide telehealth data for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the figures for any telehealth indicators achieved as result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns.
TELEHEALTH INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 8a. Access to Telehealth Services | Number of individuals with ability to participate in telehealth services prior to receiving TBCP grant funds
Number of individuals with ability to participate in telehealth service after receiving TBCP grant funds
| 8b. New Access to Telehealth Services | Number of individuals with new access to telehealth services
| 8c. Telehealth Appointments Scheduled | Estimated number of telehealth appointments scheduled
BROADBAND USE & ADOPTION DIGITAL INCLUSION INDICATORS
9 | Use the following table to provide digital inclusion data for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Total column, provide the figures for any digital inclusion indicators achieved as result of TBCP funds. If the figure provided in this semi-annual report differs from the corresponding cell in your most recent Baseline Report, explain the reasons for the variance in the Narrative column. If your project does not include a particular indicator, enter “NA" in the Total and Narrative columns.
DIGITAL INCLUSION INDICATORS
| OUTCOMES | QUESTIONS | Total |  |  |  | Narrative (Describe reasons for variance from baseline plan or subsequent written updates provided to your Program Officer)
| 9a. Participation in Affordable Broadband Connectivity Program | Number of households in affordable broadband connectivity program
| 9b. Digital Literacy Trainings | Number of digital literacy training events held with TBCP funds
| 9c. Tribal Programs Transitioned to Online Platform | Number of Tribal programs transitioned to online platform previously (before receiving TBCP grant funds)
Number of Tribal programs transitioned to online platform with TBCP funds
| 9d. Devices Distributed to Individuals | Number of individuals given device
| 9e. Devices Distributed to Households | Number of households given device
| 9f. Devices Distributed to Other Entities (i.e., community anchor institutions, schools, Tribal businesses) | Number of other entities given device
BROADBAND USE & ADOPTION TYPE OF INTERNET DEVICES
10 | Use the following table to provide the internet connectivity devices that you have acquired for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. For each row, select the appropriate device from the dropdown menu in the Device Type column, provide the number of units purchased with grant funds under the Number of Devices column, and provide the total cost under the Total Cost column. If you select the device type Other, provide a brief description of the device in the Total Cost column.
| Device Type |  | Number of Devices |  |  |  | Total Cost
INFRASTRUCTURE DEPLOYMENT, PLANNING, AND BROADBAND USE & ADOPTION TYPE OF COLLABORATORS
11 | Use the following table to provide information about the contractors, subrecipients, and unfunded collaborators involved in your TBCP project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Collaborator Organization Type column, indicate whether the participating organization is a Contractor, Subrecipient, or Informal Unfunded Collaborator by selecting an option from the dropdown menu. Enter the full name of the participating organization’s point of contact (POC) in the Collaborator POC Name, and the point of contact’s email address in the Collaborator POC Email column. Indicate whether the participant is Funded or Unfunded by selecting an option from the dropdown menu in the Funded or Unfunded Collaboration column.
COLLABORATORS
| Collaborator Organization Type | Collaborator Organization Name | Collaborator POC Name | Collaborator POC Email |  |  |  | Funded or Unfunded Collaboration
INFRASTRUCTURE DEPLOYMENT BUDGET EXECUTION DETAILS
12 | Use the following table to provide budget execution details for your Infrastructure Deployment and/or Planning project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Actual Budget column, record the budgeted totals from your most recently approved SF-424C. In the Total Funds Expended column, list the amount of grant funds expended to date per each cost category. The total listed at the bottom of the Total Funds Expended column should match the Federal expenditures reported in your SF-425.
| COST CLASSIFICATION |  |  |  | Actual Budget |  |  |  |  | Total Funds Expended
12a. Administrative and legal expenses
12b. Land, structures, rights-of way, appraisals, etc.
12c. Relocation expenses and payments
12d. Architectural and engineering fees
12e. Other architectural and engineering fees
12f. Project inspection fees
12g. Site work
12h. Demolition and removal
12i. Construction
12j. Equipment
12k. Miscellaneous
| Subtotal |  |  |  | 0 |  |  |  |  | 0
12l. Contingencies
| Totals |  |  |  | 0 |  |  |  |  | 0
BROADBAND USE & ADOPTION BUDGET EXECUTION DETAILS
13 | Use the following table to provide budget execution details for your Use and Adoption project. Report this information cumulatively from the start of your award through the end of the semi-annual reporting period captured in this report. In the Actual Budget column, record the budgeted totals from your most recently approved SF-424A. In the Total Funds Expended column, list the amount of grant funds expended to date per each cost category. The total listed at the bottom of the Total Funds Expended column should match the Federal expenditures reported in your SF-425.
| GRANT PROGRAM, FUNCTION, OR ACTIVITY |  |  |  | Actual Budget |  |  |  |  | Total Funds Expended
13a. Personnel
13b. Fringe Benefits
13c. Travel
13d. Equipment
13e. Supplies
13f. Contractual
13g. Construction
13h. Other
| 13i. Total Direct Charges (sum of 13a thru 13h) |  |  |  | 0 |  |  |  |  | 0
13j. Indirect Charges
| 13k. Totals (sum of 13i+13j) |  |  |  | 0 |  |  |  |  | 0
INFRASTRUCTURE DEPLOYMENT OTHER INDICATORS
14 | Use the following table to provide the maximum download and upload speeds in Megabits per second (Mbps) available as a result of TBCP funds. This information should not be reported cumulatively. Report the highest speeds available as of the end of the semi-annual reporting period captured in this report. For the purposes of this section, eligible area refers to your proposed service area.
| Project Speed | [7 empty] | Download |  | Upload
| Outcome |  | Questions
| 14a. Maximum available speed upon project completion |  | What is the maximum available speeds for Tribal Households in your eligible area?
What is the maximum available speeds for Tribal Businesses in your eligible area?
What is the maximum available speeds for Tribal CAIs in your eligible area?
CERTIFICATION | I certify to the best of knowledge and belief that this report is correct and complete for performance of activities for the purposes set forth in the award documents.
| Typed or printed name and title of Authorized Certifying Official: |  |  |  |  | Telephone (area code, number and extension):
| Signature of Certifying Official: |  |  |  |  | Email Address:
Date:
PAPERWORK REDUCTION ACT (PRA) OF 1995 (Public Law 104-13) STATEMENT OF PUBLIC BURDEN: An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information subject to the requirements of the Paperwork Reduction Act unless that collection of information displays a currently valid OMB Control Number 0690-0039. Public reporting burden for these reports is estimated to average 40 hours per response. This burden includes time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate to Margaret Gutierrez, Director, Tribal Broadband Connectivity Program, National Telecommunications and Information Administration, U.S Department of Commerce, 1401 Constitution Avenue, Room 4887, Washington, DC 20230 via telephone at 202-235-5467 or by email at mgutierrez@ntia.gov.

## BABA Reporting Addendum
OMB Control No. 0660-0047 Expiration Date: 7/31/2028
TBCP II BABA Compliance: Recipient Reporting Tracker for Finished Waived Electronics
Recipient Organization: |  |  |  | Award Identification Number:
Recipient Street Address: |  |  |  | Report Submission Date (MM/DD/YYYY):
City, State, Zip Code: |  |  |  | UEI Number:
Reporting Period Start Date (MM/DD/YYYY): |  |  |  | Report Type: | Performance (Technical) Report
Reporting Period End Date (MM/DD/YYYY):
Finished Waived Electronics
Manufacturer | Electronic Category | HS Code (10 digit) | Product Identifier (e.g., SKU, Product ID, etc.) | Common language description of product function | Country of Origin | Quantity | Electronic Category Types
Router
Switch
Power System
Optical Amplifiers
Radio
Power Management System
Antennas & Antenna Arrays
FR Conditioning
Network-facing optic pluggables
Other
CERTIFICATION | I hereby certify that to the best of my knowledge and belief all Iron, Steel, Manufactured Products, and Construction Materials installed on this project by my company and by any and all subcontractors and suppliers for this project comply with the Build America, Buy America Act (BABA) requirements of the Infrastructure Investment and Jobs Act of 2021 (Pub. L. 117- 58, §§ 70901-70952), or are the subject of a waiver approved by the U.S. Department of Commerce.
| Typed or Printed Name and Title of Authorized Certifying Official |  |  | Telephone (Area code, number, and extension):
| Signature of Certifying Official |  |  | Email address:
Date:
PAPERWORK REDUCTION ACT (PRA) OF 1995 (Public Law 104-13) STATEMENT OF PUBLIC BURDEN: An agency may not conduct or sponsor, and a person is not required to respond to, a collection of information subject to the requirements of the Paperwork Reduction Act unless that collection of information displays a currently valid OMB Control Number 0690-0039. Public reporting burden for this report is estimated to average 5 hours per response. This burden includes time for reviewing instructions, searching existing data sources, gathering and maintaining the data needed, and completing and reviewing the collection of information. Send comments regarding this burden estimate to Jennifer Duane, Director, Grants Management, Administration, and Compliance, Office of Internet Connectivity and Growth, National Telecommunications and Information Administration, U.S Department of Commerce, 1401 Constitution Avenue, Room 4887, Washington, DC 20230 via telephone at (202) 482-2048 or by email at jduane@ntia.gov.